## Original Sheet (hidden)
Tag | Job Site | Job site description | Activity Description | Custom Text 1 | Customer Contact | act req date | Customer | act list2 | Activity name | If complete put finish date on actual date |  | If Erect task and finish date put date on actual build date
Scafftag No: | Location1: | Location2: | Description: | Request No | Requester | Request Received Date | Trade | Load Limit | Task | Status | Start Date: | Finish Date:
5000 | AAAA | AAAA | build access scaffold on base of AAAF vessel for lagging and painting | 1996 | David Goodes | 2016-01-22 | Electrical | Med Duty | ERECT | Complete | 2016-01-22 | 2016-01-22
5000 | AAAA | AAAA | Dismantle & re-build access scaffold on base of AAAF vessel for lagging and painting | 2651 | David Goodes | 2016-01-22 | Electrical | Med Duty | MODIFY | Complete | 2016-01-22 | 2016-01-22
5001 | AGRU 2 | Agru MRU Tank Next to Murcury Sample Panel | Modify Scaffold and remove 1mx1m in floor for installation of cable ladder. No tag attached | 3204 | Geoff Haren | 2016-04-13 | Electrical | Med Duty | TAKEOVER | Complete | 2016-04-18 | 2016-04-17
5001 | AGRU 2 | Agru MRU Tank Next to Murcury Sample Panel | Modify Scaffold and remove 1mx1m in floor for installation of cable ladder. | 3731-1 | Geoff Haren | 2016-04-28 | Electrical | Med Duty | MODIFY | complete | 2016-04-02 | 2016-04-30
5001 | AGRU 2 | Agru MRU Tank Next to Murcury Sample Panel | Remove 1 meter square section of the existing scaffold to allow for th installation of the cable ladder down to the Mercury Sampling Panel. This will also involve removing a section of the floor boards. | 3731-2 | Geoff Haren | 2016-04-28 | Electrical | Med Duty | MODIFY | complete | 2016-04-28 | 2016-05-05
5002 | UAEA | UAEA | Scaff handrails to be around top of tanks, single access point with board walkdway from tank 1 to tank 2. UACE module west side in construction area | 2037 | Mark Farley | 2016-01-28 | Mechanical | Med Duty | ERECT | Complete | 2016-01-28 | 2016-02-03
5002 | UAEA | AREA 14 UAEA | Modify pipe supports | 2117 | Craig Coombe | 2016-02-06 | Scaffolding | Med Duty | MODIFY | Complete | 2016-02-06 | 2016-02-06
5003 | UAEA | UAEA | Scaff access to remove & install fitting for level gauges. UACE heater medium module, west side of module in construction area | 2038 | Mark Farley | 2016-01-28 | Mechanical | Med Duty | ERECT | Complete | 2016-01-28 | 2016-01-28
5003 | UAEA | AREA 14 UAEA | Modify pipe supports | 2118 | Craig Coombe | 2016-02-06 | Scaffolding | Med Duty | MODIFY | Complete | 2016-02-06 | 2016-02-06
5004 | Jetty | TUG PEN GANGWAYS | Can a third handrail (Scaffold) be added to the Tug Pen Gangways where we have an above head Flourescent light fitting ( 4 light fittings per Gangway). Third handrail is for | 2048 | Mick Elliot | 2016-01-29 | Mechanical | Med Duty | ERECT | Complete | 2016-01-29 | 2016-01-30
5005 | GAEA | GAEA | Barricade around sensor probes on second level - western edge | 2050 | Mick Elliot | 2016-01-29 | Mechanical | Med Duty | ERECT | Complete | 2016-01-29 | 2016-01-29
5005 | GAEA | GAEA | Re-instate Grid mesh & Removal of Scaffold GAEA Level 2 | 4531 | Trevor Pike | 2016-05-25 | Chevron | Med Duty | MODIFY | Not Started | 2016-05-25
5006 | GAEA | GAEA | Build scaffold to enable the installation of gaskets on sensor probe, 2nd level, central/eastern corner | 2051 | Cian Sinclair | 2016-01-29 | Mechanical | Med Duty | ERECT | Complete | 2016-01-29 | 2016-01-29
5007 | UACB | UACB | Catalyst loading hopper to be put in place on the top of vessel 4401 fuelgas. Once hopper is in place the access scaffold needs to be built with sulzers input so theres no confusion like last time | 2052 | Mick Zalmsina | 2016-01-29 | Mechanical | Med Duty | ERECT | Complete | 2016-01-29 | 2016-02-07
5008 | MOF | MOF | Modify existing scaffold to eliminate "LNG Line" Clashes | 2053 | David Bennett | 2016-01-31 | Scaffolding | Med Duty | MODIFY | Complete | 2016-01-31 | 2016-01-31
5009 | MOF | MOF | Modify existing scaffold to eliminate "LNG Line" Clashes | 2054 | David Bennett | 2016-01-31 | Scaffolding | Med Duty | MODIFY | Complete | 2016-01-31 | 2016-01-31
5010 | MOF | MOF | Modify existing scaffold to eliminate "LNG Line" Clashes | 2055 | David Bennett | 2016-01-31 | Scaffolding | Med Duty | MODIFY | Complete | 2016-01-31 | 2016-01-31
5011 | MOF | MOF | Modify existing scaffold to eliminate "LNG Line" Clashes | 2056 | David Bennett | 2016-01-31 | Scaffolding | Med Duty | MODIFY | Complete | 2016-01-31 | 2016-01-31
5012 | MOF | MOF | Modify existing scaffold to eliminate "LNG Line" Clashes | 2057 | David Bennett | 2016-01-31 | Scaffolding | Med Duty | MODIFY | Complete | 2016-01-31 | 2016-01-31
5013 | MOF | MOF | Modify existing scaffold to eliminate "LNG Line" Clashes | 2058 | David Bennett | 2016-01-31 | Scaffolding | Med Duty | MODIFY | Complete | 2016-01-31 | 2016-01-31
5014 | MOF | MOF | Modify existing scaffold to eliminate "LNG Line" Clashes | 2059 | David Bennett | 2016-01-31 | Scaffolding | Med Duty | MODIFY | Complete | 2016-01-31 | 2016-01-31
5015 | MOF | MOF | Modify existing scaffold to eliminate "LNG Line" Clashes | 2060 | David Bennett | 2016-01-31 | Scaffolding | Med Duty | MODIFY | Complete | 2016-01-31 | 2016-01-31
5016 | MOF | MOF | Modify existing scaffold to eliminate "LNG Line" Clashes | 2061 | David Bennett | 2016-01-31 | Scaffolding | Med Duty | MODIFY | Complete | 2016-01-31 | 2016-01-31
5017 | MOF | MOF | Modify existing scaffold to eliminate "LNG Line" Clashes | 2062 | David Bennett | 2016-01-31 | Scaffolding | Med Duty | MODIFY | Complete | 2016-01-31 | 2016-01-31
5018 | MOF | MOF | Modify existing scaffold to eliminate "LNG Line" Clashes | 2063 | David Bennett | 2016-01-31 | Scaffolding | Med Duty | MODIFY | Complete | 2016-01-31 | 2016-01-31
5019 | MOF | MOF | Modify existing scaffold to eliminate "LNG Line" Clashes | 2064 | David Bennett | 2016-01-31 | Scaffolding | Med Duty | MODIFY | Complete | 2016-01-31 | 2016-01-31
5021 | MOF | MOF | Modify existing scaffold to eliminate "LNG Line" Clashes | 2066 | David Bennett | 2016-01-31 | Scaffolding | Med Duty | MODIFY | Complete | 2016-01-31 | 2016-01-31
5022 | MOF | MOF | Modify existing scaffold to eliminate "LNG Line" Clashes | 2067 | David Bennett | 2016-01-31 | Scaffolding | Med Duty | MODIFY | Complete | 2016-01-31 | 2016-01-31
5023 | MOF | MOF | Modify existing scaffold to eliminate "LNG Line" Clashes | 2068 | David Bennett | 2016-01-31 | Scaffolding | Med Duty | MODIFY | Complete | 2016-01-31 | 2016-01-31
5024 | MOF | MOF | Modify existing scaffold to eliminate "LNG Line" Clashes | 2069 | David Bennett | 2016-01-31 | Scaffolding | Med Duty | MODIFY | Complete | 2016-01-31 | 2016-01-31
5025 | MOF | MOF | Modify existing scaffold to eliminate "LNG Line" Clashes | 2070 | David Bennett | 2016-01-31 | Scaffolding | Med Duty | MODIFY | Complete | 2016-01-31 | 2016-01-31
5026 | MOF | MOF | Modify existing scaffold to eliminate "LNG Line" Clashes | 2071 | David Bennett | 2016-01-31 | Scaffolding | Med Duty | MODIFY | Complete | 2016-01-31 | 2016-01-31
5027 | MOF | MOF | Modify existing scaffold to eliminate "LNG Line" Clashes | 2072 | David Bennett | 2016-01-31 | Scaffolding | Med Duty | MODIFY | Complete | 2016-01-31 | 2016-01-31
5028 | MOF | MOF | Modify existing scaffold to eliminate "LNG Line" Clashes | 2073 | David Bennett | 2016-01-31 | Scaffolding | Med Duty | MODIFY | Complete | 2016-01-31 | 2016-01-31
5029 | MOF | MOF | Modify existing scaffold to eliminate "LNG Line" Clashes | 2074 | David Bennett | 2016-01-31 | Scaffolding | Med Duty | MODIFY | Complete | 2016-01-31 | 2016-01-31
5032 | UACB | UACB | Erect Scaffold on UACB module near 250 NB Line (1st level) | 2077 | Cian Sinclair | 2016-02-01 | Mechanical | Med Duty | ERECT | Complete | 2016-02-01 | 2016-02-01
5034 | MOF | I1556 | modification to scaffold where potable water line extends vertically in order to install lagging and sheet metal. Potable water line is priority for start up | 2049 | Tony Bosnovic | 2016-01-29 | Mechanical | Med Duty | MODIFY | Complete | 2016-01-29 | 2016-01-30
5036 | RBDM | RBDM | RBDM south HM-144 Need gin wheel to access 2nd lift for sheet metal works | 2080 | Felise Emelio | 2016-02-02 | Blast/Painting | Med Duty | ERECT | Complete | 2016-02-02 | 2016-02-02
5037 | AAAA | AGRU 1 AAAA | AAAA S/E ground level HM-145 need to modify scaffold to allow access to heat tracem line for insulation works | 2081 | Felise Emelio | 2016-02-02 | Blast/Painting | Med Duty | ERECT | Complete | 2016-02-02 | 2016-02-02
5038 | RBDM | RBDM | RBDM south HM-146 need to drop deck 500mm to allow access to flange for sheet metal works and move boards/tubes back 200mm for clearance | 2082 | Felise Emelio | 2016-02-02 | Blast/Painting | Med Duty | MODIFY | Complete | 2016-02-02 | 2016-02-02
5039 | SASA | SASA | Errect Scaffold for "LNG" Pipe clash on East Side of SASA module top level | 2083 | George Fomin | 2016-02-02 | KJV | Med Duty | ERECT | Complete | 2016-02-02 | 2016-02-02
5040 | ABAA | AGRU 2 ABAA | Build over head protection to allow for simops between CKJV and Downer | 2084 | Mike Knott | 2016-02-02 | Mechanical | Med Duty | ERECT | Complete | 2016-02-02 | 2016-02-02
5041 | Area 10 | AREA 10 yard | Build scaffolding shelfs in containers at olivers yard 40ft | 2085 | Craig Fishlock | 2016-02-02 | Common User | Med Duty | ERECT | Complete | 2016-02-02 | 2016-02-03
5042 | Area 10 | AREA 10 yard | Build scaffolding shelfs in containers at olivers yard 40ft | 2086 | Craig Fishlock | 2016-02-02 | Common User | Med Duty | ERECT | Complete | 2016-02-02 | 2016-02-03
5044 | LPW | Jetty - LPW | LPW HM-147 Need to erect scaffold to access all bolts for chartek repairs and painting works. x2 working decks | 2088 | Felise Emelio | 2016-02-02 | Blast/Painting | Med Duty | ERECT | Complete | 2016-02-02 | 2016-02-02
5045 | RBFD | AREA 9 RBFD | Erect Scaffold for "LNG" Pipe Clash on RBFD Module top level | 2089 | John Simoni | 2016-02-03 | Mechanical | Med Duty | ERECT | Complete | 2016-02-03 | 2016-02-03
5046 | RBFC | AREA 9 RBFC | Erect Scaffold for "LNG" Pipe Clash on RBFC Module top level | 2091 | John Simoni | 2016-02-03 | Mechanical | Med Duty | ERECT | Complete | 2016-02-03 | 2016-02-03
5047 | RBFD | AREA 9 RBFD | Erect Scaffold for "LNG" Pipe Clash on RBFD Module top level | 2090 | John Simoni | 2016-02-03 | Mechanical | Med Duty | ERECT | Complete | 2016-02-03 | 2016-02-03
5048 | DAAA | AREA 14 - DAAA | Erect scaffold on RV platform south east corner of central handrail | 2092 | Cian Sinclair | 2016-02-05 | Mechanical | Med Duty | ERECT | Complete | 2016-02-05 | 2016-02-05
5048 | DAAA | RV platform south east corner of central | Disscaffold on RV platform south east corner of central handrail | 2167 | Daniel Edwards | 2016-02-15 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-02-15 | 2016-02-16
5049 | DAAA | AREA 14 - DAAA | Remove scaffold on south east corner of RV platform | 2093 | Cian Sinclair | 2016-02-05 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-02-05 | 2016-02-05
5050 | DAAA | AREA 14 - DAAA | Extend Scaffold on northen elbow north valve train | 2094 | Cian Sinclair | 2016-02-05 | Mechanical | Med Duty | MODIFY | Complete | 2016-02-05 | 2016-02-05
5051 | DAAA | AREA 14 - DAAA | Build scaff up to underside of first platform mercury absober vessel south edge of vessel | 2095 | Cian Sinclair | 2016-02-05 | Mechanical | Med Duty | ERECT | Complete | 2016-02-05 | 2016-02-05
5052 | DAAA | AREA 14 - DAAA | Build scaffold for hyde, mercury absorber vessel south edge of vessel (second platform - walk up ladder) | 2096 | Cian Sinclair | 2016-02-05 | Mechanical | Med Duty | ERECT | Complete | 2016-02-05 | 2016-02-05
5053 | DAAA | DAAA | Extend scaffold upwards to allow for hide to be constructed | 2078 | Cian Sinclair | 2016-02-01 | Mechanical | Med Duty | ERECT | Complete | 2016-02-01 | 2016-02-04
5053 | DAAA | AREA 14 - DAAA | Build scaffold for hyde, mercury absorber vessel south edge of vessel (first platform) | 2097 | Cian Sinclair | 2016-02-05 | Mechanical | Med Duty | ERECT | Complete | 2016-02-05 | 2016-02-05
5054 | DAAA | AREA 14 - DAAA | Install three scaffold supports for pipe suport on 24371-01 | 2098 | Cian Sinclair | 2016-02-05 | Mechanical | Med Duty | ERECT | Complete | 2016-02-05 | 2016-02-05
5055 | DAAA | AREA 14 - DAAA | Move standard 200mm to the west in order to stop the 'T' piece clashing with existing scaffold, (northern valve) | 2099 | Cian Sinclair | 2016-02-05 | Mechanical | Med Duty | MODIFY | Complete | 2016-02-05 | 2016-02-05
5056 | DAAA | AREA 14 - DAAA | Remove scaffold in order to install 3" spools level 6 (24376-03) | 2100 | Cian Sinclair | 2016-02-05 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-02-05 | 2016-02-05
5057 | DAAA | AREA 14 - DAAA | Extend scaffold in a southerly direction along the length of the HG drains scaffold. (Ground Level - South end of DomGas) | 2101 | Cian Sinclair | 2016-02-05 | Mechanical | Med Duty | ERECT | Complete | 2016-02-05 | 2016-02-05
5058 | DAAA | AREA 14 - DAAA | Build scaffold around valves to enable pipe to be installed, (1st level - Southern end of DomGas) | 2102 | Cian Sinclair | 2016-02-05 | Mechanical | Med Duty | ERECT | Complete | 2016-02-05 | 2016-02-05
5059 | DAAA | AREA 14 - DAAA | Build scaffold on SE corner of Domgas to enable pipe to be installed (1st level - SE corner above Loop Line) | 2103 | Cian Sinclair | 2016-02-05 | Mechanical | Med Duty | ERECT | Complete | 2016-02-05 | 2016-02-05
5060 | DAAA | AREA 14 - DAAA | Modify scaffold to enable welder access pipe spool RV platform level (Eastern edge of DomGas) | 2104 | Cian Sinclair | 2016-02-05 | Mechanical | Med Duty | MODIFY | Complete | 2016-02-05 | 2016-02-05
5061 | ABAA | OLD TAG 1165 -Agru 2 Lvl 1 S/E Area | Temporary edge protection to facilitate the removal of the perment handrails on level 1 south/eastern area (Temp edge protection to be 500mm away from the existing handrails for removal) | 1574 | John Simoni | 2015-11-30 | Mechanical | Med Duty | ERECT | Complete | 2015-11-30 | 2015-12-04
5061 | ABAA | OLD TAG 1165 -Agru 2 Lvl 1 S/E Area | Erect scaffolf for Over head protection | 1948 | David Goodes | 2016-01-16 | Mechanical | Med Duty | MODIFY | Complete | 2016-01-16 | 2016-01-19
5061 | AAAA | AGRU 1 AAAA | Modify existing scaffold, extend overhead protection towards MRU vessel as cloas as possible | 2105 | Mike Knott | 2016-02-05 | Mechanical | Med Duty | MODIFY | Complete | 2016-02-05 | 2016-02-05
5062 | DAAA | AREA 14 - DAAA | Ground east side erect over head protection over weld testing humpy | 2107 | Cian Sinclair | 2016-02-06 | Mechanical | Med Duty | ERECT | Complete | 2016-02-06 | 2016-02-06
5063 | UACA | AREA 14 UACA | Level 1, Fuel Gas center of module reinstate scaffold for painters | 2108 | Craig Coombe | 2016-02-05 | Scaffolding | Med Duty | ERECT | Complete | 2016-02-05 | 2016-02-05
5064 | AAAF | AREA 17 AAAF | Modify on existing scaffold to access top flange on elbow. | 2109 | Shane Shillabeer | 2016-02-05 | Mechanical | Med Duty | MODIFY | Complete | 2016-02-05 | 2016-02-05
5065 | RBAF | AREA 18 RBAF | Scaffold to change out 2 gearbox's on valves | 2110 | Shane Shillabeer | 2016-02-05 | Mechanical | Med Duty | ERECT | Complete | 2016-02-05 | 2016-02-05
5065 | RBAF | WEST END | DISMANTLE 1081 RBAF | 2182 | Shane Shillabeer | 2016-02-16 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-02-17 | 2016-02-17
5065 | RBAF | RBAF | Dismantle Scaffold 5065 for Hertel to continue works on RBAF module | 2314 | Wilfred Nahona | 2016-02-29 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-02-29 | 2016-03-01
5066 | AREA 10 | AREA 10 yard | Erect humpy between 2 containers in APTS laydown yard | 2111 | Tim Whiffin | 2016-02-05 | APTS | Med Duty | ERECT | Complete | 2016-02-05 | 2016-02-05
5067 | Area 10 | container EST | Erect humpie between containers in area 10 work shop old tag 602 | 570 | Tim Whiffin | 2015-07-10 | Mechanical | Med Duty | ERECT | Complete | 2015-07-16 | 2015-08-09
5067 | AREA 10 | AREA 10 yard | dismantle humpy between 2 containers in APTS laydown yard old tag 602 | 2112 | Tim Whiffin | 2016-02-05 | APTS | Med Duty | DISMANTLE | Complete | 2016-02-05 | 2016-02-05
5068 | TAJD | AREA 17 TAJD | Build scaffold deck under fin fan motor 1E-1451-KM1 in module TAJD northern end of train one fin fan deck, Deck needs to be big enough to store coverso it can be left on scaffold. Pictures attaced. | 2113 | Todd Lyons | 2016-02-06 | Mechanical | Med Duty | ERECT | Complete | 2016-02-06 | 2016-02-06
5069 | MAG | Jetty - MAG | Erect hard barricading around gridmesh with access gate | 2114 | Justin Brown | 2016-02-06 | Mechanical | Med Duty | ERECT | Complete | 2016-02-06 | 2016-02-06
5070 | TAJB | AREA 17 TAJB | Erect hard barricading around gridmesh Level 2 | 2115 | Justin Brown | 2016-02-06 | Mechanical | Med Duty | ERECT | Complete | 2016-02-06 | 2016-02-07
5072 | DAAA | AREA 14 DAAA | Erect scaffold on MRU vessel on the 1st platform eastern side of vessel | 2119 | Cian Sinclair | 2016-02-07 | Mechanical | Med Duty | ERECT | Cancelled | 2016-02-07
5075 | UACA | FUEL GAS | Build Scaff for Brackets and Field Welds, Full Encapsulation. | 2123 | Robert Hanley | 2015-10-01 | Mechanical | Med Duty | ERECT | Complete | 2015-10-01 | 2015-10-10
5076 | GAAC | AREA 18 GAAC | Construct supports for the hipps valve so that when piping is removed the valves cant fall over under testing | 2116 | Justin Brown | 2016-02-06 | Mechanical | Med Duty | ERECT | Cancelled | 2016-02-10
5077 | RBAF | AREA 18 RBAF | Scaffold to change out 2 gearbox's on valves | 2124 | Shane Shillabeer | 2016-02-07 | Mechanical | Med Duty | ERECT | Complete | 2016-02-07 | 2016-02-07
5077 | RBAF | RBAF | Dismantle Scaffold 5077 for Hertel to continue works on RBAF module | 2313 | Wilfred Nahona | 2016-02-29 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-02-29 | 2016-03-01
5078 | LPW | LPW | LPW HM-150 Need access to complete insulations scope. Keep 250mm clearance from pipe works. | 0-1 | Felise Emelio | 2016-02-11 | Hertel | Med Duty | ERECT | Complete | 2016-02-11 | 2016-02-11
5078 | LPW | LPW | LPW HM-150 Need access to complete insulations scope. Keep 250mm clearance from pipe works. | 0-2 | Felise Emelio | 2016-02-11 | Hertel | Med Duty | DISMANTLE | Complete | 2016-02-11 | 2016-04-29
5080 | Area 10 | Area 18 | Build scaffold Humpy for new stores area at inlet laydown, Scaffold will be alongside of 1x 40FT container approx 12mtrs x5mtrs, Exact location and design to be shown by Matty H once area established ETA 10-12-16 | 2128 | Matty Hodges | 2016-02-11 | Common User | Med Duty | ERECT | Complete | 2016-02-10 | 2016-02-11
5082 | UACA | UACA | Eect Scaffold to accesss cable tray ladder support | 2130 | Mathew Poole | 2016-02-11 | Electrical | Med Duty | ERECT | Complete |  | 2016-02-13
5082 | GAEA | GAEA tag 5082 | Dismantle 5082 | 2481 | John Watson | 2016-03-12 | Chevron | Med Duty | DISMANTLE | Not Started | 2016-03-13
5084 | TACA | TACA | Scaffold to be erected to access cable tray clash ground level | 2132 | John Young | 2016-02-11 | Mechanical | Med Duty | ERECT | Cancelled | 2016-02-11
5085 | GAGA | GAGA | Scaffold is required to enable the installation of roof sheets as per model shots | 2133-1 | Thomas Murphy | 2016-02-07 | Mechanical | Med Duty | ERECT | Complete | 2016-02-11 | 2016-02-15
5085 | GAGA | GAGA | Scaffold is required to enable the installation of roof sheets as per model shots | 2133-2 | Thomas Murphy | 2016-02-07 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-02-11 | 2016-04-29
5087 | ABAG | ABAG | Build and modify scaffold to allow handrail and walkway installation on RV deck. Scaffold will need to allow for spark encapsulation. | 2135 | David Goodes | 2016-02-11 | Electrical | Med Duty | ERECT | Complete | 2016-02-11 | 2016-02-15
5089 | TAJD | TAJD - fin fans | Build scaffold deck under fin fan motor 1E1451-KM1 in module TAJD northern end of train one fin fan deck, Deck needs to be big enough to store cover so it can be left on scaffold | 2138 | Craig Coombe | 2016-02-12 | Scaffolding | Med Duty | ERECT | Complete |  | 2016-02-13
5090 | GAGA | GAGA - Inlet | Scaffold required for supports | 2139 | Shane Shillabeer | 2016-02-12 | Mechanical | Med Duty | ERECT | Complete | 2016-02-13 | 2016-02-25
5091 | TADA | TADA | Scaffold to be erected to access pipe support level 2 below level 3 north end of module Clash Number:1003 | 2141 | John Young | 2016-02-12 | Mechanical | Med Duty | ERECT | Complete |  | 2016-02-12
5092 | MD5W | Capstan MD5W | Pre-commissioning require a scaffold lifting frame erected at Capstan MD5W to enable the lifting of the top of the Capstan head. This will allow access to electrical connection boxes for inspection / rectification works. | 2143 | Brad Scheers | 2016-02-12 | Common User | Med Duty | ERECT | Complete | 2016-02-13 | 2016-02-22
5093 | DAAA | DAAA - RV Platform | erect an extention to access pipe spools & supports on southern end of DOMGAS RV platform | 2146 | Daniel Edwards | 2016-02-13 | Mechanical | Med Duty | ERECT | Complete |  | 2016-02-15
5094 | DAAA | DAAA - RV Platform | Need Deck erected to access the welding of the structural support | 2145 | Daniel Edwards | 2016-02-13 | Mechanical | Med Duty | ERECT | Complete | 2016-02-14 | 2016-02-15
5095 | DAAA | DAAA - RV Platform | Erect hard Hard barricade for hydes | 2144 | Daniel Edwards | 2016-02-13 | Mechanical | Med Duty | ERECT | Complete |  | 2016-02-15
5095 | DAAA | DAAA RV Platform | Dismantle Welding humpies top Level | 2544 | Paul Velonias | 2016-03-15 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-21 | 2016-03-25
5096 | TADA | TADA Level 4 | Hard barricades entry needed to merry up to attached | 2147 | John Young | 2016-02-13 | Mechanical | Med Duty | ERECT | Complete |  | 2016-02-14
5097 | GAHJ | HM-156 GAHJ west Tag G0383 | HM-156 GAHJ west Tag G0383 need to extend deck west to access insulation works. Drop deck 500mm and extend west. Remove plywood around pipes 200mm clearance is needed. | 2148 | Felise Emelio | 2016-02-13 | Blast/Painting | Med Duty | ERECT | Complete | 2016-02-14 | 2016-03-01
5098 |  | RBAK-RBAL | RBAK-RBAL HM-157 Need access for insulation works. 200mm clearance above pipe is needed. Deck 1.8m below pipe works. | 2149 | Felise Emelio | 2016-02-13 | Blast/Painting | Med Duty | ERECT | Complete | 2016-02-14 | 2016-03-04
5099 | GAHL | GAHL | GAHL HM-158 need access to pipe for insulation works on whole of line. | 2150 | Felise Emelio | 2016-02-13 | Blast/Painting | Med Duty | ERECT | Complete | 2016-02-14 | 2016-03-03
5100 | RBAQ | RBAQ north | RBAQ north HM-159 modify scaffold to complete insulations scope. Keep 250mm clearance from pipe works. | 2151 | Felise Emelio | 2016-02-13 | Blast/Painting | Med Duty | ERECT | Complete | 2016-02-14 | 2016-03-02
5101 | SANA | SANA Pumps | SANA A - Erect Frames | 2152 | Thomas Murphy | 2016-02-13 | Mechanical | Med Duty | ERECT | Complete | 2016-02-14 | 2016-02-24
5102 | SANA | SANA Pumps | SANA B - Erect Frames | 2153 | Thomas Murphy | 2016-02-13 | Mechanical | Med Duty | ERECT | Complete | 2016-02-14 | 2016-02-23
5103 | ABAH | AGRU 2, ABAH | Build scaffold to allow for elbow removal for hydro. Must allow for blind install, and pink steel removal in direct proximity. will also require handrail for gridmesh removal-superviser to advise | 2154 | David Goodes | 2016-02-13 | Electrical | Med Duty | ERECT | Complete | 2016-02-13 | 2016-02-16
5103 | ABAH | AGRU 2, ABAH Ground level south/east corner | ABAH HM-1947 Ground level south/east corner need to modify scaffolds to allow for insulation works. 225mm clearance is needed around all of pipe where handrails are hard up against pipe. | 3197 | Felise Emelio | 2016-04-13 | Hertel | Med Duty | MODIFY | Complete | 2016-04-17 | 2016-04-18
5104 | AAAH | AGRU 1, AAAH | existing scaffold to be modified to allow for 1" spool lagging (in yellow) speak with supervisor for further details | 2155 | David Goodes | 2016-02-14 | Electrical | Med Duty | ERECT | Complete | 2016-02-15 | 2016-03-01
5105 | ABAH | AGRU 2, - ABAH | build scaffold on north and south trunions for guide install build the same as AGRU 1, starting on the southside see supervisor for further details | 2156 | David Goodes | 2016-02-14 | Electrical | Med Duty | ERECT | Complete | 2016-02-15 | 2016-02-22
5106 | ABAA | AGRU 2, - ABAA | build scaffold to allow for strut brace fit up and welding will also capture the spring can installation see supervisor for further details | 2157 | David Goodes | 2016-02-14 | Electrical | Med Duty | ERECT | Complete | 2016-02-15 | 2016-03-01
5107 | ABAA | AGRU 2, ABAH - ABAA | build scaffold to allow for strut brace fit up and welding this scaffold will need to be build once spool is in final position see supervisor for further details | 2158 | David Goodes | 2016-02-14 | Electrical | Med Duty | ERECT | Complete | 2016-02-15 | 2016-03-01
5108 | Area 19 | CBI laydown Yard | erect scaffold around valve to remove gearbox. | 2159 | Shane Shillabeer | 2016-02-14 | Mechanical | Med Duty | ERECT | Complete | 2016-02-14 | 2016-02-15
5108 | Area 19 | CBI yard | Dismantle 5108 | 2230 | Shane Shillabeer | 2016-02-21 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-02-22 | 2016-03-08
5109 | TBAA | TBAA 2V-1201 | Build internal scaffold access for demolition / hot works and instalation of mechanial equipment in 2V-1201 | 2160 | Andrew Ledingham | 2016-02-14 | Mechanical | Med Duty | ERECT | Complete | 2016-02-18 | 2016-02-18
5109 | TBAA | TBAA | Adjustment is required on scaffold in vessel Vessel: 2V-1201 Drop deck height two stars | 2419 | Andrew Ledingham | 2016-03-08 | Mechanical | Med Duty | MODIFY | Complete | 2016-03-08 | 2016-03-08
5110 | SAYN | SAYL-SAYN | SAYL-SAYN HM-161 need to reinstate ladder access to deck and insure all penetrations are filled in. keep all tubes/boards/ply 250mm from pipe works. | 2161 | Felise Emelio | 2016-02-14 | Blast/Painting | Med Duty | ERECT | Complete | 2016-02-15 | 2016-03-01
5111 | LPE | LPE HM- 160 | LPE HM- 160 Need to reinstate scaffold to allow insulation works. Keep all structural tubes 500mm of pipe and 250mm boards/puddys. | 2162 | Felise Emelio | 2016-02-14 | Blast/Painting | Med Duty | ERECT | Complete | 2016-02-16 | 2016-02-16
5112 | TBAA | TBBA TRAIN 2 RE-BOILERS | Build Scaffold to access flanges, and welding on reboilers 2E-1601. 2E-1612, 2E- 1613, Area: TRAIN 2 Re-Boilers TBBA -2E-1601 | 2163 | Mick Zalmsina | 2016-02-15 | Mechanical | Med Duty | ERECT | Complete | 2016-02-16 | 2016-02-23
5112 | TBBA | TBBA TRAIN 2 RE-BOILERS | As per attached model shots and scaffold tag numbers. | 4222 | Brett Taane | 2016-05-11 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-14 | 2016-05-15
5113 | TBAA | TBBA TRAIN 2 RE-BOILERS | Build Scaffold to access flanges, and welding on reboilers 2E-1601. 2E-1612, 2E- 1613, Area: TRAIN 2 Re-Boilers TBBA-2E-1612 TOP | 2164 | Mick Zalmsina | 2016-02-15 | Mechanical | Med Duty | ERECT | Complete | 2016-02-16 | 2016-02-23
5113 | TBBA | TBBA TRAIN 2 RE-BOILERS | Tag # 5113 to be dismantled. | 3105 | James Halliday | 2016-04-09 | Hertel | Med Duty | DISMANTLE | Complete | 2016-04-11 | 2016-05-15
5114 | TBBA | TBBA TRAIN 2 RE-BOILERS | Build Scaffold to access flanges, and welding on reboilers 2E-1601. 2E-1612, 2E- 1613, Area: TRAIN 2 Re-Boilers TBBA - 2E-1612 BOTTOM | 2165 | Mick Zalmsina | 2016-02-15 | Mechanical | Med Duty | ERECT | Complete | 2016-02-16 | 2016-03-23
5114 | TBBA | TBBA TRAIN 2 RE-BOILERS | As per attached model shots and scaffold tag numbers. | 4219 | Brett Taane | 2016-05-11 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-14 | 2016-05-14
5115 | TBBA | TRAIN 2 Re-Boilers TBBA -2E-1604 | Build Scaffold to access flanges, and welding on reboilers 2E-1601. 2E-1612, 2E- 1613, Area: TRAIN 2 Re-Boilers TBBA-2E - 1613 | 2166 | Mick Zalmsina | 2016-02-15 | Mechanical | Med Duty | ERECT | Complete | 2016-02-16 | 2016-03-25
5115 | TBBA | TBBA South | Tag # 5115 to be dismantled. | 3106 | James Halliday | 2016-04-09 | Hertel | Med Duty | DISMANTLE | Complete | 2016-04-11 | 2016-05-15
5116 | DAAA | DAAA – Top of RV Platform | Erect hard barricade to enable gridmesh to be repaired, Area: DAAA – Top of RV Platform | 2168 | Daniel Edwards | 2016-02-15 | Mechanical | Med Duty | ERECT | Complete | 2016-12-14 | 2016-02-18
5117 | DAAA | Area 14 Domgas north end Ground Level | Scaffold deck to be erected to access Bolt ups & Field welds | 1892 | Daniel Edwards | 2016-01-07 | Mechanical | Med Duty | ERECT | Complete | 2016-01-05 | 2016-01-07
5117 | DAAA | DAAA – Nth end – Ground Level old tag 1125 | Scaffold modification is required for rotating T piece & tesnisoning of studs | 2169 | Daniel Edwards | 2016-02-15 | Mechanical | Med Duty | MODIFY | Complete | 2016-02-16 | 2016-02-21
5118 | DAAA | DAAA – Nth end – Ground Level | Raise deck on scaffold to access next field weld | 2170 | Daniel Edwards | 2016-02-15 | Mechanical | Med Duty | ERECT | Complete | 2016-02-15 | 2016-01-16
5119 | DAAA | DAAA – East end – Ground Level | Erect scaffold to access and install 2" pipe spool | 2172 | Daniel Edwards | 2016-02-16 | Mechanical | Med Duty | ERECT | Complete | 2016-02-16 | 2016-02-17
5119 | DAAA | Domgas | Dismantle | 4376 | Trevor Pike | 2016-05-16 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-16 | 2016-05-18
5120 | DAAA | DAAA – East end – Ground Level | Scaffold needs to move to south approximate 200mm to allow encapsulation and hotworks to weld on light post, set up tubes on top of scaff for encapsulation | 2173 | Daniel Edwards | 2016-02-16 | Mechanical | Med Duty | ERECT | Complete | 2016-02-16 | 2016-02-17
5121 | DAAA | DAAA – East end – Ground Level | Boards to be added tp access support to be fitted | 2174 | Daniel Edwards | 2016-02-16 | Mechanical | Med Duty | ERECT | Complete | 2016-02-16 | 2016-02-17
5122 | ABAF | AGRU 2, ABAF | build scaffold access to install and weld out piping tie-ins on ABAG (RV platform) scaffold must be built big enough to capture purge cap install. scaffold must have high handrails for encapsulation. | 2034 | David Goodes | 2016-01-25 | Mechanical | Med Duty | ERECT | Complete | 2016-01-25 | 2016-02-26
5122 | DAAA | DAAA – East end – Ground Level | Need scaffold deck extended to access pipe spool. Need space for closure weld. Need 2 boards to be added | 2175 | Daniel Edwards | 2016-02-16 | Mechanical | Med Duty | ERECT | Complete | 2016-02-16 | 2016-02-17
5123 | DAAA | DAAA – East end – Ground Level | Strip scaff under east-west pipe rack at south end of train 3 previously used for hot tap works on heating medium system | 2177 | Daniel Edwards | 2016-02-16 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-02-17 | 2016-02-20
5124 | DAAA | DAAA – East end – Ground Level | Scaffolding is required at front of the Inlet stores | 2176 | Daniel Edwards | 2016-02-16 | Mechanical | Med Duty | ERECT | Complete | 2016-02-17 | 2016-02-26
5125 | DAAA | DAAA eastern side of the MRU, | Build scaffold at ground level at the eastern side of the MRU, to access pipe work for hydro test | 2179 | Daniel Edwards | 2016-02-16 | Mechanical | Med Duty | ERECT | Complete | 2016-02-17 | 2016-03-07
5125 | DAAA | DAAA – East end – Ground Level | Lower existing deck | 2401 | Charlie Bryce | 2016-03-04 | Mechanical | Med Duty | MODIFY | Complete | 2016-03-11 | 2016-03-10
5126 | JACA | 2ND LEVEL JACA | ERECT SCAFFOLD AROUND PIPE SUPPORT AT INLET NORTH RBAH MODULE | 2180 | Shane Shillabeer | 2016-02-16 | Mechanical | Med Duty | ERECT | Complete | 2016-02-17 | 2016-02-29
5127 | RBAH | RBAH - Inlet | ERECT SCAFFOLD AROUND PIPE SUPPORT AT INLET NORTH RBAH MODULE | 2181 | Shane Shillabeer | 2016-02-16 | Mechanical | Med Duty | ERECT | Complete | 2016-02-17 | 2016-02-26
5128 | POF | POF | Cable pits at POF require scaffold barrier and ladder beams and life Retrieval capability. Two locations as discussed with Wilfred. | 1897-1 | Shane Shillabeer | 2016-02-16 | Mechanical | Med Duty | ERECT | Complete | 2016-02-17 | 2016-02-26
5128 | POF | POF | Cable pits at POF require scaffold barrier and ladder beams and life Retrieval capability. Two locations as discussed with Wilfred. | 1897-2 | Shane Shillabeer | 2016-05-12 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-12 | 2016-05-12
5129 | DAAA | Area 14 Domgas East end Ground Level Tag 1163 | Need scaffold erected to remove elctrical clash & install pipe support | 1898 | Daniel Edwards | 2016-01-08 | Mechanical | Med Duty | ERECT | Complete | 2016-01-08 | 2016-01-08
5141 | DAAA | Area 14 - DAAA | Build new tower in front of Electrical junction boxes on level 1 North of module to access cable ladder (approximately 3 platforms) | 1141 | Jason Hopkins | 2015-10-10 | Electrical | Med Duty | ERECT | Complete | 2015-11-13 | 2015-10-28
5141 | DAAA | Area 14 - DAAA | mod – 24372.01-support 003 | 1906 | Cian Sinclair | 2016-01-09 | Mechanical | Med Duty | MODIFY | Complete | 2016-01-07 | 2016-01-09
5141 | DAAA | Area 14 - DAAA | old tag 887 DAAA - Dismantle scaffold used for electrical calbe installation | 1903 | Mathew Poole | 2016-01-09 | Electrical | Med Duty | DISMANTLE | Complete | 2016-01-07 | 2016-01-11
5156 | ABAA | AGRU 2, ABAA | build scaffold (same as agru1) for sample station steel work install this will include barrier on first floor for gridmesh removal. | 1936 | David Goodes | 2016-01-13 | Mechanical | Med Duty | ERECT | Complete | 2016-01-13 | 2016-01-14
5158 | ABAC | AGRU 2, ABAC | build scaffold to access CW20 and CW16, where our pipework ties into the ABAC vessel. Please contact David Goodes or Mick Knott for further details. | 1938 | David Goodes | 2016-01-13 | Mechanical | Med Duty | ERECT | Complete | 2016-01-13 | 2016-01-15
5174 | JACA | Area 18 JACA | Erect scaffold to access the top of Vaccum Scrubber(mech works) | 1980 | Tim Whiffin | 2016-01-20 | Mechanical | Med Duty | ERECT | Complete | 2016-01-20 | 2016-01-21
5217 | TACA | Train 1 TACA Level3 | Gridmesh removal - baricade | 2183 | Craig Coombe | 2016-02-17 | Scaffolding | Med Duty | ERECT | Complete | 2016-02-17 | 2016-02-17
5218 | TACA | Train 1 TACA Level3 | Gridmesh removal - baricade | 2184 | Craig Coombe | 2016-02-17 | Scaffolding | Med Duty | ERECT | Complete | 2016-02-17 | 2016-02-17
5219 | Area 8 | Sap 1 Area 8 | Set up new handrail around 2 x sap1 water ponds / after new hand rail is set up. Old one is to be removed to allow permanent on to be installed | 2186 | Mark Farley | 2016-02-17 | Mechanical | Med Duty | ERECT | Complete | 2016-02-18 | 2016-02-28
5220 | ABAA | AGRU 2, - ABAA | extend scaffold to remove pink steel and weld in channel guides build extends from 300NB tie-in scaffold | 2187 | David Goodes | 2016-02-17 | Mechanical | Med Duty | ERECT | Complete | 2016-02-18 | 2016-03-22
5221 | AAAA | 1057AAAA | Modify scaffold to allow completion of electrical scope. | 2188 | Andrew Ferres | 2016-02-17 | Electrical | Med Duty | ERECT | Complete | 2016-02-18 | 2016-02-28
5222 | GAA1 | GAA1 | Erect scaffold to access and install 2" pipe allow insulation cladding | 2189 | Andrew Ferres | 2016-02-17 | Electrical | Med Duty | ERECT | Complete | 2016-02-18 | 2016-03-01
5222 | GAA4 | GAA4 | GAA4 HM-2034 Line# OE-09038.01 SUB SYSTEM RSI 759 Ledger needs to be moved to allow for Insulation to be completed. | 3678 | TROY BRAND | 2016-04-28 | Mechanical | Med Duty | MODIFY | Complete | 2016-05-05 | 2016-05-10
5223 | AAAF | AGRU 1, - AAAF | build scaffold access to remove pink steel from the western side of MRU | 2190 | David Goodes | 2016-02-17 | Mechanical | Med Duty | ERECT | Complete | 2016-02-18 | 2016-03-22
5224 | TBJD | TBJD - Ground Level Nth | Build scaffold - @ the end of the instrument air head train 2 - required to preform blowing activites install 6' butterfly valve at the end of the header for blowing activities | 2191 | Sukahyur Fahmy | 2016-02-17 | Chevron | Med Duty | ERECT | Complete | 2016-02-17 | 2016-02-18
5225 | LPE | JETTY - SAY3 and LPE | Build Scaffold for access to valve stems to remove and install collars on valve shafts | 2192 | Adam Keown | 2016-02-17 | Mechanical | Med Duty | ERECT | Complete | 2016-02-18 | 2016-03-11
5226 | DAAA | sth east crn DAAA | Pipe support - Dismantle | 2194 | Daniel Edwards | 2016-02-17 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-02-17 | 2016-02-17
5226 | DAAA | 1130 DAAA ground lvl | Need to lower the deck on the scaffold to accommodate for PNHT | 2193 | Daniel Edwards | 2016-02-17 | Mechanical | Med Duty | ERECT | Complete | 2016-02-17 | 2016-02-18
5227 | GAGA | Inlet top floor GAGA | Scaffold required to access the underside of the GAGA top floor | 2195 | Thomas Murphy | 2016-02-18 | Mechanical | Med Duty | ERECT | Complete | 2016-02-18 | 2016-03-01
5228 | MOP | MOP – M1 | Erect mobile podium platform for guest at first cargo ceremony | 2196 | George Fomin | 2016-02-18 | Electrical | Med Duty | ERECT | Complete | 2016-02-20 | 2016-02-22
5228 | MOF | Mof | Dismantle 1st gas ceremony mobile podium | 2509 | Martin Riegert | 2016-03-13 | scaffolding | Med Duty | DISMANTLE | Complete | 2016-03-15 | 2016-03-14
5229 | BD`S | BDW & MDW | Dismantle hand rails and any capstan interfering with hook pulls | 2197 | George Fomin | 2016-02-18 | Electrical | Med Duty | DISMANTLE | Complete | 2016-02-18 | 2016-02-19
5230 | MD1 | MD1 - MD5 | Erect hard barricadeing gate to provide sfe access for pre-comms to reach western capstans | 2198 | George Fomin | 2016-02-18 | Electrical | Med Duty | ERECT | Complete | 2016-02-20 | 2016-02-22
5230 | M1 | Abutment to M1 | Change all access to tech trusses along jetty corridor so all outstanding handrails can be installed. | 2199-1 | Adam Keown | 2016-02-18 | Mechanical | Med Duty | ERECT | Complete | 2016-02-20 | 2016-03-16
5231 | M1 | Abutment to M1 | Change all access to tech trusses along jetty corridor so all outstanding handrails can be installed. | 2199-2 | Adam Keown | 2016-02-18 | Mechanical | Med Duty | ERECT | Complete | 2016-02-20 | 2016-03-16
5232 | DAAA | 1066 DAAA | Modify Scaffold to allow for Installation of Pipe Spools | 2201 | Daniel Edwards | 2016-02-18 | Mechanical | Med Duty | ERECT | Complete | 2016-02-18 | 2016-02-19
5232 | T12 | T12 T13 T14 | Remove exsisting hard barriers on see access ladder to a drop bar or gate so we can get to the bottom of the ladder to install safety mesh | 2200 | Adam Keown | 2016-02-18 | Mechanical | Med Duty | ERECT | Complete | 2016-02-20 | 2016-03-11
5233 | RBAH | 09B00-07 RBAH Seq 1 | 09B00-07 RBAH Seq 1 Scaffold is required to access flange to allow for detensioning of the flange for the removal of the valve. Scaffold is not to obstruct the removal of the valve. | 2203 | Thomas Murphy | 2016-02-18 | Mechanical | Med Duty | ERECT | Complete | 2016-02-20 | 2016-02-22
5234 | ABAA | CO2 Agru 2 Stores | Shelter for CO2 stores | 2202 | Jim McWhitner | 2016-02-18 | HSE | Med Duty | ERECT | Complete | 2016-02-20 | 2016-02-20
5234 | ABAA | CO2 Agru 2 Stores | Shelter frames for CO2 stores | 2244 | Jim McWhitner | 2016-02-21 | HSE | Med Duty | MODIFY | Complete | 2016-02-20 | 2016-03-22
5235 | T6 | T6 | Erect access to layer hung scaffold an extend Hop over platform 1 bay north | 2204 | Jeffery Spry | 2016-02-18 | Electrical | Med Duty | ERECT | Complete | 2016-02-20 | 2016-02-22
5235 | T6 | T6 | Dismantle access to layer hung scaffold an extend Hop over platform 1 bay north | 3677 | Adam Keown | 2016-04-28 | Mechanical | Med Duty | DISMANTLE | Not Started | 2016-05-04
5236 | T5 | T5 | Erect access to layer hung scaffold an extend Hop over platform 1 bay north | 2205 | Jeffery Spry | 2016-02-19 | Electrical | Med Duty | ERECT | Complete | 2016-02-19 | 2016-02-20
5236 | Jetty | T5 | Dismantle 5236 | 4528 | Chris Hampson | 2016-05-24 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-24 | 2016-05-24
5237 | DAAA | 229 DAAA | Change over of tag 229 to DNC & modification of ladder & one tube. | 2206 | Paul Velonias | 2016-02-19 | Mechanical | Med Duty | ERECT | Complete | 2016-02-20 | 2016-03-04
5238 | GAAC | Level 1 / GAAF & GAAC | Take Over Scaffold H1711 | 2207-1 | Wayne Hall | 2016-01-19 | Mechanical | Med Duty | TAKEOVER | Complete | 2016-01-20 | 2016-01-19
5238 | GAAC | Level 1 / GAAF & GAAC | Dismantle Scaffold H1711 | 2207-2 | Wayne Hall | 2016-02-19 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-02-20 | 2016-02-20
5239 | Area 19 | Laser Label Room - Oliver | Build a staircase to with a platform to remove the supplied staircase of the building. The current staircase has no platform posing a potential hazard of a fall from heights | 2208 | Nathan Gleean | 2016-02-19 | Common User | Med Duty | ERECT | Complete | 2016-02-19 | 2016-02-20
5240 | JACA | ACA-JAC1 HM-162 | JACA-JAC1 HM-162 Need to gain access to painting/insulation works keep all stuctural tubes (standards) 500mm from pipe and 250mm boards/puddies/trannies to allow clearance. Subsystem 09J00-01 Line 0P09144-02 work pack 2219 | 2209 | Felise Emelio | 2016-02-19 | Hertel | Med Duty | ERECT | Complete | 2016-03-10 | 2016-03-13
5240 | JAC1 | JAC1 | Dismantle 5240 - to rebuild scaffold for chartek works | 3214 | Felise Emelio | 2016-04-13 | Hertel | Med Duty | DISMANTLE | Complete | 2016-03-14 | 2016-04-18
5241 | JACA | JACA HM-163 | JACA HM-163 Need to gain access to painting/insulation works keep all structural tubes (standards) 500mm from pipe and 250mm boards/puddies/trannies to allow clearance. Subsystem 45A09-01 Line ow09128-01 work pack 2220-W | 2210 | Felise Emelio | 2016-02-19 | Hertel | Med Duty | ERECT | Complete | 2016-02-26 | 2016-03-13
5241 | JAC1 | JAC1 | Dismantle 5241 - to rebuild scaffold for chartek works | 3213 | Felise Emelio | 2016-04-13 | Hertel | Med Duty | DISMANTLE | Complete | 2016-03-14 | 2016-04-18
5242 | GAH1 | GAH1 HM-164 | GAH1 HM-164 Need to gain access to painting/insulation works keep all structural tubes (standards) 500mm from pipe and 250mm boards/puddies/trannies to allow clearance. Subsystem 09J00-16 Line 0G09069-02 | 2211 | Felise Emelio | 2016-02-19 | Hertel | Med Duty | ERECT | Complete | 2016-02-26 | 2016-03-13
5242 | ACAA | south level 3 - ACAA | GAH1 HM-1826 on inside of bung wall north side of tank ground floor need to reinstate boards to gain access to field welds for painting works. | 2629 | Felise Emelio | 2016-03-22 | Hertel | Med Duty | MODIFY | Complete | 2015-03-29 | 2016-03-30
5243 | GAA3 | GAA3 HM-165 | GAA3 HM-165 Need to gain access to painting/insulation works keep all structural tubes (standards) 500mm from pipe and 250mm boards/puddies/trannies to allow clearance. Subsystem 09A00-07 Line 0E09045-02 work pack 0957-P | 2212 | Felise Emelio | 2016-02-19 | Hertel | Med Duty | ERECT | Complete | 2016-02-26 | 2016-03-16
5244 | JAC1 | JAC1 | JAC1 HM-166 Need to gain access to painting/insulation works keep all structural tubes (standards) 500mm from pipe and 250mm boards/puddies/trannies to allow clearance. Subsystem 45A10-01 Line OW45E38-01 work pack 2218 | 2213 | Felise Emelio | 2016-02-19 | Hertel | Med Duty | ERECT | Complete | 2016-03-22 | 2016-03-22
5244 | JAC1 | JAC1 | Dismantle scaffold between JAC1 vessals ground level | 3212 | Felise Emelio | 2016-04-13 | Hertel | Med Duty | DISMANTLE | Complete | 2016-03-14 | 2016-04-14
5245 | Inlet | Inlet | Dismantle 5245 | 2215-1 | Mark Farley | 2016-02-20 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-02-22 | 2016-02-28
5245 | Inlet | Inlet | Scaffold | 2215-2 | Mark Farley | 2016-02-20 | Mechanical | Med Duty | MODIFY | Complete | 2016-02-22 | 2016-02-28
5245 | Inlet | Inlet | Take over ownership H1241 | 2215-3 | Mark Farley | 2016-02-20 | Mechanical | Med Duty | TAKEOVER | Complete | 2016-02-22 | 2016-02-28
5246 | GAH1 | Inlet GAH1 | Scaffold modification to allow for insullation of welding of pipe spooling | 2216 | Thomas Murphy | 2016-02-20 | Mechanical | Med Duty | ERECT | Complete | 2016-02-22 | 2016-02-26
5246 | RBAL-RBAK | RBAL | Modify tag 5246 DN150 | 2655 | Chris Black | 2016-05-22 | Mechanical | Med Duty | MODIFY | Complete | 2016-03-27 | 2016-05-23
5247 | GAHL | GAHL - Inlet Area | Remove current scaffold, handrail & barricade, as per attached PSSR punchlist. Reinstate small handrail section on Citric Acid loading bay to allow SMP works, to continue. | 2217 | Wayne McCarthy | 2016-02-21 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-02-22 | 2016-03-02
5247 | TBBA | TBBA TRAIN 2 RE-BOILERS | As per attached model shots and scaffold tag numbers. | 4218 | Brett Taane | 2016-05-11 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-14 | 2016-05-22
5248 | UACA | UACA NW corner | UACA HM-DN 167 NW corner. Tag 441. Access for blasting and Chartek of structural beams x2 locations. | 2218 | Troy Brand | 2016-02-21 | Hertel | Med Duty | ERECT | Cancelled | 2016-02-22
5249 | RBAQ | RBAQ inlet | Modify existing scaffold (H1761) to allow access to pipe clamps or build another deck from existing scaffold (H1761) to give access | 2219 | Thomas Murphy | 2016-02-21 | Mechanical | Med Duty | ERECT | Complete | 2016-02-23 | 2016-03-04
5250 | AREA 8 | AREA 8 / SAP WATER ON WALKWAY BETWEEN PONDS | Reinstate scaffolding mesh, corner bracing and lock ties to existing scaffold.Beam straps required on every standard on north side for harness hookup. | 2220 | John Pouroula | 2016-02-21 | Electrical | Med Duty | ERECT | Complete | 2016-02-21 | 2016-02-21
5251 | ABAA | ABAA AGRU2 | build scaffold to access 750NB field welds. As discussed the deck should continue around from the nothern trunion deck. Build to suit top 750NB weld first then modify to weld the bottom one. Deck height minimum 500mm from underside of spool | 2224 | David Goodes | 2016-02-21 | Mechanical | Med Duty | ERECT | Complete | 2016-02-24 | 2016-03-01
5251 | ABAH | ABAH | Modify exsisting scaffold planks to allow for instrumental tube penatration | 2460 | Andrew Ferres | 2016-03-10 | Mechanical | Med Duty | MODIFY | Complete | 2016-03-10 | 2016-03-10
5251 | ABAH | ABAH | ABAH HM-1831 east ground floor. Need access to complete painting works keep deck height 900mm below pipe and 225mm clearance from around pipe works. | 2652 | Felise Emelio | 2016-03-22 | Hertel | Med Duty | MODIFY | complete | 2016-03-29 | 2016-03-29
5252 | ABAA | ABAA AGRU2 | build access scaffold for southern utility station, allow for closure welds and support welding. Be aware of 750NB spool placement and that it is in its correct position before construction. | 2225 | David Goodes | 2016-02-21 | Mechanical | Med Duty | ERECT | Complete | 2016-02-24 | 2016-03-01
5253 | ABAA | AGRU 2, ABAA | build scaffold for access and welding on 750NB pipe - CW35 and CW28 scaffold is currently erected for install and needs enlarging for welding. | 2226 | David Goodes | 2016-02-21 | Mechanical | Med Duty | ERECT | Complete | 2016-02-24 | 2016-03-01
5254 | DAAA | nth end of dom gas | need hop up rerected to access T piece blind | 2227 | David Goodes | 2016-02-21 | Mechanical | Med Duty | ERECT | Complete | 2016-02-21 | 2016-02-25
5255 | DAAA | nth end of dom gas | need another level to be able to commence final bolt up & bleed during hydro | 2228 | Daniel Edwards | 2016-02-21 | Mechanical | Med Duty | ERECT | Complete | 2016-02-23 | 2016-02-24
5255 | DOMGAS | DOMGAS North End | Modification works to scaffold to enable the removal of 2 blinds and rotation. Installation of Tee Piece spool. | 4199 | Mark Farley | 2016-05-07 | Mechanical | Med Duty | MODIFY | Complete | 2016-05-14 | 2016-05-14
5256 | DAAA | sth end of dom gas / level 2 | 229DAAA - Extend deck to allow access to install guides and lines stops | 2229 | Daniel Edwards | 2016-02-21 | Mechanical | Med Duty | ERECT | Complete | 2016-02-26 | 2016-02-23
5256 | DAAA | sth end of dom gas / level 2 | Modify scaff to weld line stops on the North side of pipe shoe. Please note: Scaffold has been extended previously to do task however it needs more. | 2404 | Daniel Edwards | 2016-03-05 | Mechanical | Med Duty | MODIFY | Complete | 2016-03-05 | 2016-03-10
5256 | DAAA | sth end of dom gas / level 2 | Dimantle 5256 | 4370 | Craig Coombe | 2016-05-15 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-17 | 2016-05-17
5258 | TBAA | TBAA | Hop up is required for Catalyst loading on the 3 sisters Vessel: 2C-1201A Flange: UC1 Hop up is required to reach the Dump nozzle on the front of the vessel. | 2233 | Andrew Ledingham | 2016-02-21 | Mechanical | Med Duty | ERECT | Complete | 2016-03-01 | 2016-03-08
5258 | TBAA | TBAA Train 2 | Dismantle 5258 | 3255 | Michael Outram | 2016-04-15 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-04-17 | 2016-05-13
5259 | TBAA | TBAA | Hop up is required for Catalyst loading on the 3 sistersVessel: 2C-1201A Flange: N1 Scaff is required for the top elbow/pig pen/hopperhop up. This all ties in asone Scaffold. | 2234 | Andrew Ledingham | 2016-02-21 | Mechanical | Med Duty | ERECT | Complete | 2016-03-01 | 2016-03-15
5259 | TRAIN 2 TBAA | TRAIN 2 TBAA | Dismantle rated anchor humpy, top south. | 3047 | George Fomin | 2016-04-05 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-05 | 2016-04-03
5260 | TBAA | TBAA | Hop up is required for Catalyst loading on the 3 sistersVessel: 2C-1201A Flange: N2 | 2235 | Andrew Ledingham | 2016-02-21 | Mechanical | Med Duty | ERECT | Complete | 2016-03-01 | 2016-03-06
5261 | TBAA | TBAA | Hop up is required for Catalyst loading on the 3 sistersVessel: 2C-1201B Flange: UC1 | 2236 | Andrew Ledingham | 2016-02-21 | Mechanical | Med Duty | ERECT | Complete | 2016-03-01 | 2016-03-08
5261 | TBAA | TBAA Train 2 | Dismantle 5261 | 3248 | Michael Outram | 2016-04-15 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-04-17 | 2016-05-13
5261 | TACA | TACA - Train 1 top level | Dismantle Scaffold | 4299 | Barry Baker | 2016-05-14 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-20 | 2016-05-16
5262 | TBAA | TBAA | Hop up is required for Catalyst loading on the 3 sisters Vessel: 2C-1201BFlange: N1 - Scaff is required for the top elbow/pig pen/hopper hop up. This all ties in as one Scaffold. | 2237 | Andrew Ledingham | 2016-02-21 | Mechanical | Med Duty | ERECT | Complete | 2016-03-01 | 2016-03-16
5262 | TRAIN 2 TBAA | TRAIN 2 TBAA | Dismantle anchor point for catalyst, top south. Scaff TAG# 5262 | 3048 | George Fomin | 2016-04-05 | Chevron | Med Duty | MODIFY | Complete | 2016-04-05 | 2016-04-03
5263 | TBAA | TBAA | Hop up is required for Catalyst loading on the 3 sisters Vessel: 2C-1201B Flange: N2 | 2238 | Andrew Ledingham | 2016-02-21 | Mechanical | Med Duty | ERECT | Complete | 2016-03-01 | 2016-03-09
5264 | TBAA | TBAA | Hop up is required for Catalyst loading on the 3 sisters Vessel: 2C-1201C Flange: N1 Scaff is required for the top elbow/pig pen/hopper hop up. This all ties in as one Scaffold. | 2239 | Andrew Ledingham | 2016-02-21 | Mechanical | Med Duty | ERECT | Complete | 2016-02-28 | 2016-03-05
5265 | TBAA | TBAA | Hop up is required for Catalyst loading on the 3 sisters Vessel: 2C-1201C Flange: N2 | 2240 | Andrew Ledingham | 2016-02-21 | Mechanical | Med Duty | ERECT | Complete | 2016-03-01 | 2016-03-08
5265 | TBAA | TBAA Train 2 | Dismantle 5265 | 3247 | Michael Outram | 2016-04-15 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-04-17 | 2016-05-13
5266 | TBAA | TBAA | Hop up is required for Catalyst loading on the 3 sisters Vessel: 2C-1301 Flange: UC1 Hop up is required to reach the Dump nozzle on the front of the vessel. | 2241 | Andrew Ledingham | 2016-02-21 | Mechanical | Med Duty | ERECT | Complete | 2016-03-01 | 2016-03-08
5266 | TBAA | TBAA | Dismantle | 2241 | Andrew Ledingham | 2016-02-21 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-01 | 2016-05-16
5267 | TBAA | TBAA | Hop up is required for Catalyst loading on the 3 sistersVessel: 2C-1301Flange: N1 Scaff is required for the top elbow/pig pen/hopper hop up. This all ties in as one Scaffold. | 2242 | Andrew Ledingham | 2016-02-21 | Mechanical | Med Duty | ERECT | Complete | 2016-03-01 | 2016-03-09
5267 | TBAA | TBAA | Dismantle 5267 | 2242 | Andrew Ledingham | 2016-02-21 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-01 | 2016-05-16
5268 | TBAA | TBAA | Hop up is required for Catalyst loading on the 3 sistersVessel: 2C-1301Flange: N2 | 2243 | Andrew Ledingham | 2016-02-21 | Mechanical | Med Duty | ERECT | Complete | 2016-03-01 | 2016-03-01
5269 | UACA | Sth/West crn UACA | Scaffold to be built up to access field welds guides and support with full encaputlation | 933 | Daniel Edwards | 2015-09-09 | Mechanical | Med Duty | ERECT | Complete | 2015-09-16 | 2015-09-16
5269 | UACA | sth -west crn | Dismantle 1166UACA | 2222 | Daniel Edwards | 2016-02-21 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-02-23 | 2016-03-02
5269 | UACB | 2nd Level | Dismantle 724UACB | 2222 | Daniel Edwards | 2016-02-21 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-02-23 | 2016-03-02
5270 | GAA1 | GAA1 INLET | install scaffold drop protection over small bore piping and transmitters inside shelter | 2221 | Thomas Murphy | 2016-02-21 | Mechanical | Med Duty | ERECT | Complete | 2016-02-23 | 2016-03-04
5271 | GAA1 | GAA1 INLET | Install scaffold to access cable tray pn the underside of the gorgon Pig Reciever shelter roof | 2245 | Thomas Murphy | 2016-02-21 | Mechanical | Med Duty | ERECT | Complete | 2016-02-23 | 2016-03-08
5272 | GAAF | GAAF - Inlet Area HIPPS pipe spools | Remove current scaffold, handrail & barricade, around pipe spools. Handrails are obstructing removal of DN500 return loop | 2246 | Wayne McCarthy | 2016-02-21 | Mechanical | Med Duty | ERECT | Complete | 2016-02-21 | 2016-03-07
5278 | ABAF | AGRU 2, ABAF | MOD scaffold access to install and weld out piping tie-ins on ABAG (RV platform) Scaffold must be built big enough to capture purge cap install. scaffold must have high handrails for encapsulation. | 2035 | David Goodes | 2016-01-25 | Mechanical | Med Duty | MODIFY | Complete | 2016-02-28 | 2016-02-12
5279 | TADA | TADA | hard barricades required for gridmesh removal and handrail removal for pipe classes due to LNG being introduced into train 1 | 2248 | John Young | 2016-02-21 | Mechanical | Med Duty | ERECT | Complete | 2016-02-21 | 2016-02-25
5280 | TADA | TADA | hard barricades required for gridmesh removal and handrail removal for pipe classes due to LNG being introduced into train 1 | 2249 | John Young | 2016-02-21 | Mechanical | Med Duty | ERECT | Complete | 2016-02-21 | 2016-02-27
5281 | TADA | TADA | hard barricades required for gridmesh removal and handrail removal for pipe classes due to LNG being introduced into train 1 | 2250 | John Young | 2016-02-21 | Mechanical | Med Duty | ERECT | Complete | 2016-02-21 | 2016-02-21
5282 | TADA | TADA | Ground Floor hard barricades required for gridmesh removal and handrail removal for pipe classes due to LNG being introduced into train 1 | 2251 | John Young | 2016-02-21 | Mechanical | Med Duty | ERECT | Complete | 2016-02-21 | 2016-02-21
5283 | TADA | TADA | TOP Level - hard barricades required for gridmesh removal and handrail removal for pipe classes due to LNG being introduced into train 1 | 2252 | John Young | 2016-02-21 | Mechanical | Med Duty | ERECT | Complete | 2016-02-21 | 2016-02-21
5284 | TACA | TACA | scaffold to be erected to access cable tray clash ground level | 2253 | John Young | 2016-02-21 | Mechanical | Med Duty | ERECT | Complete | 2016-02-21 | 2016-02-21
5285 | AAAH | AAAH | AAAH HM-1587 N/E Tag 1180 Extend deck to allow for insulation | 2254 | John Young | 2016-02-21 | Mechanical | Med Duty | ERECT | Complete | 2016-02-21 | 2016-02-21
5286 | JH23 | JH23 | dismantle (partial) all scaffolding above line of sight facing south east from M5 (towards LPE) for 1st cargo ceremony | 2255 | Matt Alderidge | 2016-02-21 | Mechanical | Med Duty | ERECT | Complete | 2016-02-22 | 2016-03-29
5287 | LPE | LPE | dismantle (partial) all scaffolding above line of sight facing south from JH23 (towards LPE) for 1st cargo ceremony | 2256 | Matt Alderidge | 2016-02-21 | Mechanical | Med Duty | ERECT | Complete | 2016-02-23 | 2016-02-24
5288 |  | Tug pen | dismantle all remaining T+C+gates remaining on tugpen pontoons + walkways, remove all excess materials from area | 2257 | Matt Alderidge | 2016-02-21 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-02-24 | 2016-02-24
5289 | GAHJ | GAHJ | GAHJ HM-1572 line # GAH100-0E-09690.022 x modifications required to give 200mm clearance for insulation works. Scaffold tag #G383 | 2258 | Troy Brand | 2016-02-21 | Hertel | Med Duty | ERECT | Complete | 2016-03-10 | 2016-03-10
5290 | AAA3 | AAA3 | AAA3 HM-1579. Line # TP-4002-0004 Erect scaffold to access weld for painting. Deck to be 1.2m down from weld. 200mm clearance required. | 2259 | Troy Brand | 2016-02-21 | Hertel | Med Duty | ERECT | Complete | 2016-03-10 | 2016-03-21
5291 | AAA3 | AAA3 | AAA3 HM-1578. Tag # 704 Line # TP-4002-0001 scaffold needs to be reinstated for painting works. 200mm clearance required. | 2260 | Troy Brand | 2016-02-21 | Hertel | Med Duty | ERECT | Complete | 2016-03-10 | 2016-03-22
5292 | AAA3 | AAA3 | AAA3 HM-1580. Tag # 845 Line # TP-4002-0003 lower scaffold lift needs extending and higher lift modified to give clearance for painting. 200mm clearance required. | 2261 | Troy Brand | 2016-02-21 | Hertel | Med Duty | ERECT | Complete | 2016-03-11 | 2016-03-25
5293 | GAA1 | GAA1 | GAA1 HM-1589 SM0001 Dropped Object Shelter. Scaffold required for the application of Chartek on Structural Beams. Two scaffolds ( one on the inside one on the outside) First lift at 2m the second lift for roof beams will be at 4m. | 2262 | Troy Brand | 2016-02-21 | Hertel | Med Duty | ERECT | Complete | 2016-03-23 | 2016-05-21
5294 | TBBA | TRAIN 2 Re-Boilers TBBA -2E-1601 | Build Scaffold to access flanges, and welding on reboilers 2E-1601. 2E-1612, 2E- 1613, Area: TRAIN 2 Re-Boilers TBBA -2E-1601 | 2263 | Mick Zalmsina | 2016-02-15 | Mechanical | Med Duty | ERECT | Complete | 2016-02-16 | 2016-03-24
5295 | TBAA | TRAIN 2 Re-Boilers TBBA -2E-1602 | Build Scaffold to access flanges, and welding on reboilers 2E-1601. 2E-1612, 2E- 1613, Area: TRAIN 2 Re-Boilers TBBA-2E-1612 TOP | 2264 | Mick Zalmsina | 2016-02-15 | Mechanical | Med Duty | ERECT | Complete | 2016-02-16 | 2016-02-27
5295 | TBBA | TBBA | Dismantle | 4431 | Brett Taane | 2016-05-20 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-25 | 2016-05-21
5296 | TBAA | TRAIN 2 Re-Boilers TBBA -2E-1603 | Build Scaffold to access flanges, and welding on reboilers 2E-1601. 2E-1612, 2E- 1613, Area: TRAIN 2 Re-Boilers TBBA - 2E-1612 BOTTOM | 2265 | Mick Zalmsina | 2016-02-15 | Mechanical | Med Duty | ERECT | Complete | 2016-02-16 | 2016-02-27
5297 | TBBA | TRAIN 2 Re-Boilers TBBA -2E-1604 | Build Scaffold to access flanges, and welding on reboilers 2E-1601. 2E-1612, 2E- 1613, Area: TRAIN 2 Re-Boilers TBBA-2E - 1613 | 2266 | Mick Zalmsina | 2016-02-15 | Mechanical | Med Duty | ERECT | Complete | 2016-02-16 | 2016-03-25
5297 | TBBA | TRAIN 2 Re-Boilers TBBA -2E-1604 | Build Scaffold to access flanges, and welding on reboilers 2E-1601. 2E-1612, 2E- 1613, Area: TRAIN 2 Re-Boilers TBBA-2E - 1613 | 4364 | Mick Zalmsina | 2016-05-15 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-02-16 | 2016-05-15
5298 | CCAA | 1st Level of CCAA east side of module | CO2 Compressors on module CCAA require scaffolds to be erected for inspection and preservation tasks. Similar scaffs have been completed on the 2 modules on the 2 modules next door. (CAAA and CBAA) These Scaffolds can be used as a reference | 2270 | Denny Shewell | 2016-02-18 | Mechanical | Med Duty | ERECT | Complete | 2016-02-21 | 2016-04-13
5299 | TAHA | TAHA train 1 | Train 1 north level 1 erect scaffold fram, approx 2.5m h 2.4m x 1.2m. The frame has to be able to accommodate the lift of approx 150kgs. This is for removal of TC valve. This is a CSU job | 2269 | Joe Alaalatoa | 2016-02-23 | Scaffolding | Med Duty | ERECT | Complete | 2016-02-23 | 2016-02-26
5300 | T7 | Jetty T7 | build access to bottom side of roadway to access bearing pad for removal of timber and install of correct bearing | 2268 | Adam Keown | 2016-02-24 | Mechanical | Med Duty | ERECT | Complete | 2016-02-27 | 2016-02-28
5300 | Jetty | t7 | Dismantle access from walkay T7 | 4527 | Chris Hampson | 2016-05-24 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-24 | 2016-05-24
5300 | T7 | T7 jetty | Dismantle access from walkway | 4527 | Chris Hampson | 2016-05-24 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-24 | 2016-05-24
5301 | TAHA | TAHA train 1 | Train 1 north level 1 erect scaffold fram, approx 2.5m h 2.4m x 1.2m. The frame has to be able to accommodate the lift of approx 150kgs. This is for removal of TC valve. This is a CSU job | 2267 | Joe Alaalatoa | 2016-02-23 | Scaffolding | Med Duty | ERECT | Complete | 2016-02-23 | 2016-02-26
5302 | ABAA | AGRU 2, ABAA | build access scaffold for southern utility station, allow for closure welds and support welding. Be aware of 750NB spool placement and that it is in its correct position before construction. | 2271 | David Goodes | 2016-02-21 | Mechanical | Med Duty | ERECT | Complete | 2016-02-27 | 2016-03-03
5303 | UACA | UACA S/W | UACA M-1611 Tag? Fuel Gas S/W Reinstate access we have no tag as access has been removed | 2272 | Troy Brand | 2016-02-24 | Hertel | Med Duty | ERECT | Complete | 2016-02-29 | 2016-04-24
5304 | Area 19 | Oliver Yard | Erect shelving in 40' container | 2247 | Paul Cummins | 2016-02-21 | Mechanical | Med Duty | ERECT | Complete | 2016-02-21 | 2016-02-21
5305 | UACA | UACA S/W 1st Lvl | UACA HM-1610 Tag 5082 Fuel Gas 1st Lvl S/W Move Standard, Brace and open up a penetration around pipe. | 2273 | Troy Brand | 2016-02-24 | Hertel | Med Duty | MODIFY | Complete | 2016-02-29 | 2016-03-16
5305 | UACA | UACA | Dismantle Scaffold | 4311 | Trevor Pike | 2016-05-14 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-15 | 2016-05-19
5306 | UACA | UACA S/W | UACA HM-1612 Fuel Gas S/W Access to Black Pipe section for Insulation. | 2274 | Troy Brand | 2016-02-24 | Hertel | Med Duty | ERECT | Complete | 2016-02-29 | 2016-03-07
5307 | LPW | LPW Dolphins MD1,2,3,4,5,6E and BD1,2,3,4E | Install scaffold barrier around capstans as discussed with Andrew Georgiou. | 2275 | Grant Percy | 2016-02-24 | Electrical | Med Duty | ERECT | Complete | 2016-03-01 | 2016-03-05
5308 | LPW | LWP South Side at MDW1, NMDW2, MDW3 | Install scaffold barrier around capstans as discussed with Andrew Georgiou. | 2276 | Grant Percy | 2016-02-24 | Electrical | Med Duty | ERECT | Complete | 2016-03-03 | 2016-03-14
5309 | INLET | Inlet - GAAC | Part 1 - Hard Barricade required for grid mesh removal c/w access gate and hook up point for grid mesh removal. Part 2 - Existing scaffold No H1683 is too low for welding of 2x structural pipe supports. Existing deck is built on underside of beam flangs. We require extra deck to be built on top of beam flanges. This dck is directly underneath Part 1 hard barricade. Subsystem 10B00-02, Volume 6, Sequence 7 & 9 | 2277 | Mark Farley | 2016-02-24 | Mechanical | Med Duty | ERECT | Complete | 2016-02-26 | 2016-03-14
5310 | SASC | SASC | We require scaff mod to access valve as shown on attached | 2278 | John Young | 2016-02-25 | Mechanical | Med Duty | MODIFY | Cancelled | 2016-03-07
5311 | GAHL | GAHL - Inlet Area | Remove current scaffold, handrail & barricade, as per attached PSSR punchlist. Reinstate small handrail section on Critic Acid loading bay to allow SMP works, to continue. | 2279 | Wayne McCarthy | 2016-02-25 | Mechanical | Med Duty | MODIFY | Complete | 2016-02-25 | 2016-03-02
5312 | INLET | Inlet - GAAC | Hard barricade to allow for grid mesh removal c/w access gate and hook up point W.P. 3-053-P-04-Volume 6 Sequence 12, Sub system-10B00-02, ABS-GAH1 | 2280 | Mark Farley | 2016-02-25 | Mechanical | Med Duty | ERECT | Complete | 2016-02-27 | 2016-03-14
5313 | LPE | SAYM LPE | SAYM LPE HM-1613 accss to pipe work wrapped in black plastic for lagging installation. As shown to Marty | 2281 | Troy Brand | 2016-02-25 | Hertel | Med Duty | ERECT | Complete | 2016-03-01 | 2016-03-02
5314 | SAYL | SAYL | SAYL HM-1614 OP34025003SA003 access to pipe work for lagging installation. As shown to Marty | 2282 | Troy Brand | 2016-02-25 | Hertel | Med Duty | ERECT | Complete | 2016-03-01 | 2016-03-02
5315 | SCJC | SCJC | SCJC HM-1615 0P-34026.01 Re instatement needed to access Pipe work x6 for lagging. | 2283 | Troy Brand | 2016-02-25 | Hertel | Med Duty | MODIFY | Complete | 2016-03-01 | 2016-03-02
5317 | L13 | L13 | Dismantle scaffold at the bottom of L13 ladder for install of safety mesh also modify Tech Truss access so handrail can be installed | 2285 | Adam Keown | 2016-02-25 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-02-26 | 2016-02-26
5318 | GAHL | GAHL - North end | Please dismantle these scaffolds for access to chemical cleaning pump and valves so operations can commission. | 2286 | Michael Hemmings | 2016-02-25 | CKJV | Med Duty | DISMANTLE | Complete | 2016-02-27 | 2016-03-02
5319 | RBAC | RBAC | Existing scaffold down at RBAC rack inlet needs inspection and tag. All levels so access can be gained to deck under pipe spools. | 2287 | Todd Lyons | 2016-02-26 | Mechanical | Med Duty | MODIFY | Complete | 2016-02-28 | 2016-03-03
5320 | AGRU 2 | AGRU 2, ABAG | Build scaffold at south end of RV platform to allow for handrail and walkway modifications. Arrange walk down with supervisor prior to build as there are small details that need to be allowed for. | 2288 | David Goodes | 2016-02-26 | Mechanical | Med Duty | MODIFY | Complete | 2016-03-04 | 2016-03-03
5321 | AGRU 3 | AGRU3, ACAA | Build temp handrail to allo the removal of fixed handrail. Fixed handrail will currently clash with ACAH modul install approx 15m long | 2289 | David Goodes | 2016-02-26 | Mechanical | Med Duty | MODIFY | Complete | 2016-03-04 | 2016-03-02
5322 | AGRU 3 | AGRU 3, ACAG | Build access scaffold for RV ti-in pipework and purge caps. This scaffold is built from 300NB spool scaffold. Rfer to AGRU 2 as this scaffold will be the same. | 2290 | David Goodes | 2016-02-26 | Mechanical | Med Duty | MODIFY | Complete | 2016-03-04 | 2016-03-03
5323 | AGRU 3 | AGRU 3, ACAC | Build access and temp handrail to ACAC vessel platform for pipe removal pipe to be removed for hydro-testing. | 2291 | David Goodes | 2016-02-26 | Mechanical | Med Duty | MODIFY | Complete | 2016-03-04 | 2016-03-03
5324 | AGRU 3 | AGRU 3, ACAA | Scaffold build to accss 300NB spool welding, including guides and caps. See AGRU 2 for reference as it will be the same. | 2292 | David Goodes | 2016-02-26 | Mechanical | Med Duty | MODIFY | Complete | 2016-03-04 | 2016-03-04
5325 | RBDH | RBDH, PIPERACK | Reinstate 441 access to East West piperack for cable tray install. | 2293 | Mathew Poole | 2016-02-26 | Electrical | Med Duty | MODIFY | Complete | 2016-02-28 | 2016-03-01
5326 | INLET | Inlet - GAA1 | Take over, re-instate and tag scaff ready for use. Scaff location at Western Pig Receiver or Gorgon Pig Receiver. Western Pig Receiver structural steel platform. | 2295 | Mark Farley | 2016-02-25 | Mechanical | Med Duty | ERECT | Complete | 2016-03-04 | 2016-03-04
5327 | INLET | Inlet - RBAH | Hard barricading is required for 20 mtr exclusion zone around Depressurising Valve and spooll removal as per WMS W.P. 3-053-P-04-Volume 3 Sequence 1, Sub system-09800-07, ABS-RBAH | 2294 | Mark Farley | 2016-02-26 | Mechanical | Med Duty | ERECT | Complete | 2016-02-27 | 2016-03-01
5328 | LPE | LPE | Dismantle of LPE "S" bend cladding scaffold - as directed by Mike Brown and requested by Rob Breuker (CUX) | 2296 | Martin Riegert | 2016-02-26 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-02-26 | 2016-02-29
5329 | AAAC | AAAC AGRU1 | AAAC HM-1625 Line # 1P-11056 Modify scaffold to give clearance for installation of insulation to full line. 225mm clearance is required | 2297-1 | Troy Brand | 2016-02-27 | Hertel | Med Duty | MODIFY | Complete | 2016-03-07 | 2016-03-19
5329 | AAAC | AAAC AGRU1 | AAAC HM-1625 Line # 1P-11056 Modify scaffold to give clearance for installation of insulation to full line. 225mm clearance is required | 2297-2 | Troy Brand | 2016-02-27 | Hertel | Med Duty | MODIFY | Complete | 2016-03-07 | 2016-03-20
5329 | AAAC | AAAC AGRU1 | AAAC HM-1625 Line # 1P-11056 Modify scaffold to give clearance for installation of insulation to full line. 225mm clearance is required | 2297-3 | Troy Brand | 2016-02-27 | Hertel | Med Duty | MODIFY | Complete | 2016-03-07 | 2016-03-21
5330 | DAAA | DAAA South East Corner | DAAA HM-1623 Line# OP24374-02 Tag# 5119 Modify scaffold to access welds and burn marks for painting blasting. Standard too close needs to be moved. | 2298 | Troy Brand | 2016-02-27 | Hertel | Med Duty | MODIFY | Complete | 2016-03-07 | 2016-03-05
5331 | GAH3 | GAH3 1st Level | Hand over scaffold to Downer | 2299 | Dave Dundon | 2016-02-27 | Scaffolding/Rigging/Crane | Med Duty | TAKEOVER | Complete | 2016-03-02 | 2016-03-02
5332 | GACA | GACA, Eastside ground LVL | Hand over scaffold to Downer | 2300 | Dave Dundon | 2016-02-27 | Scaffolding/Rigging/Crane | Med Duty | TAKEOVER | Complete | 2016-03-04 | 2016-03-04
5333 | JADB | JADB-RBAC GROUND LVL | Hand over scaffold to Downer | 2301 | Dave Dundon | 2016-02-27 | Scaffolding/Rigging/Crane | Med Duty | TAKEOVER | Complete | 2016-03-01 | 2016-03-01
5334 | RBAC | RBAC/GACB GROUND LVL | Hand over scaffold to Downer | 2302 | Dave Dundon | 2016-02-27 | Scaffolding/Rigging/Crane | Med Duty | TAKEOVER | Complete | 2016-03-01 | 2016-03-01
5335 | AGRU 2 | AGRU 2 filter platform stair access | Built scaff frame with screw jacks to allow for gluts to be remove and civil contractors to install precast concrete under stair bace plates. | 2303 | Mike Knott | 2016-02-28 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-06 | 2016-03-04
5336 | FUELGAS | TOP LEVEL OF RV PLATFORM FUELGAS | Strip scaffold barricading on top of RV platform fulgas to enable access to install kick plate | 2304 | Daniel Edwards | 2016-02-28 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-02-28 | 2016-03-01
5337 | AGRU 3 | AGRU 3, ACAA | Build scaffold as discussed to allow easy access to south/east corner of AGRU 3 scaffold is only temporary while waiting for permanent stairway istallation | 2305 | David Goodes | 2016-02-28 | Mechanical | Med Duty | MODIFY | Complete | 2016-03-06 | 2016-03-02
5338 | DAAA | DAAA South East Corner | Hop up is required for Catalyst loading on the DOM Gas MRU Vessel Vessel: 0C-2401 Flange: N1 Scaff is required for the top elbow/pig pn hopper hop up. This all ties in as one Scaffold. | 2306 | Andrew Ledingham | 2016-02-28 | Sulzer | Med Duty | ERECT | Complete | 2016-03-02 | 2016-03-09
5339 | AGRU 2 | AGRU 2 | Navis Picture #4 (2 Pages) Scaffold to be installed above pipe to gain access to cable ladder | 2307 | Gunther Grossinger | 2016-02-28 | Electrical | Med Duty | ERECT | Complete | 2016-02-29 | 2016-03-05
5340 | AGRU 2 | AGRU 2 | Navis Picture #1 (2 Pages) Scaffold to be installed from first floor to RL40 to gain access to cable ladder | 2308 | Gunther Grossinger | 2016-02-28 | Electrical | Med Duty | ERECT | Complete | 2016-02-29 | 2016-03-30
5341 | AGRU 2 | AGRU 2 | Navis Picture #2 (1 Page) Scaffold to be installed to gain acccess to flame detector | 2309 | Gunther Grossinger | 2016-02-28 | Electrical | Med Duty | ERECT | Complete | 2016-03-07 | 2016-03-11
5342 | AGRU 2 | AGRU 2 | Navis Picture #5 (1 Page) Scaffold to be installed from ground floor to first floor to gain access to flame detector | 2310 | Gunther Grossinger | 2016-02-28 | Electrical | Med Duty | ERECT | Complete | 2016-03-07 | 2016-03-05
5343 | AGRU 2 | AGRU 2 | Navis Picture #3 (2 Pages) Scaffold to be extended to gain access to cable ladder | 2311 | Gunther Grossinger | 2016-02-28 | Electrical | Med Duty | ERECT | Complete | 2016-03-07 | 2016-03-15
5343 | ABAA | ABAA | Scaffold to provide access to instrument stands - see attached | 2654 | Paul Slocombe | 2016-03-23 | Mechanical | Med Duty | MODIFY | Complete | 2016-03-29 | 2016-04-12
5344 | AAAA | AGRU 1 | AAAA HM-1626 need access to lines on 3 pumps, for insulation scope. Keep 250mm clearance boards/tubes/ply from pipe.subs 11B-01-02 | 2312 | Felise Emelio | 2016-02-29 | Hertel | Med Duty | ERECT | Complete | 2016-03-03 | 2016-03-03
5345 | MRU | Top of MRU DOMGAS | Strip scaffold at the end of MRU DOMGAS to enable gridmsh to be installed for catalyst loading. | 2315 | Daniel Edwards | 2016-02-29 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-02-28 | 2016-03-06
5346 | DOMGAS | North end DOMGAS Ground level | Strip scaffold for T piece then rebuild for tensionning | 2316 | Daniel Edwards | 2016-02-29 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-01 | 2016-03-03
5347 | DOMGAS | East side DOMGAS Ground level | Strip scaffold walkway from around east side of DOMGAS | 2317 | Daniel Edwards | 2016-02-29 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-01 | 2016-03-02
5348 | DOMGAS | Ground level East side DOMGAS | Strip scaffold on ground level east corner of DOMGAS to allow for stair installation | 2318 | Daniel Edwards | 2016-02-29 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-02-29 | 2016-01-08
5349 | JH23 | JH23 | Modify existing scaffold to allow install of hand rails and kick plate. JH23 southern stair access as per drawing. | 2319 | Todd Lyons | 2016-02-29 | Mechanical | Med Duty | MODIFY | Complete | 2016-03-01 | 2016-02-29
5350 | Jetty | L5/L6 jetty passing bay | Build hope up to allow access to welding of stairs coming off road way. SMP crew to advise of build need. | 2320 | Todd Lyons | 2016-02-29 | Mechanical | Med Duty | ERECT | Complete | 2016-03-01 | 2016-02-29
5351 | LPE | LPE | Build deck to access and install valves onto hydraulic lines condensate loading arms. Vendor to show how scaffold is needed. | 2321 | Todd Lyons | 2016-02-29 | Mechanical | Med Duty | ERECT | Complete | 2016-03-01 | 2016-03-05
5352 | AGRU 2 | AGRU 2 Ground floor | Scaffold required to onstall cable ladder and cable for telephone | 2322 | Gunther Grossinger | 2016-02-29 | Electrical | Med Duty | ERECT | Complete | 2016-03-07 | 2016-03-11
5353 | AGRU 2 | AGRU 2 RL27 | Scaffold required to install flame detector stand, cable ladder and cable on RL27 | 2323 | Gunther Grossinger | 2016-02-29 | Electrical | Med Duty | ERECT | Complete | 2016-03-07 | 2016-03-11
5354 | AGRU 2 | AGRU 2 RL33 | Require scaffold to get stand for flame detector welded to structure, cable ladder and cable installation | 2324 | Gunther Grossinger | 2016-02-29 | Electrical | Med Duty | ERECT | Complete | 2016-03-07 | 2016-03-15
5355 | AGRU 2 | AGRU 2 RL27 | Scaffold required to install cable ladder and cable | 2325 | Gunther Grossinger | 2016-02-29 | Electrical | Med Duty | ERECT | Complete | 2016-03-07 | 2016-03-18
5356 | GUA | GUA | Build scaffold under roof for GUA flame arrester | 2326 | Richard Jensen | 2016-02-29 | Inspection | Med Duty | ERECT | Complete | 2016-03-06 | 2016-03-05
5357 | MOF | WHARF | Erect a shade shelter along the length of the new security TCP (situated at the entrance to roro area). Shelter will be approx 13m long x 2.4m wide. | 2328 | Mike Hemming | 2016-03-01 | KJV | Med Duty | ERECT | Complete | 2016-03-01 | 2016-03-03
5358 | UACA | UACA | UACA HM-153 tag 1146 need access for painting works. Deck height 1.8m from elbow keep all boards/ply min 250mm from pipe works. | 2327 | Felise Emelio | 2016-02-29 | Hertel | Med Duty | MODIFY | Complete | 2016-02-15 | 2016-03-14
5359 | RBAC | RBAC - Tag ID #G1462 | Scaffold Tag been removed by CKJV. Please inspect and re-instat tag for urgent access, CVX require access for valve isolations and nitrogen purging. **This is part of the DOMGAS system and is high priority** | 2329 | Wayne McCarthy | 2016-03-01 | Mechanical | Med Duty | MODIFY | Complete | 2016-03-01 | 2016-03-02
5360 | Jetty | JETTY MOP | MOP south end HM-1630 need access to pipe to compete insulation works. Reinstate all hand rails and access to scaffold. Note there was no scaff tag attached. | 2330 | Felise Emelio | 2016-03-01 | Hertel | Med Duty | MODIFY | Complete | 2016-03-05 | 2016-03-03
5361 | Jetty | JETTY L9-L10 | L9-L10 HM-1631 need to dismantle hop ups both east/west of stair to allow for painting works. | 2331 | Felise Emelio | 2016-03-01 | Hertel | Med Duty | MODIFY | Complete | 2016-03-05 | 2016-03-02
5362 | AAAB | AAAB | HM-1634 AAAB D1274 Need to access flange to fit box and move all tubes/boards back around pipe works on hole of line 250mm for metal works. | 2332 | Felise Emelio | 2016-03-01 | Hertel | Med Duty | MODIFY | Complete | 2016-03-10 | 2016-03-15
5363 | AAA3 | AAA3 | AAA3 HM-1578 #704 Line #TP-4002-0001 Scaffold need to be reinstated for painting works. 200mm clearance required. | 2333 | Troy Brand | 2016-03-01 | Hertel | Med Duty | MODIFY | Cancelled | 2016-02-26
5364 | AAA3 | AAA3 | AAA3 HM-1579. Line #TP-4002-0004 Erect scaffold to access weld for painting. Deck to be 1.2m down from weld. 200mm clearance required. | 2334 | Troy Brand | 2016-03-01 | Hertel | Med Duty | ERECT | Cancelled | 2016-02-26
5365 | AAA3 | AAA3 | AAA3 HM-1580. Tag #845 Line #TP-4002-0003 Lower scaffold lift needs extending and higher lift modified to give clearance for painting. 200mm clearance required. | 2335 | Troy Brand | 2016-03-01 | Hertel | Med Duty | ERECT | Cancelled | 2016-02-26
5365 | AAA3 | AAA3 | AAA3 HM-1580. Tag #845 Line #TP-4002-0003 Lower scaffold lift needs extending and higher lift modified to give clearance for painting. 200mm clearance required. | 2335 | Troy Brand | 2016-03-01 | Hertel | Med Duty | MODIFY | Cancelled | 2016-02-26
5366 | GAA1 | GAA1 | GAA1 HM-1635 Access needed to 5 locations shown in diagram. Keep all boards/tubes/ply 250mm from pipe works. Subsystem 09B00-07 W/P #10063 | 2336 | Felise Emelio | 2016-03-01 | Hertel | Med Duty | ERECT | Complete | 2016-03-09 | 2016-04-18
5367 | GAA1 | GAA1 | GAA1 HM-1637 Access needed to pipe mark in red shown in diagram. Keep all boards/tubes/ply 250mm from pipe works. Subsystem 09B00-07 W/P #10065WP | 2337 | Felise Emelio | 2016-03-01 | Hertel | Med Duty | ERECT | Complete | 2016-03-22 | 2016-04-24
5368 | AAAB | AAAB | HM-1633 AAAB D1275 Need to move all tubes/boards back around pipe works on hole of line 250mm for metal works | 2338 | Felise Emelio | 2016-03-01 | Painting/Electrical | Med Duty | MODIFY | Complete | 2016-03-07 | 2016-03-11
5369 | GAH1 | GAH1 | GAH1 HM-1638 Access needed to pipe shown in diagram. Keep al boards/tubes/ply 250mm from pipe works. Subsystem 09500-16 W/P #2226WP | 2339 | Felise Emelio | 2016-03-01 | Hertel | Med Duty | ERECT | Complete | 2016-03-22 | 2016-04-24
5370 | SAP | SAP | Build scaff for grid mesh removal on top of T6405 with over head hook up | 2343 | Richard Jensen | 2016-03-01 | Inspection | Med Duty | ERECT | Complete | 2016-03-04 | 2016-03-05
5371 | UACB | West side UACB Ground Level | Dismantle scaffold and remove hard barricading from all ladders. | 2344 | Daniel Edwards | 2016-03-02 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-02 | 2016-03-05
5372 | FUELGAS | Top Level of RV Platform FUELGAS | Strip scaffold barricading on top of RV Platform FUELGAS to enable access to install kick plate | 2345 | Daniel Edwards | 2016-03-02 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-02-28 | 2016-03-02
5373 | INLET | GAA1 | GAA1 HM-1639 Access needed to pipe mark in red shown in diagram. Keep all boards/tubes/ply 250mm from pipe works. Subsytm 09J00-05 W/P #2190P | 2340 | Felise Emelio | 2016-03-01 | Hertel | Med Duty | ERECT | Complete | 2016-03-22 | 2016-03-20
5373 | GAA1 | GAA1 - RBAQ | GAA1-RBAQ HM-1996 tag 5373 Scaffold can be dismantled from sub station to module painting works complete. HM-258 | 3402 | Felise Emelio | 2016-04-19 | Hertel | Med Duty | DISMANTLE | Complete | 2016-04-20 | 2016-05-18
5374 | AAA3 | AAA3 | AAA3 HM-1640 Access needed to pipe x3 mark in red as shown in diagram for painting. Keep all boards/tubes/ply 250mm from pipe works. Line #1G-48AR3.70 W/P #8280NP | 2341 | Felise Emelio | 2016-03-01 | Hertel | Med Duty | ERECT | Complete | 2016-03-14 | 2016-04-24
5375 | AAA3 | AAA3 | AAA3 HM-1641 Access needed to pipe x2 marked in red as shown in diagram for painting. Keep all boards/tubes/py 250mm from pipe works. Subs #11B01-09 W/P #8283 | 2342 | Felise Emelio | 2016-03-01 | Hertel | Med Duty | ERECT | Complete | 2016-03-12 | 2016-03-15
5376 | UACB | 1st Level UACB | Dismantle scaffold on UACB Module | 2349 | Daniel Edwards | 2016-03-01 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-02 | 2016-03-13
5377 | UACB | Top of MRU UACB | Dismantle scaffolds on top of MRU Vessel UACB | 2350 | Daniel Edwards | 2016-03-01 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-02 | 2016-03-13
5378 | UACB | 2nd Level UACB | Need scaffold dismantled to enable filter lids to be removed | 2351 | Daniel Edwards | 2016-03-01 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-02 | 2016-03-13
5379 | GTGS | GT3 | Build access to PRV's for Inergen system | 2352 | Lennie Haira | 2016-03-01 | Mechanical | Med Duty | ERECT | Complete | 2016-03-03 | 2016-03-06
5379 | GTGS | GT3 | Dismantle 5379 | 2545 | Lennie Haira | 2016-03-01 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-03 | 2016-03-14
5380 | Jetty | L5-L6 | L5-L6 HM-1652 hops ups and mods needed to allow for painting scopes as shown to Alistair Nicholas to what is required. | 2353 | Felise Emelio | 2016-03-02 | Hertel | Med Duty | MODIFY | Complete | 2016-02-16 | 2016-03-08
5381 | Jetty | L9-L10 | L9-L10 HM-1652 hops ups and mods needed to allow for painting scopes as shown to Alistair Nicholas to what is required. | 2354 | Felise Emelio | 2016-03-02 | Hertel | Med Duty | MODIFY | Complete | 2016-02-16 | 2016-03-02
5382 | INLET | GAA1 | GAA1 HM-1642 Access needed to pipe x2 marked in red as shown in diagram for painting. Keep all boards/tubes/ply 250mm from pipe works. Subs #09B00-07 W/P #10068 | 2346 | Felise Emelio | 2016-03-01 | Hertel | Med Duty | ERECT | Complete | 2016-03-22 | 2016-03-18
5383 | GAE1 | GAE1 | GAE1 HM-1643 Access needed to pipe x2 marked in red as shown in diagram for painting. Keep all boards/tubes/ply 250mm from pipe works. Subs #10D00-02 W/P #4071 | 2347 | Felise Emelio | 2016-03-01 | Hertel | Med Duty | ERECT | Complete | 2016-03-14 | 2016-04-24
5384 | AGRU 2 | ABAB | ABAB HM-1644 Access needed to pipe marked in red as shown in diagram for painting. Keep all boards/tubes/ply 250mm from pipe works. Subs #11B02-02 W/P #10033 | 2348 | Felise Emelio | 2016-03-01 | Hertel | Med Duty | ERECT | Complete | 2016-03-14 | 2016-03-25
5385 | ACAH | ACAH - AGRU 3 | Build access to perform flange management and bolt up pipe spool. Will also allow access for surveying purposes. ACAH module is currently located in the shake-out area off the south road. Similar scaffold is already in use on AGRU 2. | 2355 | David Goodes | 2016-03-02 | Mechanical | Med Duty | Erect | Not Started | 2016-03-09
5386 | AGRU 1 | AAAD | AAAD HM-1581. Erect scaffold deck 600mm down from bottom of pipe for insulation works. 225mm clearance required. | 2358 | Troy Brand | 2016-03-01 | Hertel | Med Duty | ERECT | Complete | 2016-02-24 | 2016-03-25
5387 | AGRU 1 | AAAD | AAAD HM-1582. Erect scaffold deck 600mm down from bottom of pipe for insulation works. 225mm clearance required. | 2359 | Troy Brand | 2016-03-01 | Hertel | Med Duty | ERECT | Complete | 2016-02-26 | 2016-03-25
5388 | AGRU 1 | AAAD | AAAD HM-1583. Erect scaffold deck 600mm down from bottom of pipe and chase vertical section with 225mm clearance required. | 2360 | Troy Brand | 2016-03-01 | Hertel | Med Duty | ERECT | Complete | 2016-02-26 | 2016-03-09
5389 | AGRU 2 | ABAA | Build scaffold to allow for pipe welding on purge cap and CW5. Floor height to be at same level as module walkay-no lower. Will need high handrails for encapsulation. Mods required for final fit and prep. Make big enough for welders, equipment, inspectors-big is good. | 2361 | David Goodes | 2016-03-02 | Mechanical | Med Duty | ERECT | Complete | 2016-03-09 | 2016-03-22
5390 | DOMGAS | North end DOMGAS Ground level | Dismantle scaffold on northern end DOMGAS | 2362 | Daniel Edwards | 2016-03-02 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-02 | 2016-03-06
5391 | DAAA | North end DOMGAS Ground floor | Need to remove all the higher standards that were used for the tie off of humpy | 2363 | Daniel Edwards | 2016-03-02 | Mechanical | Med Duty | MODIFY | Complete | 2016-03-03 | 2016-03-05
5392 | DOMGAS | Top of RV Platform DOMGAS | Dismantle humpy tubing on top of RV platform. | 2364 | Daniel Edwards | 2016-03-02 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-03 | 2016-03-06
5393 | UTILITY WEST | DAA | Require a mobile work bench to assist in fabrication of brackets/cable tray & cabe ladder. Fixing electrical devices to bracketry etc. Overall size to be around 3m x 1m. | 2365 | Gavin Hughes | 2016-03-02 | Electrical | Med Duty | ERECT | Complete | 2016-03-04 | 2016-03-07
5393 | DAAA | DAAA | Dismantle Scaffold | 4307 | Trevor Pike | 2016-05-14 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-20 | 2016-05-12
5394 | DOMGAS | DAAA Ground level South side of B8372 (Substation) and HV transformer | Humpy required: Overall size 3m Wide x 4m Long x 3m High. Build at grade, between substation B8372 and the HV transformer bay (south of the substation). Require a humpy/work shelter with a work bench (4m long x 1m wide) incorporated in the middle of the scaffold around 1200mm H (so each side of the work bench can be used for fabrication works). Shade on roof and the two ends only. | 2366 | Gavin Hughes | 2016-03-02 | Electrical | Med Duty | ERECT | Complete | 2016-03-04 | 2016-03-09
5394 | DOMGAS | DAAA Ground level South side of B8372 (Substation) and HV transformer | Dismantle 5394 | 4280 | Steve Linton | 2016-05-12 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-12 | 2016-05-13
5394 | DAAA | DAAA | Dismantle Scaffold | 4309 | Trevor Pike | 2016-05-14 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-20 | 2016-05-12
5395 | MOF | SCAL-SCAM | SCAL-SCAM HM-1655 Access needed to pipe marked in red box as shown in diagram for insulation. Keep all boards/tubes/ply 250mm from pipe works. | 2367 | Felise Emelio | 2016-03-02 | Hertel | Med Duty | MODIFY | Complete | 2016-03-16 | 2016-04-24
5396 | MOF | SCAH-SCAJ | SCAH-SCAJ HM-1656 Access needed to pipe marked in red box as shown in diagram for insulation. Keep all boards/tubes/py 250mm from pipe works. | 2368 | Felise Emelio | 2016-03-02 | Hertel | Med Duty | MODIFY | Complete | 2016-03-16 | 2015-03-18
5397 | MOF | SATT-SCAA | SATT-SCAA HM-1657 complete scaffold to pipe marked n red box as shown in diagram for insulation. Keep all boards/tubes/ply 250mm from pipe works. | 2369 | Felise Emelio | 2016-03-02 | Hertel | Med Duty | MODIFY | Complete | 2016-03-16 | 2016-04-24
5398 | AGRU 1 | AAAA | AAAA HM-1660 require all scaffold to pipe marked in red box as shown in diagram for insulation. Keep all boards/tubes/ply 250mm from pipe works. | 2372 | Felise Emelio | 2016-03-02 | Hertel | Med Duty | ERECT | Complete | 2016-03-09 | 2016-03-12
5399 | AGRU 1 | AAAA | AAAA HM-1659 require scaffold to pipe marked in red box as shown in diagram for insulation. Keep all boards/tubes/ply 250mm from pipe works. | 2371 | Felise Emelio | 2016-03-02 | Hertel | Med Duty | ERECT | Complete | 2016-03-09 | 2016-03-19
5400 | AGRU 1 | AAAA | AAAA HM-1658 require scaffold to pipe marked in red box as shown in diagram for insulation. Keep all boards/tubes/ply 250mm from pipe works. | 2370 | Felise Emelio | 2016-03-02 | Hertel | Med Duty | ERECT | Complete | 2016-03-09 | 2016-03-19
5401 | MEG | JACA | JACA HM-1661 raise scaffold deck 500mm as shown in diagram for chartek work. | 2373 | Felise Emelio | 2016-03-02 | Hertel | Med Duty | MODIFY | Complete | 2016-03-16 | 2016-03-10
5402 | INLET | RBAE | RBAE HM-1663 need scaffold frame to encapsulate shown in diagram for chartek work. | 2374 | Felise Emelio | 2016-03-02 | Hertel | Med Duty | ERECT | Complete | 2016-03-16 | 2016-03-30
5403 | INLET | RBAE | RBAE HM-1664 modify scaffold 300mm clearance from pink steel to allow for chartek works. Encapsulation will be needed. | 2375 | Felise Emelio | 2016-03-02 | Hertel | Med Duty | MODIFY | Complete | 2016-03-16 | 2016-04-02
5404 | FUELGAS | UACA | UACA HM-1666 extend scaffold west o allow for paint/blast works on field welds. | 2376 | Felise Emelio | 2016-03-02 | Hertel | Med Duty | ERECT | Complete | 2016-03-16 | 2016-03-08
5405 | FUELGAS | UACA | UACA HM-1667 hop up required to allow for paint/blast works on field welds | 2377 | Felise Emelio | 2016-03-02 | Hertel | Med Duty | MODIFY | Complete | 2016-03-17 | 2016-03-09
5406 | INLET | RBAQ | Move a temporary scaffold handrail back approximately 100-200mm, to allow the permanent handrail to be installed in its place. The handrail is located on the first level of the module. Once the permanent handrail is in place, the temporary scaffold handrail can then be removed. | 2378 | Jason Princen | 2016-03-02 | Mechanical | Med Duty | MODIFY | Complete | 2016-03-09 | 2016-03-08
5407 | OLIVER | OLIVER YARD | X3 weld humpys able to be lifted by crane. At least 3 x 3 x 3.5 high | 2379 | George Allan | 2016-03-03 | Mechanical | Med Duty | ERECT | Complete | 2016-03-07 | 2016-03-19
5408 | INLET | PRODUCTION PUMP | Dismantle scaffold for removal of valve | 2380 | Mark Farley | 2016-03-03 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-03 | 2016-03-04
5409 | INLET | GAA5 | GAA5 HM-1645 Access needed to pipe marked in red as shown in diagram for painting. Keep all boards/tubes/ply 250mm from pipe works. Subs #47A10-06 W/P #2194 | 2356 | Felise Emelio | 2016-03-01 | Hertel | Med Duty | ERECT | Complete | 2016-03-14 | 2016-03-18
5410 | INLET | GAA3 | GAA3 HM-1646 Access needed to X2 pipe marked in red as shown in diagram for painting. Keep all boards/tubes/ply 250mm from pipe works. Subs #45J00 47E10.03 W/P #2056 | 2357 | Felise Emelio | 2016-03-01 | Hertel | Med Duty | ERECT | Complete | 2016-03-14 | 2016-03-16
5411 | TAJB | TRAIN 1 - TAJB | Require a scaffold built to access the underside of the 2nd level in Train 1 in order to tighten a turn buckle lock nut. The scaffold can be built off level 1. | 2381 | Jason Princen | 2016-03-03 | Mechanical | Med Duty | ERECT | Cancelled | 2016-03-09
5412 | AAAA | AGRU 1 | AAAA HM-1626 need access to lines on 5 pumps, for insulation scope. Keep 250mm clearance boards/tubes/ply from pipe.subs 11B-01-02 | 2383 | Felise Emelio | 2016-03-04 | Hertel | Med Duty | ERECT | Complete | 2016-03-08 | 2016-03-11
5413 | AAAA | AGRU 1 | AAAA HM-1626 need access to lines on 5 pumps, for insulation scope. Keep 250mm clearance boards/tubes/ply from pipe.subs 11B-01-02 | 2384 | Felise Emelio | 2016-03-04 | Hertel | Med Duty | ERECT | Complete | 2016-03-08 | 2016-03-11
5414 | AAAA | AGRU 1 | AAAA HM-1626 need access to lines on 5 pumps, for insulation scope. Keep 250mm clearance boards/tubes/ply from pipe.subs 11B-01-02 | 2385 | Felise Emelio | 2016-03-04 | Hertel | Med Duty | ERECT | Complete | 2016-03-08 | 2016-03-11
5415 | AAAA | AGRU 1 | AAAA HM-1626 need access to lines on 5 pumps, for insulation scope. Keep 250mm clearance boards/tubes/ply from pipe.subs 11B-01-02 | 2386 | Felise Emelio | 2016-03-07 | Hertel | Med Duty | ERECT | Complete | 2016-03-08 | 2016-03-11
5416 | TADA | TRAIN 1 - TADA | Require 2 x scaffolds to be dismantled that were previously in place to protect an open penetration where grid mesh had been removed. The scaffolds are located on level 3. | 2382 | Jason Princen | 2016-03-03 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-09 | 2016-03-16
5417 | DAAA | 1066 DAAA | South Western corner of Domgas, there is a main round column with a scaffold build along the southern part of the module. We need to have to scaffold modified to expose a hole around 500mm x 500mm, in the north western part of this partiular scaffold build. | 2394 | Gavin Hughes | 2016-03-04 | Electrical | Med Duty | MODIFY | Complete | 2016-03-07 | 2016-03-04
5418 | TBAA | TRAIN 2 Re-Boilers TBBA -2E-1601 | Build Scaffold to access flanges, and welding on reboilers 2E-1601. 2E-1612, 2E-1613, Area: TRAIN 2 Re-Boilers TBBA -2E-1601 | 2395 | Mick Zalmsina | 2016-03-04 | Mechanical | Med Duty | ERECT | Complete | 2016-03-07 | 2016-03-03
5418 | TBBA | TBBA TRAIN 2 RE-BOILERS | As per attached model shots and scaffold tag numbers. | 4215 | Brett Taane | 2016-05-11 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-14 | 2016-05-14
5419 | TBAA | TRAIN 2 Re-Boilers TBBA -2E-1601 | Build Scaffold to access flanges, and welding on reboilers 2E-1601. 2E-1612, 2E-1613, Area: TRAIN 2 Re-Boilers TBBA -2E-1601 | 2396 | Mick Zalmsina | 2016-03-04 | Mechanical | Med Duty | ERECT | Complete | 2016-03-07 | 2016-03-03
5420 | TBAA | TRAIN 2 Re-Boilers TBBA -2E-1601 | Build Scaffold to access flanges, and welding on reboilers 2E-1601. 2E-1612, 2E-1613, Area: TRAIN 2 Re-Boilers TBBA -2E-1601 | 2397 | Mick Zalmsina | 2016-03-04 | Mechanical | Med Duty | ERECT | Complete | 2016-03-07 | 2016-03-11
5420 | TBBA | TBBA TRAIN 2 RE-BOILERS | As per attached model shots and scaffold tag numbers. Nightshift | 4224 | Brett Taane | 2016-05-11 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-14 | 2016-05-19
5421 | TBBA | TRAIN 2 Re-Boilers TBBA -2E-1601 | Build Scaffold to access flanges, and welding on reboilers 2E-1601. 2E-1612, 2E-1613, Area: TRAIN 2 Re-Boilers TBBA -2E-1601 | 2398 | Mick Zalmsina | 2016-03-04 | Mechanical | Med Duty | ERECT | Complete | 2016-03-07 | 2016-03-14
5421 | TBBA | TBBA TRAIN 2 RE-BOILERS | As per attached model shots and scaffold tag numbers. | 4223 | Brett Taane | 2016-05-11 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-14 | 2016-05-14
5422 | TBBA | TRAIN 2 Re-Boilers TBBA -2E-1601 | Build Scaffold to access flanges, and welding on reboilers 2E-1601. 2E-1612, 2E-1613, Area: TRAIN 2 Re-Boilers TBBA -2E-1601 | 2399 | Mick Zalmsina | 2016-03-04 | Mechanical | Med Duty | ERECT | Complete | 2016-03-07 | 2016-03-22
5422 | TBBA | TBBA TRAIN 2 RE-BOILERS | As per attached model shots and scaffold tag numbers. | 4220 | Brett Taane | 2016-05-11 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-14 | 2016-05-14
5423 | TBBA | TRAIN 2 Re-Boilers TBBA -2E-1601 | Build Scaffold to access flanges, and welding on reboilers 2E-1601. 2E-1612, 2E-1613, Area: TRAIN 2 Re-Boilers TBBA -2E-1601 | 2400-1 | Mick Zalmsina | 2016-03-04 | Mechanical | Med Duty | ERECT | Complete | 2016-03-07 | 2016-03-18
5423 | TBBA | TRAIN 2 Re-Boilers TBBA -2E-1601 | Dismantle 5423 | 2400-2 | Mick Zalmsina | 2016-05-15 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-15 | 2016-03-18
5424 | AGRU 1 | AGRU 1 | Strip old riggers loft on the very north end of AGRU 1 near the road. | 2387 | David Goodes | 2016-03-03 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-11 | 2016-03-22
5425 | UACA | UACA East/West Piperack - 721 | Scaffold to be built up to access field welds guides and support with full encaputlation | 933 | Daniel Edwards | 2015-09-09 | Mechanical | Med Duty | ERECT | Complete | 2015-09-16 | 2015-09-16
5425 | UACA | UACA East/West Piperack - 721 | Scaffold at UACA on the East/West piperack needs to be completed, as its was stripped for cyclone prep. Toe boards and mesh panels need to be replaced. | 2388 | Gavin Hughes | 2016-03-03 | Electrical | Med Duty | MODIFY | Complete | 2016-03-04 | 2016-03-08
5426 | JAA1 | JAA1 | JAA1 HM-1675 access required to pipes mark in red shown in diagram for PIF scopes keep all boards/tube/ply clearance of 250mm from pipe works subs 47E10-03 W/P 2221 | 2389 | Felise Emelio | 2016-03-03 | Hertel | Med Duty | ERECT | Complete | 2016-03-22 | 2016-03-24
5427 | AAAA | AAAA | AAAA HM-1676 access required to pipes marked in red shown in diagram for PIF scopes keep all boards/tube/ply clearance of 250mm from pipe works subs 64C01-00 W/P 8279 | 2390 | Felise Emelio | 2016-03-03 | Hertel | Med Duty | ERECT | Complete | 2016-03-17 | 2016-04-24
5428 | B8331 | B8331 | B8331 HM-1671 access required to x3 pipes for PIF scopes keep all boards/tube/ply clearance of 250mm from pipe works. Also need to retag scaffolds shown in diagram. Subs 46C03-08/02/07 W/P 46C03-02-20000-NP | 2391 | Felise Emelio | 2016-03-03 | Hertel | Med Duty | ERECT | Complete | 2016-03-17 | 2016-04-24
5429 | GAA1 | GAA1 | GAA1 HM-1677 access required to pipes marked in red shown in diagram for PIF scopes keep all board/tube/ply clearance of 250mm from pipe orks subs 47G00-00 W/P 2199 | 2392 | Felise Emelio | 2016-03-03 | Hertel | Med Duty | ERECT | Complete | 2016-03-22 | 2016-04-24
5430 | SASL | SASL | SASL HM-1684 access required to pipes marked in red shown in diagram for PIF scopes keep all boards/tube/ply clearance of 250mm from pipe works subs 45R00-00 W/P 6185 | 2393 | Felise Emelio | 2016-03-03 | Hertel | Med Duty | ERECT | Complete | 2016-03-17 | 2016-04-24
5431 | DAAA | DOMGAS | Lower existing deck - Double up of tag 5125 | 2401 | Charlie Bryce | 2016-03-04 | Mechanical | Med Duty | MODIFY | Complete | 2016-03-11 | 2016-03-09
5432 | INLET | North Inlet - RBAQ | Build edge protection in two locations for grid mesh removal. The locations are on the 2nd and 3rd level of the RBAQ module in North Inlet. | 2402 | Jason Princen | 2016-03-04 | Mechanical | Med Duty | ERECT | Complete | 2016-03-11 | 2016-03-17
5432 | INLET | North Inlet - RBAQ | Dismaltle | 2402 | Jason Princen | 2016-04-25 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-04-25 | 2016-04-29
5432 | TBBA | TBBA TRAIN 2 RE-BOILERS | As per attached model shots and scaffold tag numbers. | 4216 | Brett Taane | 2016-05-11 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-14 | 2016-05-22
5433 | INLET | Tool store inlet | Erect shade scaffold above 40 ft tool store | 2403 | Shane Shillabeer | 2016-03-05 | Mechanical | Med Duty | ERECT | Complete | 2016-03-12 | 2016-04-22
5434 | DOMGAS | DAAA DOMGAS | Modify scaff to weld line stops on the North side of pipe shoe. Please note: Scaffold has been extended previously to do task however it needs more. | 2404 | Daniel Edwards | 2016-03-05 | Mechanical | Med Duty | MODIFY | Cancelled | 2016-03-05
5435 | JAC1 | JAC1 | JAC1 HM-1698 need to erect scaffold to complete FW keep tubes/boards/ply 250mm clearance from pipe works. | 2405 | Felise Emelio | 2016-03-05 | Hertel | Med Duty | ERECT | Cancelled | 2016-03-17
5436 | JABH | JABH | Erect over head protection due to possible ice falling from pipes. | 2406 | Mark Orr | 2016-03-05 | Chevron | Med Duty | ERECT | Complete | 2016-03-05 | 2016-03-11
5437 | RBCB | RBCB | Erect over head protection due to possible ice falling from pipes. | 2407 | Mark Orr | 2016-03-05 | Chevron | Med Duty | ERECT | Complete | 2016-03-05 | 2016-03-11
5438 | RBCA | RBCA | Erect over head protection due to possible ice falling from pipes. | 2408 | Mark Orr | 2016-03-05 | Chevron | Med Duty | ERECT | Complete | 2016-03-05 | 2016-03-11
5439 | RBCD | RBCD | Erect over head protection due to possible ice falling from pipes. | 2409 | Mark Orr | 2016-03-05 | Chevron | Med Duty | ERECT | Complete | 2016-03-05 | 2016-03-11
5440 | RBCC | RBCC | Erect over head protection due to possible ice falling from pipes. | 2410 | Mark Orr | 2016-03-05 | Chevron | Med Duty | ERECT | Complete | 2016-03-05 | 2016-03-11
5441 | JADA | JADA | Permit request #11: Navis picture 3 off shows were Scaffold is required for the Boilermaker to install Encapsulation to weld brackets | 2412 | Gunther Grossinger | 2016-03-05 | Electrical | Med Duty | ERECT | Complete | 2016-03-07 | 2016-03-19
5442 | INLET | GAA1 | Please remove scaffold boards on the following scaffold in the GAA1 area and reinstate after valve installation. Scaffold No H1622 | 2413 | Michael Outram | 2016-03-06 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-09 | 2016-03-14
5443 | TRAIN 1 | TADA | We require scaffold handrail/edge protection erected for grid mesh removal. Once the gridmsh has been modified and repaced, he scaffold can then be dismantled. The 2 locations are on the 1st and 3rd level. | 2414 | Jason Princen | 2016-03-06 | Mechanical | Med Duty | ERECT | Cancelled | 2016-03-12
5444 | AGRU 2 | AGRU 2 | Require extension to scaff ABAH 1158 to allow for welding of purge caps | 2415 | David Goodes | 2016-03-06 | Mechanical | Med Duty | MODIFY | Complete | 2016-03-12 | 2016-03-09
5445 | INLET | GAA1 | Permit request #10: Navis picture 4 off shows were Scaffold is required to be build for Encapsulation, for the Boilermakers to weld Brackets | 2411 | Gunther Grossinger | 2016-03-05 | Electrical | Med Duty | ERECT | Complete | 2016-03-08 | 2016-03-15
5446 | GACA | South Inlet - GACA | Require handrail/edge protection to be built for a grid mesh removal. | 2416 | Jason Princen | 2016-03-07 | Mechanical | Med Duty | ERECT | Complete | 2016-03-10 | 2016-03-16
5447 | Inlet | Inlet | Takeover mas scaffold 0087 | 2417 | Felise Emelio | 2016-03-07 | Hertel | Med Duty | ERECT | Complete | 2016-03-10 | 2016-03-10
5447 | RBAE | RBAE-RBAP | RBAE-RBAP HM-1995 tag 5447 Scaffold can be dismantled on interface painting works complete. HM-257 | 3403 | Felise Emelio | 2016-04-20 | Hertel | Med Duty | DISMANTLE | Complete | 2016-04-20 | 2016-05-18
5448 | ABAA | AGRU 2 | ERECT SCAFFOLD TO ACCESS CLOSURE WELDS 5 & 36, ENSURE THE DECKS ARE 1M ALL THE WAY AROUND THE EXCEPT WHERE IT CLASHES WITH THE AMEIN VESSLE BOTTOM DECK WILL NEED TO BE AT THE CENTER LINE OF THIS PIPE | 2418 | David Goodes | 2016-03-08 | Mechanical | Med Duty | MODIFY | Complete | 2016-03-08 | 2016-03-22
5448 | Agru 2 | Aru 2 RL 33 | Build/modify current scaffold to allow for CW14 encapulation and welding. Please bare in mind any potential clashes with the next spool installation. Please allow as much room as possible around spool with min 600mm clearance under spool | 2684 | David Goodes | 2016-03-24 | Mechanical | Med Duty | MODIFY | Complete | 2016-03-31 | 2016-04-14
5449 | ABAE | ABAE top level | Modify existing scaffold to carry,anchor and support 2 x 12" lines to allow the line to pass through from level to level at the flushing, chemical and passivation cleaning of and passivation of the heating medium system at AGRU 2 As this activity spans across both construction and operations areas (Symops) it may be prudent to make this a night shift scope. maybe prudent to make this a night shift scope Existing scaffold number is DO 192 AGRU 2 ABAE top level | 2420 | Lennie Haira | 2016-03-07 | CSU | Med Duty | MODIFY | Complete | 2016-03-09 | 2016-04-13
5450 | ABAE | AGRU 2 | remove scaffold deck from below FW33MODIFY EXISTING SCAFFOLD FOR ROTATION OF ELBOW | 2421 | David Goodes | 2016-03-08 | Mechanical | Med Duty | MODIFY | Complete | 2016-03-08 | 2016-03-22
5451 | TBAA | TBAA | Hop up is required for Catalyst loading on the 3 sisters Vessel: 2C-1301 Scaff is required for a change humpy nere the rescue ramp | 2422 | Andrew Ledingham | 2016-03-08 | Mechanical | Med Duty | MODIFY | Complete | 2016-03-12 | 2016-03-22
5452 | RBAG | RBAG | Mesh Panels to be reinstalled & secured & scaffold to be registered & approval to be retagged for use. 5 levels all need mesh installed | 2423 | Felise Emelio | 2016-03-08 | Hertel | Med Duty | ERECT | Complete | 2016-03-09 | 2016-03-09
5452 | RBAG | H1950 | Take over H1950 | 2423 | Felise Emelio | 2016-03-08 | Hertel | Med Duty | TAKEOVER | Complete | 2016-03-09 | 2016-03-09
5453 | Inlet | Inlet | Takeover mas scaffold | 2424 | Felise Emelio | 2016-03-07 | Hertel | med duty | TAKEOVER | Complete | 2016-03-07 | 2016-03-11
5454 | Inlet | Inlet | Takeover mas scaffold | 2425 | Felise Emelio | 2016-03-07 | Hertel | med duty | TAKEOVER | Complete | 2016-03-07 | 2016-03-11
5455 | GAC1 | Inlet | Takeover mas scaffold | 2426 | Felise Emelio | 2016-03-07 | Hertel | med duty | TAKEOVER | Complete | 2016-03-07 | 2016-03-11
5455 | GAC1 | Inlet | Modify Takeover mas scaffold | 2426 | Felise Emelio | 2016-03-07 | Hertel | med duty | MODIFY | Complete | 2016-03-07 | 2016-05-20
5456 | Inlet | Inlet | Takeover mas scaffold | 2427 | Felise Emelio | 2016-03-07 | Hertel | med duty | TAKEOVER | Complete | 2016-03-07 | 2016-03-11
5457 | Inlet | Inlet | Takeover mas scaffold | 2428 | Felise Emelio | 2016-03-07 | Hertel | med duty | TAKEOVER | Complete | 2016-03-07 | 2016-04-19
5458 | RBAC | RBAC | Takeover mas scaffold | 2429 | Felise Emelio | 2016-03-07 | Hertel | med duty | TAKEOVER | Complete | 2016-03-07 | 2016-03-11
5458 | RBAC | RBAC | RBAC HM-1763 tag 5458 level 3 need to extend scaffold 1m west past flanges to allow for insulation works. Keep all tubes/ply 225mm clearance from pipe works. | 2546 | Felise Emelio | 2016-03-15 | Hertel | med duty | MODIFY | Complete | 2016-03-29 | 2016-03-27
5459 | Inlet | Inlet | Takeover mas scaffold | 2430 | Felise Emelio | 2016-03-07 | Hertel | med duty | TAKEOVER | Complete | 2016-03-07 | 2016-03-11
5460 | Inlet | Inlet | Takeover mas scaffold | 2431 | Felise Emelio | 2016-03-07 | Hertel | med duty | TAKEOVER | Complete | 2016-03-07 | 2016-03-11
5461 | Inlet | Inlet | Takeover mas scaffold | 2432 | Felise Emelio | 2016-03-07 | Hertel | med duty | TAKEOVER | Complete | 2016-03-07 | 2016-03-11
5461 | Inlet | Inlet | Dismantle 5461 | 2432 | Felise Emelio | 2016-03-07 | Hertel | med duty | TAKEOVER | Complete | 2016-03-07 | 2016-05-08
5462 | Inlet | Inlet | Takeover mas scaffold | 2433 | Felise Emelio | 2016-03-07 | Hertel | med duty | TAKEOVER | Complete | 2016-03-07 | 2016-03-11
5463 | GAC1 | GAC1 Inlet South | Takeover mas scaffold | 2434 | Felise Emelio | 2016-03-07 | Hertel | med duty | TAKEOVER | Complete | 2016-03-07 | 2016-03-11
5463 | GAC1 | GAC1 Inlet South | Raise & modify Deck height by approx. 0.7m Deck to be adjusted to suit installation of pipe & welding of pipe | 3757 | Paul Cummins | 2016-04-29 | Mechanical | Med Duty | MODIFY | Complete | 2016-04-01 | 2016-05-12
5463 | GAC1 | GAC1 Inlet South | Please remove scaff deck as it is in the way of pipe install & welding activities | 3758 | Paul Cummins | 2016-04-29 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-04-01 | 2016-05-18
5464 | Inlet | Inlet | Takeover mas scaffold | 2435 | Felise Emelio | 2016-03-07 | Hertel | med duty | TAKEOVER | Complete | 2016-03-07 | 2016-03-11
5465 | Inlet | Inlet | Takeover mas scaffold | 2436 | Felise Emelio | 2016-03-07 | Hertel | med duty | TAKEOVER | Complete | 2016-03-07 | 2016-03-11
5466 | Inlet | Inlet | Takeover mas scaffold | 2437 | Felise Emelio | 2016-03-07 | Hertel | med duty | TAKEOVER | Complete | 2016-03-07 | 2016-03-11
5467 | Inlet | Inlet | Takeover mas scaffold | 2438 | Felise Emelio | 2016-03-07 | Hertel | med duty | TAKEOVER | Complete | 2016-03-07 | 2016-03-11
5467 | GAC1 | GAC1 Inlet South | Raise & modify Deck height by approx. 0.5m Deck to be adjusted to suit installation of pipe & welding of pipe | 3756 | Paul Cummins | 2016-04-29 | Mechanical | Med Duty | MODIFY | Complete | 2016-04-01 | 2016-05-10
5468 | Inlet | Inlet | Takeover mas scaffold | 2439 | Felise Emelio | 2016-03-07 | Hertel | med duty | TAKEOVER | Complete | 2016-03-07 | 2016-03-11
5469 | Inlet | Inlet | Takeover mas scaffold | 2440 | Felise Emelio | 2016-03-07 | Hertel | med duty | TAKEOVER | Complete | 2016-03-07 | 2016-03-11
5469 | GAC1 | GAC1 | Re-Build scaffold top deck / dismantle and erect for new purpose to access welds on ISO GAC1 - O -D 09132-01 | 4489 | Charlie Bryce | 2016-05-22 | Mechanical | Med Duty | MODIFY | Complete | 2016-05-28 | 2016-05-20
5470 | Inlet | Inlet | Takeover mas scaffold | 2441 | Felise Emelio | 2016-03-07 | Hertel | Med Duty | TAKEOVER | Complete | 2016-03-07 | 2016-03-09
5471 | Inlet | Inlet | Takeover mas scaffold | 2442 | Felise Emelio | 2016-03-07 | Hertel | Med Duty | TAKEOVER | Complete | 2016-03-07 | 2016-03-10
5472 | Inlet | Inlet | Takeover mas scaffold | 2443 | Felise Emelio | 2016-03-07 | Hertel | Med Duty | TAKEOVER | Complete | 2016-03-07 | 2016-03-10
5473 | DAAA | DOMGAS | Exsiting scaffold on ground level SE crn of the filter platform requires a ladder to be installed | 2444 | Charlie Bryce | 2016-03-08 | Mechanical | Med Duty | MODIFY | Complete | 2016-03-10 | 2016-03-17
5473 | DOMGAS | Domgas DAAA | Dismantle 5473 as per Nightshift Request | 4281 | Steve Linton | 2016-05-12 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-12 | 2016-05-13
5475 | GUA | GUA - MAJ2 / Tank OT-6401 | Remove current scaffold, handrail & barricade, on top of tank OT-6401 and remove all platforms around ground level near stair access and manholes. | 2446 | Wayne McCarthy | 2016-03-08 | Mechanical | Med Duty | TAKEOVER | Complete | 2016-03-10 | 2016-03-14
5476 | GUA | GUA - MAJ2 / Tank OT-6401 | Remove current scaffold, handrail & barricade, on top of tank OT-6401 and remove all platforms around ground level near stair access and manholes. | 2447 | Wayne McCarthy | 2016-03-08 | Mechanical | Med Duty | TAKEOVER | Complete | 2016-03-10 | 2016-03-14
5477 | GUA | GUA - MAJ2 / Tank OT-6401 | Remove current scaffold, handrail & barricade, on top of tank OT-6401 and remove all platforms around ground level near stair access and manholes. | 2448 | Wayne McCarthy | 2016-03-08 | Mechanical | Med Duty | TAKEOVER | Complete | 2016-03-10 | 2016-03-14
5478 | RBAD | INET - RBAD1081 | Buid scaffold to preform flange management and bolt up pipe spool. Will Also allow access for surveying purpose | 1804 | Robert Hanley | 2015-12-22 | Mechanical | Med Duty | ERECT | Complete | 2015-12-25 | 2015-12-24
5478 | RBAD | INET - RBAD1081 | Erect scaffold to allow acess to 20NB blind flange no encapsulation required | 1876 | Robert Hanley | 2016-01-01 | Mechanical | Med Duty | MODIFY | Complete | 2016-01-01 | 2015-12-31
5478 | RBAD | INET - RBAD1081 | Dismantle Works left over from Heater Medium Works | 2449 | Mark Farley | 2016-03-07 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-12 | 2016-03-11
5478 | RBAD | Inlet West end RBAD | Dismantle scaffold 1081 left over from the Heater Medium works | 2449 | Mark Farley | 2016-03-08 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-10 | 2016-03-11
5479 | RBAD | Inlet West end RBAD | Dismantle scaffold 1085 left over from the Heater Medium works | 2450 | Mark Farley | 2016-03-08 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-10 | 2016-03-11
5480 | RBAD | Inlet West end RBAD | Dismantle scaffold 1118 left over from the Heater Medium works | 2451 | Mark Farley | 2016-03-08 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-10 | 2016-03-13
5481 | RBAD | Inlet West end RBAD | Dismantle scaffold 1082 left over from the Heater Medium works | 2452 | Mark Farley | 2016-03-08 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-10 | 2016-03-13
5481 | GAA1 | Inlet North GAA1 | Set up shadeded area with a bench for guys to put drawings ect approx 2.4 long | 2455 | Mark Farley | 2016-03-08 | Mechanical | Med Duty | ERECT | Complete | 2016-03-16 | 2016-04-02
5482 | RBAH | H1468 RBAH top level | 1. Scaffold on the underside of RBAH top level needs to be lifted approx 900mm also noth west crn needs to be extended for grid mesh removal on the top level. | 2453 | Mark Farley | 2016-03-08 | Mechanical | Med Duty | TAKEOVER | Complete | 2016-03-12 | 2016-03-19
5482 | RBAH | H1468 RBAH top level | 1. Scaffold on the underside of RBAH top level needs to be lifted approx 900mm also noth west crn needs to be extended for grid mesh removal on the top level. | 2724 | Mark Farley | 2016-03-26 | Mechanical | Med Duty | MODIFY | Complete | 2016-03-12 | 2016-03-19
5483 | RBAH | Top level RBAH | 2. Hard baricade with gate access 100% hood up fall restraints attchment points for grid mesh removal on the top level | 2454 | Mark Farley | 2016-03-08 | Mechanical | Med Duty | ERECT | Complete | 2016-03-12 | 2016-03-19
5485 | GAA1 | Inlet North GAA1 | Access required to fit and weld 200nb pipe joint Must allow encaptulation | 2456 | Michael Outram | 2016-03-08 | Mechanical | Med Duty | ERECT | Complete | 2016-03-11 | 2016-04-16
5485 | GAA1 | Inlet North GAA1 | modify scaffolf acess | 2456 | Michael Outram | 2016-03-08 | Mechanical | Med Duty | MODIFY | Complete | 2016-03-11 | 2016-05-15
5486 | JACA | JACA HM-1724 | JACA HM-1724 Need to access pipe to insulate heat trace line keep all boards/tubes 250mm clearance from pipe works. deck height 1.8m below pipe. | 2457 | Felise Emelio | 2016-03-09 | Hertel | Med Duty | ERECT | Complete | 2016-03-23 | 2016-03-18
5488 | DAAA | DAAA 1147 | Removal of scaffold #1147 in Domgas module DAAA to access electrical installation works | 2459 | Mathew Poole | 2016-03-09 | Electrical | Med Duty | DISMANTLE | Complete | 2016-03-10 | 2016-05-24
5488 | DAAA | GAA4 H820 | Inspect & Take over | 2458 | Mark Farley | 2016-03-09 | Mechanical | Med Duty | TAKEOVER | Complete | 2016-03-14 | 2016-03-18
5489 | JAC1 | JAC1 | JAC1 HM-1722 hop up needed to allow for paint/blast works. | 2445 | Felise Emelio | 2016-03-08 | Hertel | Med Duty | ERECT | Complete | 2016-03-22 | 2016-03-29
5490 | GAA1 | GAA1, MEG Injection Pumps | Removal of redundant scaffold to allow for spoll installation and fitting of machining equipment. Some boards have been removed on separate request. After careful planning, and extra work scope, it has been decided the best way forward is to remove entire scaffold. | 2461 | Michael Outram | 2016-03-10 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-12 | 2016-03-14
5491 | GAA1 | Meg Injection Pumps GAA1 | Existing CBI scaffold to be stripped to allow for crane access, spool installation and pipe work preperation. Removal of this scaffold will allow for tie in | 2462 | Michael Outram | 2016-03-10 | Mechanical | Med Duty | TAKEOVER | Complete | 2016-03-12 | 2016-04-19
5492 | GAHK | GAHK | Erect shade structure with tarps above MEG Pumps | 2463 | Shane Shillabeer | 2016-03-10 | Mechanical | Med Duty | ERECT | Complete | 2016-03-12 | 2016-03-20
5492 | RBAM | RBAM | RBAM HM-2148 need a 225mm clearance on hole of pipe running north south for insulation works as shown to Kevin Hegarty. | 4673 | Felise Emelio | 2016-05-26 | Hertel | Med Duty | MODIFY | Not Started | 2016-06-02
5493 | DAAA | ground floor NE corner of DAAA | Scaffold built in DomGas for the welders to weld guides. Tagged it with #“Nightshift 2016. On the ground floor NE corner of DAAA. Will need proper tag etc. Pictures show location. | 2464 | Murray Tartaglia | 2016-03-11 | Mechanical | Med Duty | ERECT | Complete | 2016-03-11 | 2016-03-12
5493 | DAAA | DAAA | Urgent punch list items to be completed for RFSU by WE 13/05/16 Sub-system number - 40L01B-722 LF-DB8372-E02-15W-18-Light was removed and not fixed to structure - to be rectified - Ref-G1-TD-E-2400-LED0225M - scaffikd is restricting access and requires modification. | 4211 | Mick Finch | 2016-05-10 | Electrical | Med Duty | MODIFY | Complete | 2016-05-12 | 2016-05-10
5493 | DAAA | Domgas | Dismantle | 4391 | Trevor Pike | 2016-05-16 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-16 | 2016-05-19
5494 | DAAA | DAAA | DAAA HM-1668 Need to erect scaffold to allow for chartek works. | 2465 | Felise Emelio | 2016-03-11 | Hertel | Med Duty | ERECT | Complete | 2016-03-23 | 2016-03-14
5495 | Area 8 | SAP - Area 8 | 6 x Support Stands for Chevron (Pipe Support) A | 2466 | Mark Orr | 2016-03-11 | Chevron | Med Duty | ERECT | Complete | 2016-03-12 | 2016-03-11
5495 | Area 8 | SAP - Area 8 | 6 x Support Stands for Chevron (Pipe Support) B | 2466 | Mark Orr | 2016-03-11 | Chevron | Med Duty | ERECT | Complete | 2016-03-12 | 2016-03-11
5495 | Area 8 | SAP - Area 8 | 6 x Support Stands for Chevron (Pipe Support) C | 2466 | Mark Orr | 2016-03-11 | Chevron | Med Duty | ERECT | Complete | 2016-03-12 | 2016-03-11
5495 | Area 8 | SAP - Area 8 | 6 x Support Stands for Chevron (Pipe Support) D | 2466 | Mark Orr | 2016-03-11 | Chevron | Med Duty | ERECT | Complete | 2016-03-12 | 2016-03-11
5495 | Area 8 | SAP - Area 8 | 6 x Support Stands for Chevron (Pipe Support) E | 2466 | Mark Orr | 2016-03-11 | Chevron | Med Duty | ERECT | Complete | 2016-03-12 | 2016-03-11
5495 | Area 8 | SAP - Area 8 | 6 x Support Stands for Chevron (Pipe Support) F | 2466 | Mark Orr | 2016-03-11 | Chevron | Med Duty | ERECT | Complete | 2016-03-12 | 2016-03-11
5497 | GAA1 | GAA1 | Dismantle Scaffold H1622 | 2467 | THOMAS MURPHY | 2016-03-11 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-14 | 2016-03-11
5497 | GAA1 | GAA1 | Dismantle Scaffold H1622 | 2467 | THOMAS MURPHY | 2016-03-11 | Mechanical | Med Duty | TAKEOVER | Complete | 2016-03-14 | 2016-03-11
5498 | GTG3 | GTG3 | Inspect/tag mobile scaffold that CKJV have left behind, in order for us to use it to install a cable tray support. | 2468 | Jason Princen | 2016-03-11 | Mechanical | Med Duty | TAKEOVER | Complete | 2016-03-12 | 2016-03-15
5499 | GAA1 | GAA1 | Grid mesh removal - may require hard barricades to be moved and a fall restraint installed | 2469 | Shane Shillabeer | 2016-03-11 | Mechanical | Med Duty | ERECT | Complete | 2016-03-12 | 2016-04-16
5500 | Area 20 | 1199 - Baker Hughes Area L20 (near inlet area) | Baker Hughes (BH) require the removal of scaffolding from a flatbed trailer. The flat bed trailer currently contains BH Nitrogen equipment that needs to be demobilised off island and off hired.Name of scaff tag: Rey | 2470 | Simon Campbell | 2016-03-12 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-18 | 2016-03-14
5501 | Area 20 | H1960 - Baker Hughes Area L20 (near inlet area) | TAKEOVER H1960 | 2471 | Simon Campbell | 2016-03-12 | Mechanical | Med Duty | TAKEOVER | Complete | 2016-03-18 | 2016-03-13
5501 | Area 20 | H1960 - Baker Hughes Area L20 (near inlet area) | Baker Hughes (BH) require the removal of scaffolding from a flatbed trailer. The flat bed trailer currently contains BH Nitrogen equipment that needs to be demobilised off island and off hired.Name of scaff tag: Rey | 2471 | Simon Campbell | 2016-03-12 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-18 | 2016-03-14
5502 | L5/6 | L5 Tag Number 964 | extend Scaffold out for electricains to install new light.please speak to Shawn ma / Andrew Georgiou | 2474 | Andrew Georgiou | 2016-03-12 | Electrical | Med Duty | MODIFY | Complete | 2016-03-13 | 2016-05-04
5503 | L7 | L7 Tag number 338 | extend Scaffold out for electricains to install new light. Please speak to Shawn Ma / Andrew Georgiou | 2473 | Andrew Georgiou | 2016-03-12 | Electrical | Med Duty | MODIFY | Complete | 2016-03-13 | 2016-05-04
5504 | L10 | L9 - Tag no 972 | extend Scaffold out for electricains to install new light. Please speak to Shawn Ma/ Andrew Georgiou | 2472 | Andrew Georgiou | 2016-03-12 | Electrical | Med Duty | MODIFY | Complete | 2016-03-13 | 2016-05-04
5505 | LPW | LPW | Dismantle Chartek humpies at associated handrails at base of SAYV (LPW loading arms module) | 2483 | Martin Riegert | 2016-03-12 | scaffolding | Med Duty | DISMANTLE | Complete | 2016-03-13 | 2016-03-13
5506 | LPW | LPW "S" bend LNG line | Dismantle LPW "S" bend LNG line cladding access scaffold | 2484 | Martin Riegert | 2016-03-12 | scaffolding | Med Duty | DISMANTLE | Complete | 2016-03-13 | 2016-05-24
5507 | JH4 | JH4 - Jetty | Dismantle E&I cable tray access | 2482 | Martin Riegert | 2016-03-12 | scaffolding | Med Duty | DISMANTLE | Complete | 2016-03-13 | 2016-03-13
5508 | Agru 2 | Agru 2 | errect scaff frame to allow encapsulation at the back of Co2 store/ mini work shop | 2478 | Mike Knott | 2016-03-12 | Electrical | Med Duty | ERECT | Complete | 2016-03-17 | 2016-03-22
5509 | RBAL-RBAK | RBAL-RBAK | RBAL-RBAK HM-1743 Need to access pipe to allow for insulation works keep all boards/tubes 250mm clearance from pipe works. As shown to Kevin Hegarty. | 2477 | Felise Emelio | 2016-03-12 | Hertel | Med Duty | ERECT | Complete | 2016-03-16 | 2015-04-17
5510 | RBAL-RBAK | RBAL-RBAK | RBAL-RBAK HM-1744 Need to access pipe to allow for insulation works keep all boards/tubes 250mm clearance from pipe works. As shown to Kevin Hegarty. | 2476 | Felise Emelio | 2016-03-12 | Hertel | Med Duty | ERECT | Cancelled | 2016-03-16
5511 | GAEA | GAEA tag 557 | Dismantle 557 ground level west side | 2479 | John Watson | 2016-03-12 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-13 | 2016-03-23
5512 | GAEA | GAEA tag A 1716 | Dismantle A 1716 - top level humpy | 2480 | John Watson | 2016-03-12 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-13 | 2016-03-23
5513 | RBAL-RBAK | RBAL-RBAK | RBAL-RBAK HM-1745 Need to access pipe to allow for insulation works keep all boards/tubes 250mm clearance from pipe works and 500mm structural steel e.g. standards As shown to Kevin Hegarty. | 2475 | Felise Emelio | 2016-03-12 | Hertel | Med Duty | ERECT | Cancelled | 2016-03-16
5514 | LPW | LWP North side. MD4W,MD5W. | Punch list for lighting on MD4W - MD5W. Lighting on walkway side of capstans. | 2485 | Grant Percy | 2016-03-12 | Electrical | Med Duty | ERECT | Complete | 2016-03-13 | 2016-05-24
5515 | TBAA | Train 2 TBAA | Erect scaffold for access to install isolations on gas probes and double block and bleed drain blinds | 2486 | Brett Taane | 2016-03-12 | Mechanical | Med Duty | ERECT | Complete | 2016-03-14 | 2016-03-15
5515 | TBAA | Train 2 TBAA | Dismantle | 2486 | Brett Taane | 2016-03-12 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-14 | 2016-05-21
5516 | A | 86A - Dismantle | Dismantle E&I junction board access Requested by Bob Brueker (CVX), approved by Mike Brown (Downer GS) | 2487 | Martin Riegert | 2016-03-13 | scaffolding | Med Duty | DISMANTLE | Complete | 2016-03-13 | 2016-03-13
5517 | A | 120A - Dismantle | Dismantle Jetty Access Humpy Requested by Bob Brueker (CVX), approved by Mike Brown (Downer GS) | 2488 | Martin Riegert | 2016-03-13 | scaffolding | Med Duty | DISMANTLE | Complete | 2016-03-13 | 2016-03-13
5518 | TBAA | Train 2 TBAA | Erect scaffold ramp for ERT primary evacuation | 2489 | Brett Taane | 2016-03-12 | Mechanical | Med Duty | ERECT | Complete | 2016-03-14 | 2016-03-15
5519 | SADA | SADA | Emergernt Works for Chevron | 2490 | Mark Orr | 2016-03-13 | Chevron | Med Duty | ERECT | Complete | 2016-03-14 | 2016-03-14
5519 | SADA | SADA | Emergent works for chevron | 2490 | mark orr | 2016-03-13 | Chevron | Med Duty | ERECT | Complete | 2016-03-14 | 2016-03-14
5520 | AAAA | AGRU 1 - AAAA - Ground Floor | Dismantle and remove from GROUND LEVEL - D0952 | 2491 | Mark Orr | 2016-03-13 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-15 | 2016-03-21
5521 | AAAA | AGRU 1 - AAAA - Ground Floor | Dismantle and remove from GROUND LEVEL - D0953 | 2492 | Mark Orr | 2016-03-13 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-15 | 2016-03-26
5522 | AAAA | AGRU 1 - AAAA - Ground Floor | Dismantle and remove from GROUND LEVEL - D0968 | 2493 | Mark Orr | 2016-03-13 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-15 | 2016-03-22
5523 | AAAA | AGRU 1 - AAAA - Ground Floor | Dismantle and remove from GROUND LEVEL - D0969 | 2494 | Mark Orr | 2016-03-13 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-15 | 2016-03-21
5524 | AAAA | AGRU 1 - AAAA - Ground Floor | Dismantle and remove from GROUND LEVEL - D0996 | 2495 | Mark Orr | 2016-03-13 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-15 | 2016-03-27
5525 | AAAA | AGRU 1 - AAAA - Ground Floor | Dismantle and remove from GROUND LEVEL - D0969 | 2496 | Mark Orr | 2016-03-13 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-15 | 2016-05-02
5526 | AAAA | AGRU 1 - AAAA - Ground Floor | Dismantle and remove from GROUND LEVEL - D1062 | 2497 | Mark Orr | 2016-03-13 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-15 | 2016-03-22
5527 | AAAA | AGRU 1 - AAAA - Ground Floor | Dismantle and remove from GROUND LEVEL - D1106 | 2498 | Mark Orr | 2016-03-13 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-15 | 2016-03-19
5528 | AAAA | AGRU 1 - AAAA - Ground Floor | Dismantle and remove from GROUND LEVEL - D1107 | 2499 | Mark Orr | 2016-03-13 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-15 | 2016-03-19
5529 | AAAA | AGRU 1 - AAAA - Ground Floor | Dismantle and remove from GROUND LEVEL - D1180 | 2500 | Mark Orr | 2016-03-13 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-15 | 2016-03-21
5530 | RBAA | RBAA INLET | Erect Overhead Protection for possibility of falling ICE. | 2501 | Mark Orr | 2016-03-13 | Chevron | Med Duty | ERECT | Complete | 2016-04-15 | 2016-04-22
5531 | RBAB | RBAB INLET | Erect Overhead Protection for possibility of falling ICE. | 2502 | Mark Orr | 2016-03-13 | Chevron | Med Duty | ERECT | Complete | 2016-04-15 | 2016-03-15
5532 | GAA1 | GAA1 | Requires scaffold handrails & extension to close of the low speed coupling. | 2503 | Michael Outram | 2016-03-13 | Mechanical | Med Duty | ERECT | Complete | 2016-03-15 | 2016-03-21
5533 | DAAA | DAAA | Dismantle top deck only | 2504 | Mathew Poole | 2016-03-13 | Electrical | Med Duty | MODIFY | Complete | 2016-03-15 | 2016-03-15
5534 | JH23 | JETTY head 23 | Jetty head 23 HM-1750 Access needed for painting works on ambient lines keep all tubes/boards 250mm from pipe. As shown to mick. | 2505 | Felise Emelio | 2016-03-13 | Hertel | Med Duty | ERECT | Complete | 2016-03-15 | 2016-04-24
5535 | TAHA | Train 1 TAHA | Install saffold in TAHA train 1 module in EFG compressor finfans 1K-1451-K5A/B/C for blades pitch adjustment | 2507 | Cristian Niculescu | 2016-03-14 | KJV | Med Duty | ERECT | Complete | 2016-03-14 | 2016-03-16
5536 | TAHA | Train 1 TAHA | Install saffold in TAHA train 1 module in EFG compressor finfans 1K-1450-K5A/B/C for blades pitch adjustment | 2506 | Cristian Niculescu | 2016-03-14 | KJV | Med Duty | ERECT | Complete | 2016-03-14 | 2016-03-16
5537 | GAA1 | GAA1 2nd Level | Scaffold to cover underneath of second level in order to protect lower level from | 2508 | Patrick Thomas | 2016-03-14 | Mechanical | Med Duty | ERECT | Complete | 2016-03-18 | 2016-05-07
5538 | JACA | JACA | JACA HM-1731 Need to access pipe to allow for P2 works keep all boards/tubes 250mm clearance from pipe works. Deck height 1.5m below pipe. | 2510 | Felise Emelio | 2016-03-13 | Hertel | Med Duty | ERECT | Complete | 2016-03-15 | 2016-03-14
5539 | MOF | SCBL- SCBZ i824• | SCBL- SCBZ i824• Take over of mas scaffolds need new numbers. | 2511 | Felise Emelio | 2016-03-15 | Hertel | Med Duty | TAKEOVER | Complete | 2016-03-16 | 2016-03-19
5540 | MOF | SCBK-SCBY i822• | SCBK-SCBY i822• Take over of mas scaffolds need new numbers. | 2512 | Felise Emelio | 2016-03-15 | Hertel | Med Duty | TAKEOVER | Complete | 2016-03-16 | 2016-03-19
5541 | MOF | SCBY-SCCF i821• | SCBY-SCCF i821• Take over of mas scaffolds need new numbers. | 2513 | Felise Emelio | 2016-03-15 | Hertel | Med Duty | TAKEOVER | Complete | 2016-03-16 | 2016-03-19
5541 | MOF | Jetty - interfaces SCBG-SCCZ & SCBY-SCBX | Modification required to existing scaffolds on export lines, additional platform required to allow access to topside of piping, to be approx. 1.5m height. SCBY-SCCF - #5541 (Scaff Tag No.) SCCZ-SCBG - #5013 (Scaff Tag No.) Oceaneering Technician available to show scaffold crew exact location of job and size of scaffolds required. | 4204 | Howard McWaters | 2016-05-09 | Oceaneering NDT | Med Duty | MODIFY | Not Started | 2016-05-16
5542 | MOF | SCAE-SCCF i610• | SCAE-SCCF i610•Take over of mas scaffolds need new numbers. | 2514 | Felise Emelio | 2016-03-15 | Hertel | Med Duty | TAKEOVER | Complete | 2016-03-16 | 2016-03-19
5543 | MOF | SCAE-SCAF i596• | SCAE-SCAF i596• Take over of mas scaffolds need new numbers. | 2515 | Felise Emelio | 2016-03-15 | Hertel | Med Duty | TAKEOVER | Complete | 2016-03-16 | 2016-03-19
5544 | MOF | SCAB-SCCC i5023• | SCAB-SCCC i5023• Take over of mas scaffolds need new numbers. | 2516 | Felise Emelio | 2016-03-15 | Hertel | Med Duty | TAKEOVER | Complete | 2016-03-16 | 2016-04-13
5545 | MOF | SCAA-SCCC i2258• | SCAA-SCCC i2258• Take over of mas scaffolds need new numbers. | 2517 | Felise Emelio | 2016-03-15 | Hertel | Med Duty | TAKEOVER | Complete | 2016-03-16 | 2016-03-19
5546 | MOF | SATT-SCAA i2907• | SATT-SCAA i2907• DISMANTLE 5546. | 2518 | Felise Emelio | 2016-03-15 | Hertel | Med Duty | DISMANTLE | Complete | 2016-03-16 | 2016-03-19
5546 | MOF | SATT-SCAA i2907• | SATT-SCAA i2907• Take over of mas scaffolds need new numbers. | 2518 | Felise Emelio | 2016-03-15 | Hertel | Med Duty | TAKEOVER | Complete | 2016-03-16 | 2016-03-25
5547 | MOF | SATT-SATS i938• | SATT-SATS i938• Take over of mas scaffolds need new numbers. | 2519 | Felise Emelio | 2016-03-15 | Hertel | Med Duty | TAKEOVER | Complete | 2016-03-16 | 2016-03-19
5548 | MOF | SATS-SATR i5020• | SATS-SATR i5020• Take over of mas scaffolds need new numbers. | 2520 | Felise Emelio | 2016-03-15 | Hertel | Med Duty | TAKEOVER | Complete | 2016-03-16 | 2016-03-19
5549 | MOF | SATM-SATN i271 | SATM-SATN i271 Take over of mas scaffolds need new numbers. | 2521 | Felise Emelio | 2016-03-15 | Hertel | Med Duty | TAKEOVER | Complete | 2016-03-16 | 2016-03-19
5550 | Agru 1 | AGRU 1 - AAAA - Level 1 | Dismantle and remove from FIRST LEVEL DO467 | 2522 | Mark Orr | 2016-03-15 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-15 | 2016-03-24
5551 | Agru 1 | AGRU 1 - AAAA - Level 1 | Dismantle and remove from FIRST LEVEL DO506 | 2523 | Mark Orr | 2016-03-15 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-15 | 2016-03-23
5552 | Agru 1 | AGRU 1 - AAAA - Level 1 | Dismantle and remove from FIRST LEVEL DO726 | 2524 | Mark Orr | 2016-03-15 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-15 | 2016-03-25
5553 | Agru 1 | AGRU 1 - AAAA - Level 1 | Dismantle and remove from FIRST LEVEL DO769 | 2525 | Mark Orr | 2016-03-15 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-15 | 2016-03-24
5554 | AAAA | AGRU 1 - AAAA - Level 1 | Dismantle and remove from FIRST LEVEL DO782 | 2526 | Mark Orr | 2016-03-15 | Chevron | Med Duty | DISMANTLE | Not Started | 2016-04-15
5555 | Agru 1 | AGRU 1 - AAAA - Level 1 | Dismantle and remove from FIRST LEVEL DO786 | 2527 | Mark Orr | 2016-03-15 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-15 | 2016-03-22
5557 | Agru 1 | AGRU 1 - AAAA - Level 1 | Dismantle and remove from FIRST LEVEL DO1091 | 2529 | Mark Orr | 2016-03-15 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-15 | 2016-03-23
5558 | JACA | JACA | JACA HM-1752 need x6 mobile scaffolds to allow for chartek works on sheer keys. Deck height 1.2m x 700m x 1.8m as shown to Kevin Hegarty | 2530 | Felise Emelio | 2016-03-15 | Hertel | Med Duty | ERECT | Complete | 2016-03-20 | 2016-03-20
5559 | JACA | JACA | JACA HM-1752 need x6 mobile scaffolds to allow for chartek works on sheer keys. Deck height 1.2m x 700m x 1.8m as shown to Kevin Hegarty | 2531 | Felise Emelio | 2016-03-15 | Hertel | Med Duty | ERECT | Complete | 2016-03-20 | 2016-03-29
5560 | JACA | JACA | JACA HM-1752 need x6 mobile scaffolds to allow for chartek works on sheer keys. Deck height 1.2m x 700m x 1.8m as shown to Kevin Hegarty | 2532 | Felise Emelio | 2016-03-15 | Hertel | Med Duty | ERECT | Complete | 2016-03-20 | 2016-03-20
5561 | JACA | JACA | JACA HM-1752 need x6 mobile scaffolds to allow for chartek works on sheer keys. Deck height 1.2m x 700m x 1.8m as shown to Kevin Hegarty | 2533 | Felise Emelio | 2016-03-15 | Hertel | Med Duty | ERECT | Complete | 2016-03-20 | 2016-03-20
5562 | JACA | JACA | JACA HM-1752 need x6 mobile scaffolds to allow for chartek works on sheer keys. Deck height 1.2m x 700m x 1.8m as shown to Kevin Hegarty | 2534 | Felise Emelio | 2016-03-15 | Hertel | Med Duty | ERECT | Complete | 2016-03-20 | 2016-03-21
5563 | JACA | JACA | JACA HM-1752 need x6 mobile scaffolds to allow for chartek works on sheer keys. Deck height 1.2m x 700m x 1.8m as shown to Kevin Hegarty | 2535 | Felise Emelio | 2016-03-15 | Hertel | Med Duty | ERECT | Complete | 2016-03-20 | 2016-03-21
5564 | GAGA | GAGA | GAGA HM-1753 need x2 mobile scaffolds to allow for chartek works on sheer keys. Deck height 1.2m x 700m x 1.8m as shown to Kevin Hegarty | 2536 | Felise Emelio | 2016-03-15 | Hertel | Med Duty | ERECT | Complete | 2016-03-20 | 2016-03-25
5565 | GAGA | GAGA | GAGA HM-1753 need x2 mobile scaffolds to allow for chartek works on sheer keys. Deck height 1.2m x 700m x 1.8m as shown to Kevin Hegarty | 2537 | Felise Emelio | 2016-03-15 | Hertel | Med Duty | ERECT | Complete | 2016-03-20 | 2016-03-25
5566 | DAAA | DAAA | Build 1.5 x 1.5 x 3.6 lifting frame to remove 350KG Valve (024-TCV-0020B) | 2539 | Lennie Haira | 2016-03-15 | CSU | Med Duty | ERECT | Complete | 2016-03-16 | 2016-03-17
5567 | DAAA | DAAA - CKJV affold A2099 | Modification CKJV scaffold (A2099) 1.5 x 1.5 x 3.6 lifting frame to remove 200KG Valve (024-TCV-0020A) | 2540 | Lennie Haira | 2016-03-15 | CSU | Med Duty | MODIFY | Complete | 2016-03-16 | 2016-03-17
5567 | DAAA | DAAA - CKJV affold A2099 | TAKEOVER - CKJV Scaffold A2099 | 2540 | Lennie Haira | 2016-03-15 | CSU | Med Duty | TAKEOVER | Complete | 2016-03-16 | 2016-03-17
5567 | DAAA | DAAA - CKJV affold A2099 | Dismantle CKJV scaffold (A2099) 1.5 x 1.5 x 3.6 lifting frame to remove 200KG Valve (024-TCV-0020A) | 2540 | Lennie Haira | 2016-03-15 | CSU | Med Duty | DISMANTLE | Complete | 2016-03-16 | 2016-05-22
5568 | RBAE | RBAE | H1958-RBAE HM-1759 need to add extra standards to meet site specs before retagging scaffold for chartek works. As shown to kevin hegarty. | 2542 | Felise Emelio | 2016-03-15 | Hertel | Med Duty | MODIFY | Complete | 2016-03-20 | 2016-03-20
5568 | RBAE | RBAE - Scaff tag: H1958 | TAKEOVER H1958 | 2542 | Felise Emelio | 2016-03-15 | Hertel | Med Duty | TAKEOVER | Complete | 2016-03-20 | 2016-03-20
5569 | SAYC | SAY C | Erect a new scaffold in area 3 to allow E&I to install new cablew from FieldJ-Boxes to field intruments. | 2541 | Andrew Georgiou | 2016-03-15 | E&I | Med Duty | ERECT | Complete | 2016-03-16 | 2016-05-04
5570 | SADA | SADA - Scaff tag: CKJV 12463 | TAKEOVER 12463 CKJV | 2543 | Lennie Haira | 2016-03-15 | CSU | Med Duty | TAKEOVER | Complete | 2016-03-17 | 2016-04-14
5570 | SADA | SADA | 124363 - Modification to existing scaffold to allow removal of tank F50 - 02.Then to reinstate the same access to tank F50 - 02 | 2543 | Lennie Haira | 2016-03-15 | CSU | Med Duty | MODIFY | Cancelled | 2016-03-17
5570 | SADA | SADA | Dismantle Scaffold in SADA Bog Compressor tag no: | 3633 | Bob Brevker | 2016-04-26 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-30 | 2016-05-03
5572 | RBAQ | RBAQ | RBAQ HM-1762 level 3 north end need to erect access to flanges for paint/blast works. Keep all tubes/ply 225mm from pipe works | 2547 | Felise Emelio | 2016-03-16 | Hertel | Med Duty | ERECT | Complete | 2016-03-22 | 2016-03-18
5573 | EAAC | EAAC | EAAC HM-1764 need scaffold access to allow for insulation works on flanges Keep all tubes/ply 225mm clearance from pipe works. | 2548 | Felise Emelio | 2016-03-15 | Hertel | Med Duty | ERECT | Complete | 2016-03-29 | 2016-03-31
5573 | EAAD | EAAD | EAAD HM-1990 tag 5573 Scaffold no longer needed insulation works complete. HM-255 | 3406 | Felise Emelio | 2016-04-20 | Hertel | Med Duty | DISMANTLE | Complete | 2016-04-27 | 2016-05-18
5574 | EAAB | EAAB | EAAB HM-1765 need scaffold access to allow for insulation works on flanges Keep all tubes/ply 225mm clearance from pipe works. | 2549 | Felise Emelio | 2016-03-15 | Hertel | Med Duty | ERECT | Complete | 2016-03-29 | 2016-03-31
5574 | EAA1 | EAA1 | EAA1 HM-1991 tag 5574 Scaffold no longer needed insulation works complete. HM-255 | 3405 | Felise Emelio | 2016-04-20 | Hertel | Med Duty | DISMANTLE | Complete | 2016-04-27 | 2016-05-18
5575 | GAHL | GAHL | Takeover G170 | 2550 | Felise Emelio | 2016-03-15 | Hertel | Med Duty | TAKEOVER | Complete | 2016-03-21 | 2016-03-18
5576 | GAHL | GAHL | Takeover G149 | 2551 | Felise Emelio | 2016-03-15 | Hertel | Med Duty | TAKEOVER | Complete | 2016-03-21 | 2016-03-18
5577 | GAHL | GAHL | Takeover G980 | 2552 | Felise Emelio | 2016-03-15 | Hertel | Med Duty | TAKEOVER | Complete | 2016-03-17 | 2016-03-17
5578 | GAHL | GAHL | Takeover G1321 | 2553 | Felise Emelio | 2016-03-15 | Hertel | Med Duty | TAKEOVER | Complete | 2016-03-21 | 2016-03-18
5579 | ABAA | ABAA | build scaffold (same as agru1) for sample station steel work install this will include barrier on first floor for gridmesh removal. | 2554 | David Goodes | 2016-03-16 | Mechanical | Med Duty | ERECT | Complete | 2016-03-21 | 2016-03-22
5580 | RBAH | RBAH | New Scaffold on eastern end of RBAH rack | 2555 | Shane Shillabeer | 2016-03-16 | Mechanical | Med Duty | ERECT | Complete | 2016-03-21 | 2016-03-28
5581 | RBAH | RBAH | Modify scaffold deck | 2556 | Shane Shillabeer | 2016-03-16 | Mechanical | Med Duty | MODIFY | Complete | 2016-03-21 | 2016-03-27
5581 | RBAH | RBAH | TAKEOVER H1455 CBI Scaffold | 2556 | Shane Shillabeer | 2016-03-16 | Mechanical | Med Duty | TAKEOVER | Complete | 2016-03-21 | 2016-03-27
5582 | GAAF | GAAF | Erect 1 Temp handrail for grid mesh removal | 2557 | Shane Shillabeer | 2016-03-16 | Mechanical | Med Duty | ERECT | Complete | 2016-03-21 | 2016-03-19
5583 | GAAF | GAAF | Erect 1 Temp handrail for grid mesh removal | 2558 | Shane Shillabeer | 2016-03-16 | Mechanical | Med Duty | ERECT | Complete | 2016-03-21 | 2016-03-19
5584 | GABE | GABE | Erect 3x3 mobile scaffold | 2559 | Shane Shillabeer | 2016-03-16 | Mechanical | Med Duty | ERECT | Complete | 2016-03-21 | 2016-03-24
5585 | GABE | GABE | Erect 3x3 mobile scaffold | 2560 | Shane Shillabeer | 2016-03-16 | Mechanical | Med Duty | ERECT | Complete | 2016-03-21 | 2016-03-24
5586 | GADA | GADA 1080 Vessel 739 | Stablizer level extend exsisting scaffold 739 GADA for 2'butt weld | 2561 | Paul Velonias | 2016-03-17 | Mechanical | Med Duty | MODIFY | Complete | 2016-03-20 | 2016-03-22
5587 | GADA | GADA 1080 Vessel 957 | Modify scaffold 957 GADA to suit 2' murcury lines | 2562 | Paul Velonias | 2016-03-17 | Mechanical | Med Duty | MODIFY | Complete | 2016-03-20 | 2016-03-21
5588 | AAAA | AGRU 1 - AAAA - Level 3 | Dismantle and remove from 3rd LEVEL D0014 | 2563 | Mark orr | 2016-03-17 | Chevron | Med Duty | DISMANTLE | Not Started | 2016-04-15
5589 | AAAA | AGRU 1 - AAAA - Level 3 | Dismantle and remove from 3rd LEVEL D0219 | 2564 | Mark orr | 2016-03-17 | Chevron | Med Duty | DISMANTLE | Not Started | 2016-04-15
5590 | AAAA | AGRU 1 - AAAA - Level 3 | Dismantle and remove from 3rd LEVEL D0268 | 2565 | Mark orr | 2016-03-17 | Chevron | Med Duty | DISMANTLE | Not Started | 2016-04-15
5591 | AAAA | AGRU 1 - AAAA - Level 3 | Dismantle and remove from 3rd LEVEL D0285 | 2566 | Mark orr | 2016-03-17 | Chevron | Med Duty | DISMANTLE | Not Started | 2016-04-15
5592 | AAAA | AGRU 1 - AAAA - Level 3 | Dismantle and remove from 3rd LEVEL D0318 | 2567 | Mark orr | 2016-03-17 | Chevron | Med Duty | DISMANTLE | Not Started | 2016-04-15
5593 | AAAA | AGRU 1 - AAAA - Level 3 | Dismantle and remove from 3rd LEVEL D0402 | 2568 | Mark orr | 2016-03-17 | Chevron | Med Duty | DISMANTLE | Not Started | 2016-04-15
5594 | AAAA | AGRU 1 - AAAA - Level 3 | Dismantle and remove from 3rd LEVEL D0698 | 2569 | Mark orr | 2016-03-17 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-15 | 2016-03-25
5595 | AAAA | AGRU 1 - AAAA - Level 3 | Dismantle and remove from 3rd LEVEL D0714 | 2570 | Mark orr | 2016-03-17 | Chevron | Med Duty | DISMANTLE | Not Started | 2016-04-15
5596 | AAAA | AGRU 1 - AAAA - Level 3 | Dismantle and remove from 3rd LEVEL D0722 | 2571 | Mark orr | 2016-03-17 | Chevron | Med Duty | DISMANTLE | Not Started | 2016-04-15
5597 | AAAA | AGRU 1 - AAAA - Level 3 | Dismantle and remove from 3rd LEVEL D0764 | 2572 | Mark orr | 2016-03-17 | Chevron | Med Duty | DISMANTLE | Not Started | 2016-04-15
5598 | AAAA | AGRU 1 - AAAA - Level 3 | Dismantle and remove from 3rd LEVEL D0807 | 2573 | Mark orr | 2016-03-17 | Chevron | Med Duty | DISMANTLE | Not Started | 2016-04-15
5599 | AAAA | AGRU 1 - AAAA - Level 3 | Dismantle and remove from 3rd LEVEL D0845 | 2574 | Mark orr | 2016-03-17 | Chevron | Med Duty | DISMANTLE | Not Started | 2016-04-15
5600 | AAAA | AGRU 1 - AAAA - Level 3 | Dismantle and remove from 3rd LEVEL D1637 | 2575 | Mark orr | 2016-03-17 | Chevron | Med Duty | DISMANTLE | Not Started | 2016-04-15
5601 | GAA1 | GAA1 | Temp support for HVAC | 2581 | Shane Shillabeer | 2016-03-17 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-18 | 2016-03-18
5602 | RBAF | RBAF | New Build required at RBAF | 2582 | Shane Shillabeer | 2016-03-17 | Mechanical | Med Duty | ERECT | Cancelled | 2016-03-18
5603 | GAA1 | GAA1 - Takeover H1005 | Takover H1005 | 2583-1 | Michael Outram | 2016-03-17 | Mechanical | Med Duty | TAKEOVER | Complete | 2016-03-19 | 2016-03-20
5603 | GAA1 | GAA1 - Takeover H1005 | Modify existing scaffold support H1005 | 2583-2 | Michael Outram | 2016-03-17 | Mechanical | Med Duty | MODIFY | Complete | 2016-03-19 | 2016-05-23
5604 | GAA1 | GAA1 inlet | New builld hot work enclosue frame | 2584 | Michael Outram | 2016-03-17 | Mechanical | Med Duty | ERECT | Complete | 2016-03-19 | 2016-03-25
5605 | DAAF | DAAF - Tag 210 | Extend deck to allow access to re-instate cable tray | 2585 | Mathew Poole | 2016-03-17 | Electrical | Med Duty | MODIFY | Complete | 2016-03-20 | 2016-03-20
5606 | DAAF | DAAF - Tag 1066 | Extention of deck to allow removal of junction box frame DAAF module as shown on site to Jared | 2586 | Mathew Poole | 2016-03-17 | Electrical | Med Duty | MODIFY | Complete | 2016-03-20 | 2016-03-19
5607 | SATB | SATB | Takeover i1874 | 2576 | Felise Emelio | 2016-03-17 | Hertel | Med Duty | ERECT | Complete | 2016-03-18 | 2016-03-27
5607 | SATB | SATB | Takeover i1874 COMPLETED - Requires work to open up scaffold | 2576 | Felise Emelio | 2016-03-17 | Hertel | Med Duty | ERECT | Complete | 2016-03-18 | 2016-04-24
5608 | SATB | SATB | Takeover 2495 | 2577 | Felise Emelio | 2016-03-17 | Hertel | Med Duty | ERECT | Complete | 2016-03-18 | 2016-03-26
5609 | GAHL | GAHL North End | Dismantle caffolds to access chemical cleaning pump valves os operations can comminsion | 2578 | Mike Hemming | 2016-03-17 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-18 | 2016-03-20
5609 | GAHL | GAHL North End | Dismantle caffolds to access chemical cleaning pump valves os operations can comminsion | 2578 | Mike Hemming | 2016-03-17 | Chevron | Med Duty | TAKEOVER | Complete | 2016-03-18 | 2016-03-20
5610 | GAHL | GAHL North End | Dismantle caffolds to access chemical cleaning pump valves os operations can comminsion | 2579 | Mike Hemming | 2016-03-17 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-18 | 2016-03-20
5610 | GAHL | GAHL North End | Dismantle caffolds to access chemical cleaning pump valves os operations can comminsion | 2579 | Mike Hemming | 2016-03-17 | Chevron | Med Duty | TAKEOVER | Complete | 2016-03-18 | 2016-03-20
5611 | GAHL | GAHL North End | Dismantle caffolds to access chemical cleaning pump valves os operations can comminsion | 2580 | Mike Hemming | 2016-03-17 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-18 | 2016-03-20
5611 | GAHL | GAHL North End | Dismantle caffolds to access chemical cleaning pump valves os operations can comminsion | 2580 | Mike Hemming | 2016-03-17 | Chevron | Med Duty | TAKEOVER | Complete | 2016-03-18 | 2016-03-20
5612 | RBAF | RBAF | Build Scaffold need to build in order for us to install a support bracket 010-UZV-3014 | 2587 | Shane Shillabeer | 2016-03-18 | Mechanical | Med Duty | ERECT | Cancelled | 2016-03-21
5613 | RBAF | RBAF | Build Scaffold need to build in order for us to install a support bracket 010-UZV-3015 | 2588 | Shane Shillabeer | 2016-03-18 | Mechanical | Med Duty | ERECT | Cancelled | 2016-03-21
5614 | train 2 | SCM1 | Build scaffold access to feed hopper for catalyst loading train 2, 2C-120A,B,C and 2C-1301 | 2593 | Adam Keown | 2016-03-18 | Mechanical | Med Duty | Erect | Not Started | 2016-03-22
5615 | TBAA | TBAA Train 2 | Scaffold request for mods to existing scaffold in2V-1201 TBAA area 15 to provide access for inspections | 2595 | Andrew Ledingham | 2016-03-18 | Mechanical | Med Duty | MODIFY | Cancelled | 2016-03-22
5616 | TBAA | TBAA Train 2 | Build scaffold access to feed hopper for catalyst loading train 2, 2C-120A,B,C and 2C-1301 | 2589 | Brett Taane | 2016-03-18 | Mechanical | Med Duty | ERECT | Complete | 2016-03-21 | 2016-03-23
5617 | TBAA | TBAA Train 2 | Build scaffold access to feed hopper for catalyst loading train 2, 2C-120A,B,C and 2C-1301 | 2590 | Brett Taane | 2016-03-18 | Mechanical | Med Duty | ERECT | Complete | 2016-03-21 | 2016-03-25
5618 | TBAA | TBAA Train 2 | Build scaffold access to feed hopper for catalyst loading train 2, 2C-120A,B,C and 2C-1301 | 2591 | Brett Taane | 2016-03-18 | Mechanical | Med Duty | ERECT | Complete | 2016-03-21 | 2016-03-27
5619 | TBAA | TBAA Train 2 | Build scaffold access to feed hopper for catalyst loading train 2, 2C-120A,B,C and 2C-1301 | 2592 | Brett Taane | 2016-03-18 | Mechanical | Med Duty | ERECT | Complete | 2016-03-21 | 2016-03-30
5620 | GADA | GADA | Require ground level saffold built to suit welding to install a lighting bracket to light up stair access on the north side of GADA. | 2596 | Mathew Poole | 2016-03-19 | Electrical | Med Duty | ERECT | Complete | 2016-03-22 | 2016-03-25
5621 | RBAP | RBAP | TAKEOVER | 2594 | Dario Archer | 2016-03-18 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-22 | 2016-03-19
5621 | RBAP | RBAP | Remove a kick board and crossbar from the emergency exit point top level SE corner. This needs to be done to close out the PL item below so is urgent. | 2594 | Dario Archer | 2016-03-18 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-22 | 2016-03-19
5621 | RBAP | RBAP | TAKEOVER | 2594 | Dario Archer | 2016-03-18 | Chevron | Med Duty | TAKEOVER | Complete | 2016-03-22 | 2016-03-19
5622 | MOF | SATR | HM-1801 Scaffold take over. I938 | 2597 | Felise Emelio | 2016-03-19 | Hertel | Med Duty | TAKEOVER | Cancelled | 2016-03-20
5623 | MOF | SATT | HM-1802 Scaffold take over. I2097 | 2598 | Felise Emelio | 2016-03-19 | Hertel | Med Duty | TAKEOVER | Cancelled | 2016-03-20
5624 | MOF | SCAA | HM-1803 Scaffold take over.i2258 | 2599 | Felise Emelio | 2016-03-19 | Hertel | Med Duty | TAKEOVER | Cancelled | 2016-03-20
5625 | MOF | SCAB | HM-1804 Scaffold take over. I5023 | 2600 | Felise Emelio | 2016-03-19 | Hertel | Med Duty | TAKEOVER | Cancelled | 2016-03-20
5626 | MOF | SCAC | HM-1805 Scaffold take over.i2192 | 2601 | Felise Emelio | 2016-03-19 | Hertel | Med Duty | TAKEOVER | Complete | 2016-03-20 | 2016-03-20
5627 | MOF | SCCF | HM-1806 Scaffold take over.i610 | 2602 | Felise Emelio | 2016-03-19 | Hertel | Med Duty | TAKEOVER | Complete | 2016-03-20 | 2016-03-20
5628 | MOF | SCAE | HM-1806 Scaffold take over.i596 | 2603 | Felise Emelio | 2016-03-19 | Hertel | Med Duty | TAKEOVER | Cancelled | 2016-03-20
5629 | MOF | SCAF | HM-1808 Scaffold take over. I450 | 2604 | Felise Emelio | 2016-03-19 | Hertel | Med Duty | TAKEOVER | Complete | 2016-03-20 | 2016-03-20
5630 | MOF | SATG | HM-1795 Scaffold take over. I927 | 2605 | Felise Emelio | 2016-03-19 | Hertel | Med Duty | TAKEOVER | Complete | 2016-03-20 | 2016-03-20
5631 | MOF | SATL | HM-1798 Scaffold take over. I1011 | 2607 | Felise Emelio | 2016-03-19 | Hertel | Med Duty | TAKEOVER | Complete | 2016-03-20 | 2016-03-20
5632 | MOF | SATN | HM-1799 Scaffold take over. i291 | 2608 | Felise Emelio | 2016-03-19 | Hertel | Med Duty | TAKEOVER | Complete | 2016-03-20 | 2016-03-20
5633 | MOF | SATR | HM-1800 Scaffold take over. I5020 | 2609 | Felise Emelio | 2016-03-19 | Hertel | Med Duty | TAKEOVER | Cancelled | 2016-03-20
5634 | MOF | SATJ | HM-1797 Scaffold take over.i5018 | 2606 | Felise Emelio | 2016-03-19 | Hertel | Med Duty | TAKEOVER | Cancelled | 2016-03-20
5635 | JACA | JACA | JACA north HM-1751 Need access to allow for chartek works keep deck 1200 below beam. | 2610 | Felise Emelio | 2016-03-19 | Hertel | Med Duty | ERECT | Complete | 2016-03-22 | 2016-03-25
5636 | GAH1 | Meg tank 0941 | Meg Tank 0941 HM-1757 need scaffold to allow for cladding works. A min of 225mm clearance is needed around pipe. | 2611 | Felise Emelio | 2016-03-19 | Hertel | Med Duty | ERECT | Complete | 2016-03-20 | 2016-03-29
5636 | JACA | JACA | JACA HM-1994 tag 5636 north of module Scaffold can be dismantled chartek works complete. HM-256 | 3404 | Felise Emelio | 2016-04-20 | Hertel | Med Duty | DISMANTLE | Complete | 2016-04-20 | 2016-05-18
5637 | GAH1 | Meg Pump DN350Line | Erect scaffold platform from welding DN350 pipe. Must be high enough for total encaptulating | 2612 | Chris Black | 2016-03-19 | Mechanical | Med Duty | ERECT | Complete | 2016-03-23 | 2016-03-22
5638 | SAH1 | SAH1 Condensate tank skid | Erect Humpy framework to cover instrumentaion unit for condensate calibration. | 2613 | Wayne McCarthy | 2016-03-19 | Mechanical | Med Duty | Erect | Not Started | 2016-03-20
5639 | MEG | Meg Pump DN350Line | Erect scaffold platform from welding DN350 pipe. Must be high enough for total encaptulating | 2614 | Chris Black | 2016-03-19 | Mechanical | Med Duty | ERECT | Complete | 2016-03-23 | 2016-03-22
5640 | GAGA | GAGA West side- Takeover G1143 | Takeover G1143 | 2615 | Dario Archer | 2016-03-20 | Chevron | Med Duty | TAKEOVER | complete | 2016-03-22 | 2016-03-22
5641 | AAAB | AAAB Central west side | Takeover CBI Scaffold - No tag attached Central west ground level | 2616 | Martin Riegert | 2016-03-21 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-22 | 2016-03-22
5642 | Agru 3 | Agru 3 Ground Level | Build scaffold loft for SMP workshop and rigging equipment. Build identical to what is already in place for AGRU 2. In exactly the same plot position in AGRU 3. Once AGRU 3 loft is completed, SMP/Rigging equipment will mobilise to new loft to allow for AGRU 2 loft dismantle. | 2617 | David Goodes | 2016-03-21 | Mechanical | Med Duty | ERECT | Complete | 2016-03-22 | 2016-03-27
5643 | MOF | MOF A7 | HM-1827 MOF stair access A7 need to reinstate access. | 2618 | Felise Emelio | 2016-03-21 | Hertel | Med Duty | TAKEOVER | Complete | 2016-03-23 | 2016-04-24
5644 | RBAB | RBAB stair access | G1041 - Takeover scaffold | 2619 | Dario Archer | 2016-03-22 | Chevron | Med Duty | TAKEOVER | Complete | 2016-03-22 | 2016-03-23
5645 | inlet | JABG | H0267 - Takeover Scaffold | 2620 | Dario Archer | 2016-03-22 | Chevron | Med Duty | TAKEOVER | Complete | 2016-03-22 | 2016-03-23
5646 | SATU | SATU Pig launcher | Takeover Scaffold to allow to hang tag - No scaff tag attached | 2621 | Jason Princen | 2016-03-22 | Mechanical | Med Duty | TAKEOVER | Cancelled | 2016-03-25
5647 | CBAA | Agru 3 CBAA | Require exisiting handrails extended up to allow us to use a platform ladder on the walkway | 2622 | Jason Princen | 2016-03-23 | Mechanical | Med Duty | ERECT | Complete | 2016-03-23 | 2016-03-27
5647 | CBAA | AGRU 2 CO² Compressors Level 1 CBAA | Dismantle ALL Downer scaffolds around and ontop of the CO 2 Compressors as requested by Chevron for CKJV to remove 2 x motors. Other scaffolds that are allocated for dismantle in the group are listed below: | 4423 | Mike Hemming | 2016-05-20 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-25 | 2016-05-20
5647 | CBAA | AGRU 2 CO² Compressors Level 1 CBAA | Erect ontop of the CO 2 Compressors | 4423 | Mike Hemming | 2016-05-20 | Chevron | Med Duty | ERECT | Complete | 2016-05-25 | 2016-05-20
5647 | CBAA | AGRU 2 CO² Compressors Level 1 CBAA | Modify and extend HR | 4423 | Mike Hemming | 2016-05-20 | Chevron | Med Duty | MODIFY | Complete | 2016-05-25 | 2016-05-20
5648 | CCAA | Agru 3 CCAA | Require exisiting handrails extended up to allow us to use a platform ladder on the walkway | 2623 | Jason Princen | 2016-03-22 | Mechanical | Med Duty | ERECT | Complete | 2016-03-23 | 2016-03-25
5649 | SAP | SAGB | Pipestands X 7 | 2630-1 | Mark orr | 2016-03-23 | Chevron | Med Duty | ERECT | Complete | 2016-03-23 | 2016-03-23
5649 | SAGB | SAGB | Erect pipe stands | 2630-2 | Mick Elliot | 2016-04-15 | Mechanical | Med Duty | ERECT | Complete | 2016-04-17 | 2016-04-17
5651 | MOF | SCAL 1029 | SCAJ HM-1839 need to dismantle top lift to access bottom pipe works for cladding. 1029 tag | 2632 | Felise Emelio | 2016-03-22 | Hertel | Med Duty | MODIFY | Complete | 2015-03-29 | 2016-03-25
5651 | AAAA | south level 3 - AAAA | AAAA HM-1816 south level 3 hook up need access to allow for PPE insulation works, deck height marked in red. Need 225mm clearance around all of pipe works. | 2625 | Felise Emelio | 2016-03-22 | Hertel | Med Duty | ERECT | Complete | 2015-03-29 | 2016-04-17
5652 | MOF | SCAL - Tag 1025 | SCAL HM-1838 need to dismantle top lift to access bottom pipe works for cladding. 1025 | 2633 | Felise Emelio | 2016-03-22 | Hertel | Med Duty | MODIFY | Complete | 2015-03-29 | 2016-03-25
5652 | AAAA | south level 3 - AAAA | ACAA HM-1819 south level 3 hook up need access to allow for PPE insulation works, deck height 600mm from bottom of pipe marked in red and extend 1m east pass elbow. Need 225mm clearance around all of pipe works. | 2626 | Felise Emelio | 2016-03-22 | Hertel | Med Duty | ERECT | Complete | 2015-03-29 | 2016-04-17
5652 | AAAA | south level 3 - AAAA | Dismantle 5652 | 2626 | Felise Emelio | 2016-03-22 | Hertel | Med Duty | DISMANTLE | Complete | 2015-03-29 | 2016-04-20
5654 | AAAA | south level 3 - AAAA | AAAA HM-1817 south level 3 hook up need access to allow for PPE insulation works, deck height 600mm from bottom of pipe marked in red and extend 1m east pass elbow. Need 225mm clearance around all of pipe works. | 2628 | Felise Emelio | 2016-03-22 | Hertel | Med Duty | ERECT | Complete | 2015-03-29 | 2016-04-17
5654 | AAAA | south level 3 - AAAA | Dismantle 5654 | 2628 | Felise Emelio | 2016-03-22 | Hertel | Med Duty | DISMANTLE | Complete | 2015-03-29 | 2016-04-20
5658 | UACA | UACA Area 14 | Dismantle under top level south end - 1073 Downer | 2649 | Mark Orr | 2016-03-22 | Chevron | Med Duty | DISMANTLE | Complete | 2015-03-29 | 2016-03-16
5659 | UACA | UACA Area 14 | Dismantle under fin fans - lvl 3 / A 1733 mas | 2650 | Mark Orr | 2016-03-22 | Chevron | Med Duty | DISMANTLE | Complete | 2015-03-29 | 2016-03-24
5659 | UACA | UACA Area 14 top level (Under) sth end | Dismantle under top level south end A 2148 mas | 2648 | Mark Orr | 2016-03-22 | Chevron | Med Duty | DISMANTLE | Complete | 2015-03-29 | 2016-05-19
5660 | UACA | UACA Area 14 | Dismantle Level 2 - A 2253 mas | 2647 | Mark Orr | 2016-03-22 | Chevron | Med Duty | DISMANTLE | Complete | 2015-03-29 | 2016-04-06
5660 | UACA | UACA Area 14 | Take over Level 2 - A 2253 mas | 2647 | Mark Orr | 2016-03-22 | Chevron | Med Duty | TAKEOVER | Complete | 2015-03-29 | 2016-04-06
5661 | UACA | UACA Area 14 | Dismantle 1084 Downer | 2646 | Mark Orr | 2016-03-22 | Chevron | Med Duty | DISMANTLE | Complete | 2015-03-29 | 2016-03-16
5662 | UACA | UACA Area 14 | Dismantle 1183 Downer | 2645 | Mark Orr | 2016-03-22 | Chevron | Med Duty | DISMANTLE | Complete | 2015-03-29 | 2016-04-05
5663 | UACA | UACA Area 14 | Erect - 1151 Downers | 2644 | Mark Orr | 2016-03-22 | Chevron | Med Duty | ERECT | Complete | 2015-03-29 | 2015-03-29
5663 | UACA | UACA Area 14 | Dismantle 1151 Downers | 2644 | Mark Orr | 2016-03-22 | Chevron | Med Duty | DISMANTLE | Complete | 2015-03-29 | 2016-05-15
5664 | UACA | UACA Area 14 | Dismantle level 1 - A 1442 mas | 2643 | Mark Orr | 2016-03-22 | Chevron | Med Duty | DISMANTLE | Complete | 2015-03-29 | 2015-03-29
5664 | UACA | UACA Area 14 | Dismantle level 1 - A 1442 mas | 2643 | Mark Orr | 2016-03-22 | Chevron | Med Duty | DISMANTLE | Complete | 2015-03-29 | 2016-05-15
5665 | UACA | UACA Area 14 | Dismantle 417 downers | 2642 | Mark Orr | 2016-03-22 | Chevron | Med Duty | DISMANTLE | Complete | 2015-03-29 | 2016-03-31
5667 | UACA | UACA Area 14 | Dismantle scaffold RV UACA - A1644 mas | 2641 | Mark Orr | 2016-03-22 | Chevron | Med Duty | DISMANTLE | Complete | 2015-03-29 | 2016-03-22
5667 | UACA | UACA Area 14 | Dismantle scaffold top of UACA - A1412 mas | 2640 | Mark Orr | 2016-03-22 | Chevron | Med Duty | DISMANTLE | Complete | 2015-03-29 | 2016-03-23
5668 | UACA | UACA Area 14 | scaffold A1644 | 2639 | Mark Orr | 2016-03-22 | Chevron | Med Duty | TAKEOVER | Complete | 2015-03-29 | 2016-03-23
5668 | UACA | UACA Area 14 | Dismantle scaffold A1644 | 2639 | Mark Orr | 2016-03-22 | Chevron | Med Duty | DISMANTLE | Complete | 2015-03-29 | 2016-03-28
5669 | ABAA | ABAA west side Level 1 | ABAA HM-1828 west level 1. Need access to complete cladding works keep deck height 1.2m below pipe and 225mm clearance from around pipe works.swrefsxadadedewe | 2631 | Felise Emelio | 2016-03-22 | Hertel | Med Duty | ERECT | Cancelled | 2015-03-29
5670 | ABAA | ABAA west side Level 1 | ABAA HM-1828 west level 1. Need access to complete cladding works keep deck height 1.2m below pipe and 225mm clearance from around pipe works.swrefsxadadedewe | 2634 | Felise Emelio | 2016-03-22 | Hertel | Med Duty | ERECT | Complete | 2015-03-29 | 2016-03-31
5670 | ABAA | ABAA west side Level 1 | DISMANTLE - ABAA HM-1828 west level 1. Need access to complete cladding works keep deck height 1.2m below pipe and 225mm clearance from around pipe works.swrefsxadadedewe | 3649 | Mark orr | 2016-04-28 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-28 | 2016-04-29
5671 | ABAA | ABAA west side Level 1 | ABAA HM-1829 west level 1. Need access to pump 3 to complete cladding works keep deck height 1.2m below pipe and 225mm clearance from around pipe works. | 2635 | Felise Emelio | 2016-03-22 | Hertel | Med Duty | ERECT | Cancelled | 2015-03-29
5673 | ABAA | ABAA west side Level 1 | ABAA HM-1830 west level 1. Need access to pump 2 to complete cladding works keep deck height 1.2m below pipe and 225mm clearance from around pipe works. | 2637 | Felise Emelio | 2016-03-22 | Hertel | Med Duty | ERECT | Complete | 2015-03-29 | 2016-03-30
5673 | ABAA | ABAA west side Level 1 | DISMANTLE - ABAA HM-1830 west level 1. Need access to pump 2 to complete cladding works keep deck height 1.2m below pipe and 225mm clearance from around pipe works. | 3650 | Mark orr | 2016-04-28 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-28 | 2016-04-29
5674 | ABAA | ABAA west side Level 1 | ABAA HM-1830 west level 1. Need access to complete cladding works keep deck height 1.2m below pipe and225mm clearance from around pipe works. | 2638 | Felise Emelio | 2016-03-22 | Hertel | Med Duty | ERECT | Complete | 2015-03-29 | 2015-03-29
5675 | ABAA | ABAA | Scaffold to provide access to instrument stands - see attached | 2653 | Paul Slocombe | 2016-03-23 | Mechanical | Med Duty | MODIFY | Complete | 2016-03-29 | 2016-03-31
5676 | GAGA | GAGA | Build scaffold to access valve 010UZV-2811 on top of GAGA module for removal of insuation and will req incaptulation | 2656 | Adam Keown | 2016-03-23 | Mechanical | Med Duty | ERECT | Complete | 2016-03-31 | 2016-04-13
5676 | GAGA | GAGA west ground need | Modify scaffold to allow for the removal of the actualator on valve 010/UZV-2401 | 3369 | Charlie Bryce | 2016-04-17 | Mechanical | Med Duty | MODIFY | complete | 2016-04-17 | 2016-04-17
5677 | GAGA | GAGA | Build scaffold to access valve 010UZV-2401 on top of GAGA module for removal of insuation and will req incaptulation | 2657 | Adam Keown | 2016-03-23 | Mechanical | Med Duty | ERECT | Complete | 2016-03-31 | 2016-04-11
5677 | GAGA | Top Level GAGA | Dismantle scaffold top level GAGA tag 5677 | 3259 | Charlie Bryce | 2016-04-15 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-04-17 | 2016-05-18
5677 | GAGA | GAGA top level | Dismantle scaffold top level GAGA tag ??? Top section | 3495 | Thomas Murphy | 2016-04-23 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-04-23 | 2016-05-07
5678 | RBAQ | RBAQ | RBAQ north central ground floor HM-1815 need to modify scaffold to allow for cladding works. tubes on north and south of scaffold need to be pushed back 150mm min clearance. Tag attached was a intrim. As shown to kayne. | 2659 | Felise Emelio | 2016-03-20 | Hertel | Med Duty | MODIFY | Complete | 2016-03-21 | 2016-03-28
5679 | RBAC-RBAE | RBAC-RBAE | HM-1836 Scaffold Dismantle . H 1535 | 2658 | Felise Emelio | 2016-03-20 | Hertel | Med Duty | DISMANTLE | Complete | 2016-03-21 | 2016-03-21
5679 | RBAC-RBAE | RBAC-RBAE | HM-1809 Scaffold take over. H 1535 | 2658 | Felise Emelio | 2016-03-20 | Hertel | Med Duty | TAKEOVER | Complete | 2016-03-21 | 2016-03-21
5679 | RBAE | RBAE-RBAC | Scaffold can be dismantled. HM-1952 | 3201 | Felise Emelio | 2016-04-13 | Hertel | Med Duty | DISMANTLE | Complete | 2016-04-18 | 2016-05-18
5680 | RBAC-RBAE | RBAC-RBAE | HM-1810 Scaffold take over. Level 1 tag H 155 | 2660 | Felise Emelio | 2016-03-20 | Hertel | Med Duty | TAKEOVER | Complete | 2016-03-21 | 2016-03-21
5681 | RBAC-RBAE | RBAC-RBAE | HM-1811 Scaffold take over. Level 2 tag H 156 | 2661-1 | Felise Emelio | 2016-03-20 | Hertel | Med Duty | TAKEOVER | Complete | 2016-03-21 | 2016-03-27
5681 | RBAC-RBAE | RBAC-RBAE | HM-1811 Scaffold take over. Level 2 tag H 156 | 2661-2 | Felise Emelio | 2016-03-20 | Hertel | Med Duty | DISMANTLE | Complete | 2016-03-21 | 2016-03-27
5682 | RBAC-RBAE | RBAC-RBAE | HM-1812 Scaffold take over. Level 2 step up. H 729 | 2662 | Felise Emelio | 2016-03-20 | Hertel | Med Duty | TAKEOVER | Complete | 2016-03-21 | 2016-03-21
5683 | RBAC-RBAE | RBAC-RBAE | HM-1813 Scaffold take over. Top level. H 357 | 2663 | Felise Emelio | 2016-03-20 | Hertel | Med Duty | TAKEOVER | Complete | 2016-03-21 | 2016-03-20
5684 | MOF | MOF A7 | MOF stair access E HM-1840 need to reinstate access. | 2664 | Felise Emelio | 2016-03-20 | Hertel | Med Duty | MODIFY | complete | 2016-03-21 | 2016-03-21
5684 | MOF | MOF A7 | MOF stair access E HM-1840 Take over 794 | 2664 | Felise Emelio | 2016-03-20 | Hertel | Med Duty | TAKEOVER | complete | 2016-03-21 | 2016-03-21
5685 | ACAD | ACAD | ACAD HM-1834 need stair access to access first platform of regens. | 2665 | Felise Emelio | 2016-03-20 | Hertel | Med Duty | ERECT | Complete | 2016-03-21 | 2016-04-08
5686 | GAA1 | GAA1 | GAA1 HM-1837 need access to x4 FW for painting works. | 2666 | Felise Emelio | 2016-03-23 | Hertel | Med Duty | ERECT | Complete | 2016-04-01 | 2016-04-11
5687 | DAAA | DAAA | (Scaffold built to remove control valve) 1.5 x 1.5 x 3.6 lifting frame to dismantle | 2676 | Todd Lyons | 2016-03-23 | Mechanical | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-04-10
5688 | DAAA | DAAA | Modification to existing scaffold to remove valve (024-TCV-0020A) to dismant | 2677 | Todd Lyons | 2016-03-24 | Mechanical | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-04-10
5689 | RBAD | RBAD | Take over H 1706 / mod handrails | 2667 | Mark orr | 2016-03-23 | Chevron | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-03-28
5689 | Inlet | Inlet area pig reciever | Dismantle 5689 | 3391 | LENNIE HAIRA | 2016-04-19 | CSU | Med Duty | DISMANTLE | Complete | 2016-04-20 | 2016-04-25
5690 | TADA | TADA | Over head protection TADA | 2668 | Mark orr | 2016-03-23 | Chevron | Med Duty | ERECT | Complete | 2016-03-25 | 2016-03-24
5691 | TADA | TADA | Over head protection TADA | 2669 | Mark orr | 2016-03-23 | Chevron | Med Duty | ERECT | Complete | 2016-03-25 | 2016-03-24
5692 | TADA | TADA | Over head protection TADA | 2670 | Mark orr | 2016-03-23 | Chevron | Med Duty | ERECT | Complete | 2016-03-25 | 2016-03-24
5693 | TADA | TADA | Over head protection TADA | 2671 | Mark orr | 2016-03-23 | Chevron | Med Duty | ERECT | Complete | 2016-03-25 | 2016-03-24
5694 | CBAA | CBAA | CO2 Frames CBAA | 2672 | Mark orr | 2016-03-23 | Chevron | Med Duty | ERECT | Complete | 2016-03-25 | 2016-03-24
5694 | CBAA | AGRU 2 CO² Compressors Level 1 CBAA | Dismantle ALL Downer scaffolds around and ontop of the CO 2 Compressors as requested by Chevron for CKJV to remove 2 x motors. Other scaffolds that are allocated for dismantle in the group are listed below: | 4428 | Mike Hemming | 2016-05-20 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-25 | 2016-05-21
5695 | CBAA | CBAA | CO2 Frames CBAA | 2673 | Mark orr | 2016-03-23 | Chevron | Med Duty | ERECT | Complete | 2016-03-25 | 2016-03-24
5695 | CBAA | CBAA | DismantleCO2 Frames CBAA | 2673 | Mark orr | 2016-03-23 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-25 | 2016-05-21
5696 | CBAA | CBAA | CO2 Frames CBAA | 2674 | Mark orr | 2016-03-23 | Chevron | Med Duty | ERECT | Complete | 2016-03-25 | 2016-03-24
5696 | CBAA | CBAA | Dismantle ALL Downer scaffolds around and ontop of the CO 2 Compressors as requested by Chevron for CKJV to remove 2 x motors. Other scaffolds that are allocated for dismantle in the group are listed below: Tag H981 | 4468 | Mike Hemming | 2016-05-21 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-25 | 2016-05-21
5697 | CBAA | CBAA | CO2 Frames CBAA | 2675 | Mark orr | 2016-03-23 | Chevron | Med Duty | ERECT | Complete | 2016-03-25 | 2016-03-24
5697 | CBAA | AGRU 2 CO² Compressors Level 1 CBAA | H981 | 4427 | Mike Hemming | 2016-05-20 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-25 | 2016-05-18
5697 | CBAA | AGRU 2 CO² Compressors Level 1 CBAA | Dismantle ALL Downer scaffolds around and ontop of the CO 2 Compressors as requested by Chevron for CKJV to remove 2 x motors. Other scaffolds that are allocated for dismantle in the group are listed below: Tag H981 | 4427 | Mike Hemming | 2016-05-20 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-25 | 2016-05-18
5699 | SAP | Condensate Tanks | Stairs to be builts @ Condensate tanks | 2679 | Daniel Edwards | 2016-03-24 | Mechanical | Med Duty | ERECT | Complete | 2016-03-31 | 2016-04-02
5701 | SAP | Stores Condensate Takns | Scaffold at the stores @ Condensate tanks | 2681 | Daniel Edwards | 2016-03-24 | Mechanical | Med Duty | ERECT | Complete | 2016-03-31 | 2016-04-04
5703 | DABA | DABA | Dismantles for chevron - craig coombe request | 2689 | Craig Coombe | 2016-03-25 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-27 | 2016-03-30
5704 | DABA | DABA | Dismantles for chevron - craig coombe request | 2690 | Craig Coombe | 2016-03-25 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-27 | 2016-03-28
5705 | DABA | DABA | Dismantles for chevron - craig coombe request | 2691 | Craig Coombe | 2016-03-25 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-27 | 2016-03-28
5706 | DABA | DABA | Dismantles for chevron - craig coombe request | 2692 | Craig Coombe | 2016-03-25 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-27 | 2016-03-31
5707 | DABA | DABA | Dismantles for chevron - craig coombe request | 2693 | Craig Coombe | 2016-03-25 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-27 | 2016-03-28
5708 | DABA | DABA | Dismantles for chevron - craig coombe request | 2694 | Craig Coombe | 2016-03-25 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-27 | 2016-03-30
5709 | DABA | DABA | Dismantles for chevron - craig coombe request | 2695 | Craig Coombe | 2016-03-25 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-27 | 2016-03-31
5710 | DABA | DABA | Dismantles for chevron - craig coombe request | 2696 | Craig Coombe | 2016-03-25 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-27 | 2016-04-01
5711 | DABA | DABA | Dismantles for chevron - craig coombe request | 2697 | Craig Coombe | 2016-03-25 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-27 | 2016-03-30
5712 | DABA | DABA | Dismantles for chevron - craig coombe request | 2698 | Craig Coombe | 2016-03-25 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-27 | 2016-03-30
5713 | DABA | DABA | Dismantles for chevron - craig coombe request | 2699 | Craig Coombe | 2016-03-25 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-27 | 2016-03-28
5714 | GAAF | GAAF | H 1683 takeover | 2700 | Mark orr | 2016-03-25 | Chevron | Med Duty | TAKEOVER | Complete | 2016-03-27 | 2016-03-26
5715 | GAAC | GAAC | H 1692 Takeover | 2701 | Mark orr | 2016-03-25 | Chevron | Med Duty | TAKEOVER | Complete | 2016-03-27 | 2016-03-26
5716 | GAAC | GAAC | H 1686 takeover | 2702 | Mark orr | 2016-03-25 | Chevron | Med Duty | TAKEOVER | Complete | 2016-03-27 | 2016-03-26
5717 | GAAC | GAAC | H1684 takeover | 2703 | Mark orr | 2016-03-25 | Chevron | Med Duty | TAKEOVER | Complete | 2016-03-27 | 2016-03-26
5718 | Agru 1 | Agru 1 | Dismantle and remove from SECOND LEVEL DO109 | 2704 | Mark orr | 2016-03-25 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-27 | 2016-03-31
5719 | Agru 1 | Agru 1 | Dismantle and remove from SECOND LEVEL DO179 | 2705 | Mark orr | 2016-03-25 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-27 | 2016-04-01
5720 | AAAA | Agru 1 | Dismantle and remove from SECOND LEVEL DO295 | 2706 | Mark orr | 2016-03-25 | Chevron | Med Duty | DISMANTLE | Not Started | 2016-03-27
5721 | Agru 1 | Agru 1 | Dismantle and remove from SECOND LEVEL DO2343 | 2707 | Mark orr | 2016-03-25 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-27 | 2016-03-27
5722 | AAAA | Agru 1 | Dismantle and remove from SECOND LEVEL DO481 | 2708 | Mark orr | 2016-03-25 | Chevron | Med Duty | DISMANTLE | Not Started | 2016-03-27
5723 | Agru 1 | Agru 1 | Dismantle and remove from SECOND LEVEL DO484 | 2709 | Mark orr | 2016-03-25 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-27 | 2016-04-12
5724 | Agru 1 | Agru 1 | Dismantle and remove from SECOND LEVEL DO793 | 2710 | Mark orr | 2016-03-25 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-27 | 2016-03-26
5725 | Agru 1 | Agru 1 | Dismantle and remove from SECOND LEVEL DO794 | 2711 | Mark orr | 2016-03-25 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-27 | 2016-03-27
5726 | AAAA | Agru 1 | Dismantle and remove from SECOND LEVEL DO982 | 2712 | Mark orr | 2016-03-25 | Chevron | Med Duty | DISMANTLE | Not Started | 2016-03-27
5727 | AAAA | Agru 1 | Dismantle and remove from SECOND LEVEL No tag | 2713 | Mark orr | 2016-03-25 | Chevron | Med Duty | DISMANTLE | Not Started | 2016-03-27
5728 | Agru 1 | Agru 1 | Dismantle and remove from SECOND LEVEL No tag | 2714 | Mark orr | 2016-03-25 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-27 | 2016-04-21
5729 | GAA1 | GAA1 | GAA1 HM-1846 Handrail needed for grid mesh removal permit | 2683 | Troy Brand | 2016-03-24 | Hertel | Med Duty | ERECT | Complete | 2016-03-31 | 2016-03-31
5730 | INLET | GACA | GACA HM-1852 Sth Wst Tag 15453 Standard needs to be lifted 300mm of Shear Key & Transom is a safety hazard that could be taken out. | 2715 | Troy Brand | 2016-03-26 | Hertel | Med Duty | MODIFY | Complete | 2016-03-30 | 2016-03-30
5731 | DAAA | Level 4 East Loading Bay | Level 4 RV Platform Takeover. Tag no: 334 | 2716 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5732 | DAAA | 2nd Level North | Lagging and electrical access. Tag no: 894 | 2717 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5732 | DAAA | Domgas | Dismantle | 4375 | Trevor Pike | 2016-05-16 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-16
5733 | DAAA | DOMGAS | Top access to hydrocarbon vessel. Level 1 South. Tag no: 1191 | 2718 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5734 | DAAA | DOMGAS | Top access to hydrocarbon vessel. Level 1 South. Tag no: 1190 | 2719 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5735 |  | Shipping steel ground level S/E CNR | AA30 Tag no: 210 | 2720 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5736 | DOMGAS | DOMGAS | Drink Station DOMGAS Humpy. Tag no: 796 | 2721 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5737 |  | Ground N/E CNR | Pipe line welds and painting. AA28. Tag no: 677 | 2722 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5738 | DOMGAS | Domgas stores | Ground S/E CNR Humpy. Tag no: 706 | 2723 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-29
5739 | RBAH | H1468 RBAH top level | Modify 5482 (cancelled 5739 as it was alrady DNC under 5482) | 2724 | Mark Farley | 2016-03-26 | Mechanical | Med Duty | MODIFY | Cancelled | 2016-03-12
5740 | SAGA | SAGA | Erect platform & Hrails around NTH Vapour Skid to improve access | 2725 | Mark orr | 2016-03-25 | Chevron | Med Duty | ERECT | Complete | 2016-03-27 | 2016-04-13
5741 | TAFA | Train 1 Turbine TAFA | Erect Deck to access Inspection ports on Northern side of Turbine to allow boroscope to be installed. | 2766 | Steve walker | 2016-03-26 | Chevron | Med Duty | ERECT | Complete | 2016-03-29 | 2016-03-26
5742 | UACA | UACA Module Ground Level | Laggers access mobile UACA Module Ground Level. Tag no: 705 | 2726 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5743 | GADA | GADA | GADA Module Ground Level Mobile. Tag no: 1049 | 2727 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5744 | GAEA | GAEA | GAEA Module Level 3 off a CKJV scaffold. Tag no: 1083 | 2728 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5745 | GAEA | GAEA | GAEA Module Level 3 North for stabiliser column. Tag no: 740 | 2729 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5746 | GAEA | GAEA | GAEA Module Level 2 North to weld vertical brackets. Tag no: 1032 | 2730 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5747 | GAEA | GAEA | GAEA Module Level 2 North edge welding access. Tag no: 736 | 2731 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5748 | UACA | UACA | UACA Module Level 2 2C-1080 stabiliser column North. Tag no: 737 | 2732 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5749 | UACA | UACA | UACA Lvl 1 South/East quickstage stair access. Tag no: 417 | 2733 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5750 | GAEA | GAEA | GAEA Module Level 1 North/West corner. Tag no: 569 | 2734 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5751 | GAEA | GAEA | GAEA Module Level 1 North/West corner. Tag no: 558 | 2735 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5752 | GAEA | GAEA | GAEA Module Level 1 South Stairs. Tag no: 1188 | 2736 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5753 | GAEA | GAEA | GAEA Module Ground Level North. Tag no: 1160 | 2737 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5754 | GAEA | GAEA | GAEA Module Ground Level North. Tag no: 634 | 2738 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5755 | GAEA | GAEA | GAEA Module Ground Level North. Tag no: 1161 | 2739 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5756 | GAEA | GAEA | GAEA Module Ground Level Drinks station humpy. Tag no: 798 | 2740 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5757 | GADA | GADA | GADA Module South/East corner skid ground level. Tag no: 1119 | 2741 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5758 | GADA | GADA | GADA Module Ground Level North/West Corner. Tag no: 361 | 2742 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5759 | GADA | GADA | GADA Module Level 3 North edge over handrail to access lower landing. Tag no: 803 | 2743 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5760 | GADA | GADA | GADA Module Level 2 access North on lower level landing. Tag no: 802 | 2744 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5761 | GADA | GADA | GADA Module Level 3 . Tag no: 1065 | 2745 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5762 | UACA | UACA | UACA Module South Ground Level. Tag no: 1167 | 2746 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5763 | DOMGAS | UACA | Domgas UACA scaffolders humpy and storage racks. Tag no: 560 | 2747 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5764 | UACA | UACA | UACA West side ground for welders to install brackets. Tag no: 557 | 2748 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5765 | UACA | UACA | UACA Module quickstage ladder access Level 1. Tag no: 863 | 2749 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5766 | UACA | UACA | UACA Module Ground Level centre for installation of Chartec products. Tag no: 533 | 2750 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5766 | UACA | UACA | UACA Module Ground Level centre for installation of Chartec products. Tag no: 533 | 3130 | Adam Stark | 2016-04-10 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-17 | 2016-04-11
5767 | UACA | UACA | UACA Module Ground Level for welders, bracket installations. Tag no: 528 | 2751 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5768 | UACA | UACA | UACA Module Ground centre. Tag no: 1187 | 2752 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5768 | UACA | UACA | Module ground centre tag no 1187 | 3131 | Adam Stark | 2016-04-10 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-17 | 2016-04-11
5769 | UACA | UACA | UACA Level 1 South off stairs. Tag no: 1183 | 2753 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5770 | UACA | UACA | UACA Module Level 1 South stairs. Tag no: 685 | 2754 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5770 | UACA | UACA | UACA Module Level 1 South stairs. Tag no: 685 | 3132 | Adam Stark | 2016-04-10 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-17 | 2016-05-17
5771 | UACA | UACA | UACA Module Level 1 off S/E quickstage stair access. Tag no: 1084 | 2755 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5772 | UACA | UACA | UACA Module Level 1 off S/E quickstage stair access. Tag no: 1151 | 2756 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5773 | UACA | UACA | UACA Module Level 1 off quickstage stair access S/E CNR. Tag no: 1073 | 2757 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | DISMANTLE | Complete | 2016-03-26 | 2016-03-26
5773 | UACA | UACA | UACA Module Level 1 off quickstage stair access S/E CNR. Tag no: 1073 | 2757 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5774 | UACA | UACA | UACA Module Level 1 North. Tag no: 441 | 2758 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5774 | UACA | UACA | UACA Module Level 1 North. Tag no: 441 | 3133 | Adam Stark | 2016-04-10 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-17 | 2016-05-17
5775 | UACA | UACA | UACA Module South/West CNR Level 1-5. Tag no: 724 | 2759 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | DISMANTLE | Complete | 2016-03-26 | 2016-03-26
5775 | UACA | UACA | UACA Module South/West CNR Level 1-5. Tag no: 724 | 2759 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5776 | UACA | UACA | UACA Module Level 2 Blasting and Chartec access. Tag no: 1127 | 2760 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5777 | UACA | UACA | UACA Module Level 2 West of stairs. Tag no: 1152 | 2761 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5777 | UACA | UACA | Dismantle Scaffold | 4310 | Trevor Pike | 2016-05-14 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-15 | 2016-05-19
5778 | UACA | UACA | UACA Module Level 2 off staircase S/W. Tag no: 1146 | 2762 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | DISMANTLE | Complete | 2016-03-26 | 2016-03-26
5778 | UACA | UACA | UACA Module Level 2 off staircase S/W. Tag no: 1146 | 2762 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5779 | UACA | UACA | UACA Module 3rd landing off staircase.Tag no: 941 | 2763 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5780 | UACA | UACA | Drinks station and shade humpy Ground Level S/E CNR UACA Module. Tag no: 1189 | 2764 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5781 | UACA | UACA | UACA Module Ground Level to top North/West corner quickstage stair access. Tag no: 421 | 2765 | Mark Orr | 2016-03-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-26 | 2016-03-26
5782 | SAP | Mercury management facility | Require to build a free standing scaffold, demention as 4000 mm long x 1500 wide & 3300 high with working decks @ 2200mm from grade. The front edge of the scaffols needs 1800mm from front edge of the temp wash down container refer to drawing | 2767 | Gavin Hughes | 2016-03-26 | Electrical | Med Duty | ERECT | Complete | 2016-03-29 | 2016-04-10
5782 | SARA | Mercury Management Facility | Strip scaffold # 2767 @ Mercury Management Facility. | 3370 | Gavin Hughes | 2016-04-16 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-04-17 | 2016-04-17
5783 | SAP | Tank 4 Condensate tanks | Dismantle 5783 | 2768 | Daniel Edwards | 2016-03-27 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-29 | 2016-03-28
5783 | SAP | Tank 4 Condensate tanks | Remove hard barricade at access points . Install hard barricades at handrail openings | 2768 | Daniel Edwards | 2016-03-27 | Mechanical | Med Duty | ERECT | Complete | 2016-03-29 | 2016-04-27
5784 | TACA | Train 1 Turbine TACA | Erect Deck to access Inspection ports on Northern LPP Tcrossover on top level .of TACA | 2769 | Steve walker | 2016-03-27 | Chevron | Med Duty | ERECT | Complete | 2016-03-29 | 2016-05-19
5784 | TACA | TACA - Train 1 top level | Dismantle Scaffold | 4302 | Barry Baker | 2016-05-14 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-20 | 2016-05-16
5785 |  | MAJ2 | Dismantle hand rails attached Sth #1088 | 1266 | Mark Orr | 2015-10-30 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-10-28 | 2015-10-28
5785 | RBDM | RBDM are 14 | Dismantle scaffold RBDM | 2770 | Steve walker | 2016-03-27 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-29 | 2016-03-28
5785 | RBDM | RBDM are 14 | Dismantle take over 1088 scaffold RBDM | 2771 | Steve walker | 2016-03-27 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-29 | 2016-04-04
5786 | DAAA | DAAA Module Compressor Access | Erect Step-Up scaffold platform for access to bearing assembly | 2772 | Wayne McCarthy | 2016-03-27 | Mechanical | Med Duty | ERECT | Complete | 2016-03-28 | 2016-03-29
5787 | Agru 2 | Aru 2 RL 33 | Build/modify current scaffold to allow for CW14 encapulation and welding. Please bare in mind any potential clashes with the next spool installation. Please allow as much room as possible around spool with min 600mm clearance under spool | 2684 | David Goodes | 2016-03-24 | Mechanical | Med Duty | ERECT | Cancelled | 2016-03-31
5788 | RBAL-RBAK | RBAL | Build Hard Barricade | 2686 | Chris Black | 2016-03-24 | Mechanical | Med Duty | ERECT | Complete | 2016-03-31 | 2016-03-30
5788 | RBAL-RBAK | RBAL | Takeover | 2686 | Chris Black | 2016-03-24 | Mechanical | Med Duty | TAKEOVER | Complete | 2016-03-31 | 2016-04-19
5789 | Meg | Meg | TPC works 09L00-01-BWI - TP 0025-0001 | 2685 | Chris Black | 2016-03-24 | Mechanical | Med Duty | ERECT | Complete | 2016-03-29 | 2016-03-29
5789 | GAH4 | GAh4 | Dimantle humpy 3 mtrs desk grade | 3264 | Rick Muston | 2016-04-15 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-04-17 | 2016-04-17
5790 | inlet | Injection Pumps | New deck required for pipe installation | 2687 | Shane Shillabeer | 2016-03-24 | Mechanical | Med Duty | ERECT | Complete | 2016-03-31 | 2016-04-20
5790 | inlet | Injection Pumps | Dismantle | 2687 | Shane Shillabeer | 2016-03-24 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-31 | 2016-04-21
5790 | inlet | Injection Pumps | Added to 5959 tag number - dismantled this tag number | 2687 | Shane Shillabeer | 2016-03-24 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-31 | 2016-04-24
5791 | inlet | Inlet north laydown yard | Put shelves in contyainer at inlet stores | 2688 | Shane Shillabeer | 2016-03-24 | Mechanical | Med Duty | ERECT | Complete | 2016-03-31 | 2016-03-29
5792 | RBAK | RBAK | TAKEOVER Scaff Tag no: 1101 | 2774 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-03-30
5793 | RBAL | RBAL | TAKEOVER Scaff Tag no: 1098 | 2775 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-03-30
5794 | RBAL | RBAL | TAKEOVER Scaff Tag no: 1137 | 2776 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-04-02
5795 | RBAK | RBAK | TAKEOVER Scaff Tag no: 1097 | 2777 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-03-30
5796 | RBAJ | RBAJ | TAKEOVER Scaff Tag no: 1096 | 2778 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-03-30
5797 | RBAJ | RBAJ | TAKEOVER Scaff Tag no: 1115 | 2779 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-03-29
5798 | JACA | JACA | TAKEOVER Scaff Tag no: 1176 | 2780 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-04-01
5799 | JADA | JADA | TAKEOVER Scaff Tag no: 1108 | 2781 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-04-02
5800 | JADA | JADA | TAKEOVER Scaff Tag no: 1102 | 2782 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-04-02
5801 | GAGA | GAGA | TAKEOVER Scaff Tag no: 1172 | 2783 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-04-01
5802 | RBAH | RBAH | TAKEOVER Scaff Tag no: 1012 | 2784 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-05-07
5803 | RBAH | RBAH South | TAKEOVER Scaff Tag no: 1070 | 2785 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-05-12
5804 | RBAH | RBAH | TAKEOVER Scaff Tag no: 1063 | 2786 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-05-07
5805 | RBAH | RBAH West | TAKEOVER Scaff Tag no: 1012 | 2787 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-05-07
5806 | RBAH | RBAH | TAKEOVER Scaff Tag no: 1068 | 2788 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-04-19
5807 | RBAH | RBAH | TAKEOVER Scaff Tag no: 1064 | 2789 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-05-07
5808 | RBAH | RBAH LVL 1 | Modify TAKEOVER Scaff Tag no: 1069 | 2790 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | MODIFY | Complete | 2016-03-25 | 2016-05-24
5808 | RBAH | RBAH LVL 1 | TAKEOVER Scaff Tag no: 1069 | 2790 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-05-25
5809 | RBAH | RBAH | TAKEOVER Scaff Tag no: 1050 | 2791 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-05-12
5810 | GAA1 | GAA1 | TAKEOVER Scaff Tag no: H1624 | 2792 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-04-04
5811 | RBAH | RBAH LVL 1 | TAKEOVER Scaff Tag no: H1327 | 2793 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-04-04
5812 | GAA1 | GAA1 North | TAKEOVER Scaff Tag no: H1328 | 2794 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-04-04
5813 | GAA1 | GAA1 North | TAKEOVER Scaff Tag no: H1729 | 2795 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-05-18
5813 | GAA1 | GAA1 North | Modify Scaff Tag no: H1729 | 2795 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | MODIFY | Complete | 2016-03-25 | 2016-05-21
5813 | GAA1 | GAA1 North | Dismantle Scaff Tag no: H1729 | 2795 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | DISMANTLE | Complete | 2016-03-25 | 2016-05-23
5814 | RBAQ | RBAQ | TAKEOVER Scaff Tag no: H1746 | 2796 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-04-03
5815 | RBAQ | RBAQ | TAKEOVER Scaff Tag no: H773 | 2797 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-04-03
5816 | RBAQ | RBAQ | TAKEOVER Scaff Tag no: H1770 | 2798 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-04-03
5817 | RBAQ | RBAQ | TAKEOVER Scaff Tag no: H1891 | 2799 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-04-03
5818 | RBAQ | RBAQ | TAKEOVER Scaff Tag no: H1828 | 2800 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-04-03
5819 | RBAQ | RBAQ | TAKEOVER Scaff Tag no: H1832 | 2801 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-04-02
5820 | GAA1 | GAA1 | TAKEOVER Scaff Tag no: H704 | 2802 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-03-30
5821 | GAA1 | GAA1 | TAKEOVER Scaff Tag no: H814 | 2803 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-04-02
5821 | GAA1 | GAA1 inlet | Dismantle to allow access for pipe work | 4374 | Shane Shillabeer | 2016-05-17 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-23 | 2016-05-24
5821 | GAA1 | GAA1 inlet | Provide modifications to allow access for pipe work | 4374 | Shane Shillabeer | 2016-05-17 | Mechanical | Med Duty | MODIFY | Complete | 2016-05-23 | 2016-05-24
5822 | GAA1 | GAA1 | TAKEOVER Scaff Tag no: H1261 | 2804 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-04-03
5823 | GAA1 | GAA1 | TAKEOVER Scaff Tag no: H1469 | 2805 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-05-18
5824 | GAA1 | GAA1 | TAKEOVER Scaff Tag no: H1796 | 2806 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-04-03
5825 | GAA1 | GAA1 | TAKEOVER Scaff Tag no: H1722 | 2807 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-04-03
5826 | GAA1 | GAA1 | TAKEOVER Scaff Tag no: H1721 | 2808 | Joel Gray | 2016-03-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-25 | 2016-04-02
5827 | TACA | TACA | Erect Deck to access strainer filter. To enable change out. | 2809 | Steve walker | 2016-03-28 | Chevron | Med Duty | ERECT | Not Started | 2016-03-28
5828 | INLET | INLET | Deck out 1 of container with shelves. | 2810 | Shane Shillabeer | 2016-03-27 | Mechanical | Med Duty | ERECT | Complete | 2016-03-27 | 2016-04-11
5829 | INLET | INLET | Deck out 1 of container with shelves. | 2811 | Shane Shillabeer | 2016-03-27 | Mechanical | Med Duty | ERECT | Complete | 2016-03-28 | 2016-04-11
5830 | INLET | INLET | Deck out 1 of container with shelves. | 2812 | Shane Shillabeer | 2016-03-27 | Mechanical | Med Duty | ERECT | Complete | 2016-03-28 | 2016-04-11
5831 | GAAC | GAAC | Erect scaffold to remove PSV from Valve in order to rig and remove valve. | 2813 | Sam McGill | 2016-03-29 | Rigging | Med Duty | ERECT | Cancelled | 2016-03-28
5832 | INLET | GAH1 | Build mobile humpy for welding activities within the MEG tank bund OT-0942 | 2814 | Adam Keown | 2016-03-29 | Mechanical | Med Duty | ERECT | Cancelled | 2016-04-02
5833 | MEG | MEG Injection | Install deck to weld piping as per model shot. PUMP B | 2815 | Shane Shillabeer | 2016-03-29 | Mechanical | Med Duty | ERECT | Complete | 2016-03-29 | 2016-04-19
5833 | MEG | MEG Injection | Install deck to weld piping as per model shot. PUMP B | 2815 | Shane Shillabeer | 2016-03-29 | Mechanical | Med Duty | ERECT | Complete | 2016-03-29 | 2016-04-20
5833 | MEG | MEG Injection | Install deck to weld piping as per model shot. PUMP B | 2815 | Shane Shillabeer | 2016-03-29 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-29 | 2016-04-24
5834 | MEG | MEG Injection | Install deck as per piping as per model shot. PUMP C | 2817 | Shane Shillabeer | 2016-03-29 | Mechanical | Med Duty | ERECT | Complete | 2016-03-29 | 2016-04-19
5834 | MEG | MEG Injection | Dismantle Install deck as per piping as per model shot. PUMP C | 2817 | Shane Shillabeer | 2016-03-29 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-29 | 2016-04-21
5835 | MEG | MEG Injection | Install deck as per piping as per model shot. PUMP A | 2818 | Shane Shillabeer | 2016-03-29 | Mechanical | Med Duty | ERECT | Complete | 2016-03-29 | 2016-04-18
5836 | SAP | East side platform between con tank 3 and 4 | Need scaffold deck erected+ to allow access to fix brace, this scaffold is to be located outside the bund wall. 2 x tags under 5836 A & 5836 B | 2816 | Daniel Edwards | 2016-03-29 | Mechanical | Med Duty | ERECT | Complete | 2016-03-30 | 2016-04-05
5837 | SAP | Platform 32, Eastern wall, Tank 4 Condensate Area | Erect scaffold to access column supports under structure on top of bund wall (concrete drilling and grouting). | 2819 | Daniel Edwards | 2016-03-29 | Mechanical | Med Duty | ERECT | Complete | 2016-04-02 | 2016-04-05
5837 | SAH1 | SAH1 | Dismantle Scaffold to allow construction of new scaffold | 3769 | Mathew Poole | 2016-04-30 | Electrical | Med Duty | DISMANTLE | Complete | 2016-04-05 | 2016-05-05
5838 | UACA | UACA Fin Fan Lvl | UACA HM-1884 Est Fi Fan Lvl Access needed to Line# OP-42007.02 For Installation of two flange boxes. | 2820 | Troy Brand | 2016-03-29 | Hertel | Med Duty | MODIFY | Complete | 2016-04-02 | 2016-04-08
5839 | JAC1 West | JAC1 West | JAC1 HM-1883 Erect scaffold to access steelwork above vessel for fireproofing. Note: Grid mesh above will be removed. Scaff tag no: H0267 | 2821 | James Halliday | 2016-03-29 | Hertel | Med Duty | ERECT | Complete | 2016-04-11 | 2016-04-18
5839 | JAC1 | JAC1 - tanks no:OV-0970 and OV-0971 | Extend scaffol 5839 to allow 100 hook up so gridmesh can be removed from the top of both tanks no:OV-0970 and OV-0971 to allow paintin / blasting and chartecing of beams | 3394 | Thomas Murphy | 2016-04-19 | Mechanical | Med Duty | MODIFY | Complete | 2016-04-18 | 2016-04-20
5839 | JAC1 | JAC1 | JAC1 HM-2008 Need to extend scaffold south to capture chartek works on structural beams mark in red. | 3475 | Felise Emelio | 2016-04-22 | Hertel | Med Duty | MODIFY | Complete | 2016-04-25 | 2016-05-22
5840 | UACA | UACA Est | UACA HM-1885 Est Extra handrail needed to added to permanent handrail for Line# OP-42042.02 on Sth & Est for Installation. | 2822 | Troy Brand | 2016-03-29 | Hertel | Med Duty | ERECT | Complete | 2016-04-02 | 2016-04-07
5841 | INLET | RBAL | Provide access to weld pipes as per attached pic. Scaffold to allow for full encapsulation & be fit for use by CBI (Ensure reel on access ladder). | 2823 | Mark Farley | 2016-03-29 | Mechanical | Med Duty | ERECT | Complete | 2016-03-29 | 2016-04-24
5842 | INLET | Inlet, GAGA top level | Please provide access to removal insulation from around top of valve 010HZV-2811. The deck height needs to allow for the disconnection of instument tubing on the north side of the actuatr on the valve. The scaff will need to be built so that it doesn't impeed unbolting flanges or the removal of the valve. Alternately the scaff would need to be stripped to allow the valve removal. | 2824 | Mark Farley | 2016-03-29 | Mechanical | Med Duty | ERECT | Complete | 2016-03-29 | 2016-04-24
5843 | MOF | MOF, SCABL | Dismantle scaffold used to access line of sight camera on the MOF, rack SCBL TAG#12500 | 2825 | George Fomin | 2016-03-29 | Chevron | Med Duty | DISMANTLE | Not Started | ASAP
5844 | MOF | MOF, SCCN | Dismantle scaffold used to access line of sight camera on the MOF, rack SCCN TAG#12768 | 2826 | George Fomin | 2016-03-29 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-29 | 2016-03-29
5845 | MOF | MOF, SCCN | Dismantle scaffold used to access line of sight camera on the MOF, rack SCCN TAG#12845 | 2827 | George Fomin | 2016-03-29 | Chevron | Med Duty | DISMANTLE | Not Started | ASAP
5846 | MOF | MOF, SCBG | Dismantle scaffold used to access line of sight camera on the MOF, rack SCBG TAG#12923 | 2828 | George Fomin | 2016-03-29 | Chevron | Med Duty | DISMANTLE | Not Started | ASAP
5847 | MOF | MOF, SCCW, LOOP 7 | Dismantle scaffold used to access line of sight camera on the MOF, rack SCCW LOOP 7 NO TAG # ON SCAFF | 2829 | George Fomin | 2016-03-29 | Chevron | Med Duty | DISMANTLE | Not Started | ASAP
5848 | INLET | INLET, RBAD, Top Level | Resinstate scaff to allow disconnection of instrument tubing and electrical wiring from valve actuator. Strip scaff to allow removal of valve 010UZV-2009. | 2830 | Mark Farley | 2016-03-29 | Mechanical | Med Duty | ERECT | Complete | 2016-03-29 | 2016-04-05
5848 | RBAD | RBAD | Strip Scaffold 5848 location as per attached | 3193 | Charlie Bryce | 2016-04-13 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-04-13 | 2016-04-16
5849 | ABAA | ABAA, LVL 3 | TAKEOVER Scaff Tag #1193 | 2831 | Joel Gray | 2016-03-29 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-29 | 2016-04-03
5850 | ABAA | ABAA, LVL 4 | TAKEOVER Scaff Tag #1164 | 2832 | Joel Gray | 2016-03-29 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-29 | 2016-04-03
5851 | ABAA | ABAA | TAKEOVER Scaff Tag #1158 | 2833 | Joel Gray | 2016-03-29 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-29 | 2016-04-01
5851 | ABAA | ABAA level 1 | ABAA HM-1953 level one east of tag 5851 Need to erect hop up to purge cap/FW for paintings works note this hole line gets insulated so keep clearance 225mm to prevent clashes. | 3140 | Felise Emelio | 2016-04-11 | Hertel | Med Duty | ERECT | Complete | 2016-04-18 | 2016-04-16
5851 | AAAA | AGRU 2 SOUTH END RL27000 | Downer to take over MAS scaffold on southern end of AGRU 2 RL27000for upcoming Electrical installation work as discussed with Alistair. | 3202 | Paul Slocombe | 2016-04-12 | Electrical | Med Duty | DISMANTLE | Complete | 2016-04-16 | 2016-04-16
5851 | ABAH | level 1 west tag 5851 | ABAH HM-1667 level 1 west tag 5851 need to extend scaffold west to capture remaining insulation works. Keep deck height the same. Note ABAH module marked in red. | 3236 | Felise Emelio | 2016-04-14 | Hertel | Med Duty | MODIFY | cancelled | 2016-04-21
5852 | ABAA | ABAA | TAKEOVER Scaff Tag #278 | 2834 | Joel Gray | 2016-03-29 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-29 | 2016-04-01
5853 | ABAA | ABAA | TAKEOVER Scaff Tag #1165 | 2835 | Joel Gray | 2016-03-29 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-29 | 2016-04-01
5854 | ABAA | ABAA | TAKEOVER Scaff Tag #1058 | 2836 | Joel Gray | 2016-03-29 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-29 | 2016-03-31
5855 | ABAA | ABAA | TAKEOVER Scaff Tag #602 | 2837 | Joel Gray | 2016-03-29 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-29 | 2016-04-01
5856 | ABAA | ABAA, AGRU 2 | TAKEOVER Scaff Tag #1152 | 2838 | Joel Gray | 2016-03-29 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-29 | 2016-03-31
5857 | ABAB | ABAB | TAKEOVER Scaff Tag #1083 | 2839 | Joel Gray | 2016-03-29 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-29 | 2016-03-31
5858 | PR COMP | PR COMP | Erect work benches as discussed with Dave Dundon and Craig. 2 permanent benches on PR concrete floor (North side and West side) 2 mobile scaffolds on PR deck. 1 mobild scaffold to be built on th lift well ground level. | 2840 | Michael Hemmings | 2016-03-29 | CKJV | Med Duty | ERECT | Complete | 2016-03-06 | 2016-04-14
5859 | RBDE | RBDE | Takeover of MAS Scaff Located at RBDE Piperack Tag No A005 | 2841 | John Young | 2016-03-29 | Mechanical | Med Duty | TAKEOVER | Complete | 2016-03-29 | 2016-04-11
5860 | RBAQ | RBAQ | RBAQ HM-1762 Level 3 north end need to erect access to flangs for plaint/blast works. Keep all tubes/ply 225mm from pipe works. | 2842 | Felise Emelio | 2016-03-29 | Hertel | Med Duty | ERECT | complete | 2016-03-22 | 2016-03-22
5861 | Agru 2 | AGRU 2 | Need ssome scaffold pipe supports fone for temp pipe work for chem clean south/west corner Agru 2. Boards in use at the moment CVX Safety have asked for scaffold. | 2843 | Anthony Powell | 2016-03-29 | Mechanical | Med Duty | ERECT | Complete | 2016-03-30 | 2016-03-30
5861 | AGRU 2 | AGRU 2 South West | Need to remove steps and access deck at temp bund south of AGRU 2 Scaff request 2843. Need these stripped out Saturday as truck is coming Sunday to move the tanks and pump. | 4149 | Todd Lyons | 2016-05-05 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-07 | 2015-05-08
5862 | RBAE | RBAE | RBAE HM-1886 H1945 Handover & reinstate for Chartek the underside of steel. Access from Qyuick stage stairs. | 2844 | Troy Brand | 2016-03-29 | Hertel | Med Duty | TAKEOVER | Complete | 2016-04-06 | 2016-04-06
5863 | MOF | MOF, SCBK, SCBY | Dismantle scaffold on the north side of pipe rack SCBK, SCBY hand rails and kick boards only, make sure access can be made via the South Side. Scaff TAG# 5540 | 2845 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Not Started | ASAP
5864 | MOF | MOF, SCBC, SCBZ | Dismantle scaffold on the north side of pipe rack SCBC, SCBZ hand rails and kick boards only, make sure access can be made via the South Side. Scaff TAG# 5539 | 2846 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Not Started | ASAP
5865 | MOF | MOF, SCBX | Dismantle shade humpy on MOF rack SCBX Scaff TAG# 988 | 2847 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-30 | 2016-04-06
5866 | MOF | MOF, SCBJ | Dismantle scaffold on the north side of pipe rack SCBJ hand rails and kick boards only, make sure access can be made via the South Side. Scaff TAG# 990 | 2848 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Not Started | ASAP
5867 | MOF | MOF, SCJB | Dismantle scaffold on the north side of pipe rack SCJB hand rails and kick boards only, make sure access can be made via the South Side. Scaff TAG# 991 | 2849 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-30 | 2016-04-06
5868 | MOF | MOF, SCBG | Dismantle full scaffold on MOF rack SCBG Scaff TAG# I2810 | 2850 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-30 | 2016-04-10
5869 | MOF | MOF, SCBG | Dismantle full scaffold on MOF rack SCBG Scaff TAG# I2923 | 2851 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Not Started | ASAP
5870 | MOF | MOF, SCCZ, SCBG | Dismantle scaffold on the north side of pipe rack SCCZ, SCBG hand rails and kick boards only, make sure access can be made via the South Side. Scaff TAG# 5013 | 2852 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-30 | 2016-04-06
5871 | MOF | MOF, SCBF | Dismantle full scaffold on MOF rack SCBF Scaff TAG# I2925 | 2853 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Not Started | ASAP
5872 | MOF | MOF, SCBF | Dismantle scaffold on the north side of pipe rack SCBF hand rails and kick boards only, make sure access can be made via the South Side. Scaff TAG# 993 | 2854 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-30 | 2016-04-08
5872 | MOF | MOF, SCBF | Takeover scaffold . Scaff TAG# 993 | 2854 | George Fomin | 2016-03-30 | Chevron | Med Duty | TAKEOVER | Complete | 2016-04-08 | 2016-04-08
5873 | MOF | MOF, SCBE | Dismantle full scaffold on MOF rack SCBE Scaff TAG# I2811 | 2855 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-30 | 2016-04-11
5874 | MOF | MOF, SCBD | Dismantle full scaffold on MOF rack SCBD Scaff TAG# I1855 | 2856 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Not Started | ASAP
5875 | MOF | MOF, SCBC, SCCU | Dismantle scaffold on the north side of pipe rack SCBC, SCCU hand rails and kick boards only, make sure access can be made via the South Side. Scaff TAG# 753 | 2857 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Not Started | ASAP
5876 | MOF | MOF, SCBC | Dismantle full scaffold on MOF rack SCBC Scaff TAG# I1995 | 2858 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Not Started | ASAP
5877 | MOF | MOF, SCBC | Dismantle scaffold on the north side of pipe rack SCBC hand rails and kick boards only, make sure access can be made via the South Side. Scaff TAG# 1003 | 2859 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-30 | 2016-03-31
5878 | MOF | MOF, SCBA | Dismantle scaffold on the north side of pipe rack SCBA hand rails and kick boards only, make sure access can be made via the South Side. Scaff TAG# 1004 | 2860 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-30 | 2016-03-31
5879 | MOF | MOF, SCBA | Dismantle scaffold on the north side of pipe rack SCBA hand rails and kick boards only, make sure access can be made via the South Side. Scaff TAG# 757 | 2861 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-30 | 2016-03-31
5880 | MOF | MOF, SCAR | Dismantle scaffold on the north side of pipe rack SCAR hand rails and kick boards only, make sure access can be made via the South Side. Scaff TAG# 1005 | 2862 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-30 | 2016-04-13
5881 | MOF | MOF, SCAQ | Dismantle scaffold on the north side of pipe rack SCAQ hand rails and kick boards only, make sure access can be made via the South Side. Scaff TAG# 1006 | 2863 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-31 | 2016-03-31
5882 | MOF | MOF, SCAQ | Dismantle full scaffold on MOF rack SCAQ Scaff TAG# 0931 | 2864 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Not Started | ASAP
5883 | MOF | MOF, SCAQ | Dismantle scaffold on the north side of pipe rack SCAQ hand rails and kick boards only, make sure access can be made via the South Side. Scaff TAG# 1007 | 2865 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-30 | 2016-03-31
5884 | MOF | MOF, SCCQ | Dismantle scaffold on the north side of pipe rack SCCQ hand rails and kick boards only, make sure access can be made via the South Side. Scaff TAG# 1008 | 2866 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-30 | 2016-03-31
5885 | MOF | MOF, SCAN | Dismantle scaffold on the north side of pipe rack SCAN hand rails and kick boards only, make sure access can be made via the South Side. Scaff TAG# 1020 | 2867 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-30 | 2016-03-31
5886 | MOF | MOF, SCAN | Dismantle scaffold on the north side of pipe rack SCAN hand rails and kick boards only, make sure access can be made via the South Side. Scaff TAG# 1024 | 2868 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-30 | 2016-03-31
5887 | MOF | MOF, SCAL | Dismantle scaffold on the north side of pipe rack SCAL hand rails and kick boards only, make sure access can be made via the South Side. Scaff TAG# 1025 | 2869 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-30 | 2016-04-11
5888 | MOF | MOF, SCCK | Dismantle scaffold on the north side of pipe rack SCCK hand rails and kick boards only, make sure access can be made via the South Side. Scaff TAG# 1027 | 2870 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-30 | 2016-04-01
5889 | MOF | MOF, SCAT | Dismantle scaffold on the north side of pipe rack SCAT hand rails and kick boards only, make sure access can be made via the South Side. Scaff TAG# 1028 | 2871 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-30 | 2016-03-30
5890 | MOF | MOF, SCAH | Dismantle scaffold on the north side of pipe rack SCAH hand rails and kick boards only, make sure access can be made via the South Side. Scaff TAG# 1029 | 2872 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-30 | 2016-03-30
5891 | MOF | MOF, SCAF | Dismantle scaffold on the north side of pipe rack SCAF hand rails and kick boards only, make sure access can be made via the South Side. Scaff TAG# 5628 | 2873 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-30 | 2016-03-31
5892 | MOF | MOF, SCAE, SCAF | Dismantle scaffold on the north side of pipe rack SCAE, SCAF hand rails and kick boards only, make sure access can be made via the South Side. Scaff TAG# 5543 | 2874 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-30 | 2016-04-01
5893 | MOF | MOF, SCAE, SCCF | Dismantle scaffold on the north side of pipe rack SCAE, SCCF hand rails and kick boards only, make sure access can be made via the South Side. Scaff TAG# 5542 | 2875 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-30 | 2016-03-31
5894 | MOF | MOF, SCAC | Dismantle scaffold on the north side of pipe rack SCAC hand rails and kick boards only, make sure access can be made via the South Side. Scaff TAG# 5625 | 2876 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-30 | 2016-03-31
5895 | MOF | MOF, SCAB, SCCC | Dismantle scaffold on the north side of pipe rack SCAB, SCCC hand rails and kick boards only, make sure access can be made via the South Side. Scaff TAG# 5023 | 2877 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-30 | 2016-03-31
5895 | CBAA | AGRU 2 CO² Compressors Level 1 CBAA | Dismantle ALL Downer scaffolds around and ontop of the CO 2 Compressors as requested by Chevron for CKJV to remove 2 x motors. Other scaffolds that are allocated for dismantle in the group are listed below: | 4424 | Mike Hemming | 2016-05-20 | Chevron | Med Duty | DISMANTLE | Not started | 2016-05-25
5896 | MOF | MOF, SCAA, SCCA | Dismantle scaffold on the north side of pipe rack SCAA, SCCA hand rails and kick boards only, make sure access can be made via the South Side. Scaff TAG# 5021 | 2878 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-30 | 2016-04-01
5897 | MOF | MOF, SCAA, SCCC | Dismantle scaffold on the north side of pipe rack SCAA, SCCC hand rails and kick boards only, make sure access can be made via the South Side. Scaff TAG# 5545 | 2879 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-30 | 2016-04-01
5898 | MOF | MOF, SATT, SCAA | Dismantle scaffold on the north side of pipe rack SATT, SCAA hand rails and kick boards only, make sure access can be made via the South Side. Scaff TAG# 5546 | 2880 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-30
5899 | MOF | MOF, SATT, SATS | Dismantle scaffold on the north side of pipe rack SATT, SATS hand rails and kick boards only, make sure access can be made via the South Side. Scaff TAG# 5547 | 2881 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-30 | 2016-04-01
5900 | MOF | MOF, SATR | Dismantle scaffold on the north side of pipe rack SATR hand rails and kick boards only, make sure access can be made via the South Side. Scaff TAG# 5548 | 2882 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-30 | 2016-04-01
5901 | MOF | MOF, SATL | Dismantle scaffold on the north side of pipe rack SATL hand rails and kick boards only, make sure access can be made via the South Side. Scaff TAG# 5631 | 2883 | George Fomin | 2016-03-30 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-30 | 2016-04-01
5902 | INLET | GAGA | Please inspect, reinstate & tag scaffold ready for use. Scaff Tag no: G-1298 | 2773 | Mark Farley | 2016-03-17 | Mechanical | Med Duty | TAKEOVER | complete | 2016-03-29 | 2016-03-29
5903 | INLET | INLET, GAGA | Please provide small deck for access to allow chartec removal and insulation of pipe support steel work allowing for full encapsulation. GAGA, Ground level south west corner. | 2887 | Mark Farley | 2016-03-27 | Mechanical | Med Duty | ERECT | Complete | 2016-03-29 | 2016-04-15
5904 | RBAE | RBAE | Handover/takeover H1868 CBI scaffold. Strip scaffold H1868. | 2888 | Felise Emelio | 2016-03-30 | Hertel | Med Duty | TAKEOVER | Complete | 2016-04-07 | 2016-04-19
5905 | PR COMP | PR COMPRESSOR | Chevron require additional scaffolds on the PR Compressor in preparation for potential cover removal/inspection. Firstly job will be to measure up for 3 workbenches and 3 small mobile scaffolds (to be done on nightshift). | 2884 | Dave Dundon | 2016-03-31 | Scaffolding/Rigging/Crane | Med Duty | ERECT | Complete | 2016-04-06 | 2016-04-06
5906 | PR COMP | PR COMPRESSOR | Dismantle existing scaffold to go ahead with cover removal. | 2885 | Dave Dundon | 2016-03-31 | Scaffolding/Rigging/Crane | Med Duty | DISMANTLE | Complete | 2016-03-31 | 2016-04-14
5907 | PR COMP | PR COMPRESSOR | Erect scaffold around 3 sides for bolt removal. | 2886 | Dave Dundon | 2016-03-31 | Scaffolding/Rigging/Crane | Med Duty | ERECT | Complete | 2016-04-14 | 2016-04-14
5908 | RBAL-RBAK | RBAL | Scaffold job built under requst #2686. Requesting it to be stripped. | 2889 | Chris Black | 2016-03-30 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-04-07 | 2016-04-16
5909 | TRAIN 1 | TACA | Erect scaffold Level 2 of module TACA north end to access valve and remove lagging. | 2890 | Steve Walker | 2016-03-31 | Chevron | Med Duty | ERECT | Complete | 2016-03-31 | 2016-03-31
5910 | TRAIN 1 | TACA | Erect scaffold Level 3 of module TACA north end to access valve and remove lagging. | 2891 | Steve Walker | 2016-03-31 | Chevron | Med Duty | ERECT | Complete | 2016-03-31 | 2016-03-31
5911 | TRAIN 1 | TACA | Erect scaffold Level 4 of module TACA north end to access valve and remove lagging. | 2892 | Steve Walker | 2016-03-31 | Chevron | Med Duty | ERECT | Complete | 2016-03-31 | 2016-03-31
5911 | TACA | TACA - Train 1 top level | Dismantle Scaffold | 4300 | Barry Baker | 2016-05-14 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-20 | 2016-05-16
5911 | TACA | TACA - Train 1 top level | Dismantle Scaffold | 4305 | Barry Baker | 2016-05-14 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-20 | 2016-05-16
5912 | AAAB | AAAB | Dismantle work platform and stair access, redundant scaffold on AGRU 1 CO2 vents. | 2898 | Martin Riegert | 2016-03-31 | scaffolding | Med Duty | DISMANTLE | Complete | 2016-03-31 | 2016-04-01
5913 | ACAA | ACAA | Erect lifting frames for CO2 Compressor Maintenance | 2899 | Martin Riegert | 2016-03-31 | scaffolding | Med Duty | ERECT | Complete | 2016-04-22 | 2016-04-22
5914 | CCAA | CCAA | Erect lifting frames for CO2 Compressor Maintenance. CSU Scope | 2900 | Martin Riegert | 2016-03-31 | scaffolding | Med Duty | ERECT | complete | 2016-04-18 | 2016-04-18
5915 | UACA | UACA Ground Level | Dismantle scaffold as requested by client. Ground Level. Scaff TAG# 528 | 2901 | Jared Ngaheu | 2016-03-31 | scaffolding | Med Duty | DISMANTLE | Complete | 2016-03-31 | 2016-04-05
5916 | UACA | UACA Ground Level | Dismantle scaffold as requested by client. Ground Level. Scaff TAG# 535 | 2902 | Jared Ngaheu | 2016-03-31 | scaffolding | Med Duty | DISMANTLE | Complete | 2016-03-31 | 2016-04-19
5917 | UACA | UACA South West CNR Ground Level | Dismantle scaffold as requested by client. Ground Level. Scaff TAG# 557 | 2903 | Jared Ngaheu | 2016-03-31 | scaffolding | Med Duty | DISMANTLE | Complete | 2016-03-31 | 2016-04-05
5918 | UACA | UACA South West CNR Ground Level | Dismantle scaffold as requested by client. Ground Level. Scaff TAG# 1167 | 2904 | Jared Ngaheu | 2016-03-31 | scaffolding | Med Duty | DISMANTLE | Complete | 2016-03-31 | 2016-04-06
5919 | UACB | West side of module | Dismantle scaffold as requested by client. Ground Level. Scaff TAG# 863 | 2905 | Jared Ngaheu | 2016-03-31 | scaffolding | Med Duty | DISMANTLE | Complete | 2016-03-31 | 2016-04-06
5920 | UACA | UACA South West CNR Level 2 | Dismantle scaffold as requested by client. Ground Level. Scaff TAG# 724 | 2906 | Jared Ngaheu | 2016-03-31 | scaffolding | Med Duty | DISMANTLE | Complete | 2016-03-31 | 2016-04-19
5921 | UACA | UACA South West CNR Level 2 | Dismantle scaffold as requested by client. Ground Level. Scaff TAG# 1127 | 2907 | Jared Ngaheu | 2016-03-31 | scaffolding | Med Duty | DISMANTLE | Complete | 2016-03-31 | 2016-04-19
5922 | UACA | West side Level 1 | Dismantle scaffold as requested by client. Ground Level. Scaff TAG# 5305 | 2908 | Jared Ngaheu | 2016-03-31 | scaffolding | Med Duty | DISMANTLE | Complete | 2016-03-31 | 2016-04-19
5923 | UACA | South end of Module | Dismantle scaffold as requested by client. Ground Level. Scaff TAG# 683 | 2909 | Jared Ngaheu | 2016-03-31 | scaffolding | Med Duty | DISMANTLE | Complete | 2016-03-31 | 2016-04-19
5924 | UACA | West side Level 2 | Dismantle scaffold as requested by client. Ground Level. Scaff TAG# 1152 | 2910 | Jared Ngaheu | 2016-03-31 | scaffolding | Med Duty | DISMANTLE | Complete | 2016-03-31 | 2016-04-19
5925 | UACA | Access off stairway Level 2 | Dismantle scaffold as requested by client. Ground Level. Scaff TAG# 1146 | 2911 | Jared Ngaheu | 2016-03-31 | scaffolding | Med Duty | DISMANTLE | Complete | 2016-03-31 | 2016-04-19
5926 | UACA | 3rd Landing on Stairway | Dismantle scaffold as requested by client. Ground Level. Scaff TAG# 941 | 2912 | Jared Ngaheu | 2016-03-31 | scaffolding | Med Duty | DISMANTLE | Complete | 2016-03-31 | 2016-04-19
5927 | RBAQ | RBAQ | RBAQ HM-1890 Tag 5222 Est Off ground Lvl remove ply and remove 1200mm board to allow for insulation of vertial heat trace section. | 2893 | Troy Brand | 2016-03-31 | Hertel | Med Duty | MODIFY | Complete | 2016-03-31 | 2016-04-19
5928 | RBAQ | RBAQ | Dismantle scaffolds: TAG# H1721, TAG# 5470 | 2894 | James Halliday | 2016-03-31 | Hertel | Med Duty | DISMANTLE | Complete | 2016-04-06 | 2016-05-18
5929 | INLET | INLET, RBAD, 2nd Level | Please provide 15m exclusion zone hard barricading with gate acccess for valve 010UZV-010UZV-2802 removal under a single point isolation. | 2895 | Mark Farley | 2016-03-31 | Mechanical | Med Duty | ERECT | Cancelled | 2016-04-05
5930 | GAGB | GAGB WST | GAGB HM-1893 Wst Access needed for Chartek of patch on structural steel. Note the base of the scaffold will need to provide a frame for encapsulation and should not interfere with the shear keys. | 2896 | Troy Brand | 2016-03-31 | Hertel | Med Duty | ERECT | Complete | 2016-04-05 | 2016-04-11
5931 | GAGB | GAGB WST | GAGB HM-1894 est Access needed for Chartek of patch on structural steel. Note the base of the scaffold will need to provide a frame for encapsulation and should not interfere with the shear keys. | 2897 | Troy Brand | 2016-03-31 | Hertel | Med Duty | ERECT | Complete | 2016-04-06 | 2016-04-11
5932 | TACA | TACA | Erect scaffold either side of spool to remove insulation jacket and accces flange/spade/blind. Southern line. Double up of request | 2915 | Martin Riegert | 2016-04-01 | scaffolding | Med Duty | ERECT | Cancelled | 2016-04-01
5934 | TACA | TACA | Erect scaffold either side of spool to remove insulation jacket and accces flange/spade/blind. Southern line. Northern line. Double up of request | 2915 | Martin Riegert | 2016-04-01 | scaffolding | Med Duty | ERECT | Cancelled | 2006-04-01
5935 | RBAL | RBAL | TAKEOVER Scaff TAG# G1756 | 2916 | Joel Gray | 2016-03-30 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-30 | 2016-04-02
5936 | RBAL | RBAL | TAKEOVER Scaff TAG# G911 | 2917 | Joel Gray | 2016-03-30 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-03-30 | 2016-04-02
5937 | LP9-LP10 | LP9-LP10 | LP9-LP10 HM-1896 Access needed for Blasting, Painting of bearing. As shown to Marty. | 2918 | Troy Brand | 2016-03-31 | Hertel | Med Duty | ERECT | Complete | 2016-04-05 | 2016-04-16
5938 | Agru 1 | AGRU 1 - CAAA | Require a scaffold built to access a hatch for confined space entry. Cost Code: 0054.M01.9999 | 2919 | Jason Princen | 2016-03-31 | Mechanical | Med Duty | ERECT | Complete | 2016-04-09 | 2016-04-09
5939 | Agru 1 | AGRU 1 - CAAA | Require a scaffold built to access a hatch for confined space entry. Cost Code: 0054.M01.9999 | 2920 | Jason Princen | 2016-03-31 | Mechanical | Med Duty | ERECT | Complete | 2016-04-09 | 2016-04-09
5940 | Agru 2 | AGRU 2 - CBAA | Require a scaffold built to access a hatch for confined space entry. Cost Code: 0054.M01.9999 | 2921 | Jason Princen | 2016-03-31 | Mechanical | Med Duty | ERECT | Complete | 2016-04-04 | 2016-04-04
5940 | CBAA | AGRU 2 CO² Compressors Level 1 CBAA | Dismantle ALL Downer scaffolds around and ontop of the CO 2 Compressors as requested by Chevron for CKJV to remove 2 x motors. Other scaffolds that are allocated for dismantle in the group are listed below: | 4425 | Mike Hemming | 2016-05-20 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-25 | 2016-05-20
5941 | CBAA | AGRU 2 - CBAA | Require a scaffold built to access a hatch for confined space entry. Cost Code: 0054.M01.9999 | 2922 | Jason Princen | 2016-03-31 | Mechanical | Med Duty | ERECT | Complete | 2016-05-21 | 2016-05-21
5941 | CBAA | AGRU 2 CO² Compressors Level 1 CBAA | Dismantle ALL Downer scaffolds around and ontop of the CO 2 Compressors as requested by Chevron for CKJV to remove 2 x motors. Other scaffolds that are allocated for dismantle in the group are listed below: | 4426 | Mike Hemming | 2016-05-20 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-25 | 2016-05-20
5942 | AGRU 3 | AGRU 3 - CCAA | Require a scaffold built to access a hatch for confined space entry. Cost Code: 0054.M01.9999 | 2923 | Jason Princen | 2016-03-31 | Mechanical | Med Duty | ERECT | Complete | 2016-04-04 | 2016-04-04
5943 | AGRU 3 | AGRU 3 - CCAA | Require a scaffold built to access a hatch for confined space entry. Cost Code: 0054.M01.9999 | 2924 | Jason Princen | 2016-03-31 | Mechanical | Med Duty | ERECT | Complete | 2016-04-02 | 2016-04-02
5944 | Condensate Tanks | Condensate Tanks | Please erect mobile scaffold/humpy with wheels 2/2. Please include workbench. | 2925 | Daniel Edwards | 2016-03-28 | Mechanical | Med Duty | ERECT | Complete | 2016-03-31 | 2016-04-03
5945 | TANK 3 | North West Corner Tank 3 - Condensate Ground Level | Need scaffold erected to acccess field wweld on 400 piping, fire water bolt up and top of bund wall. | 2926 | Daniel Edwards | 2016-03-28 | Mechanical | Med Duty | ERECT | Complete | 2016-03-30 | 2016-04-08
5945 | Condensate Tanks | North west corner tank 3 condensate ground level | Need to extend scaffold to access northern wall access to fire water line flange | 3473 | Daniel Edwards | 2016-04-22 | Mechanical | Med Duty | MODIFY | Complete | 2016-04-24 | 2016-05-17
5945 | Condensate Tanks | Condensate Tanks | Need to extend scaffold or strip & rebuild to access top of bund wall to enable modifications to pipe shoes | 3614 | Daniel Edwards | 2016-04-25 | Mechanical | Med Duty | Modify | Complete | 2016-04-27 | 2016-05-03
5946 | TANK 3 | South Western wall Tank 3 Access Platform | Need scaffold erected to access steel mounts in bund wall, beneath patform. Hyde will be built on scaffold (welding, grinding) | 2927 | Daniel Edwards | 2016-03-28 | Mechanical | Med Duty | ERECT | Complete | 2016-04-03 | 2016-04-10
5947 | Condensate Tanks | Condensate Tanks | Please erect mobile scaffold/humpy with wheels 1/2. Please include workbench. | 2928 | Daniel Edwards | 2016-03-28 | Mechanical | Med Duty | ERECT | Complete | 2016-03-31 | 2016-04-03
5948 | ABAA | ABAA | HAND RAILS | 2935 | Paul Slocombe | 2016-03-27 | Mechanical | Med Duty | ERECT | Complete | 2016-03-27 | 2016-04-14
5949 | ABAA | ABAA | Require access for brackets to be welded and tray work to be mounted along stairwell no 33RL up to 40RL to pipe work on the Eastern side of AGRU 2. | 2936 | Paul Slocombe | 2016-03-27 | Mechanical | Med Duty | ERECT | Complete | 2016-04-14 | 2016-04-14
5950 | JAC1 | JAC1 | JAC1 HM-1882 Wstt Access needed to Line # OW-45E38-01 Sub System 45A10-01 for blasting and painting. | 2929 | Troy Brand | 2016-03-29 | Hertel | Med Duty | MODIFY | Complete | 2016-04-04 | 2016-04-24
5951 | AGRU 3 | AGRU 3 | Erect Lifting frame 1 at CCAA. | 2930 | Wayne Hall | 2016-03-28 | Mechanical | Med Duty | ERECT | Complete | 2016-03-28 | 2016-04-14
5952 | AGRU 3 | AGRU 3 | Erect Lifting frame 2 at CCAA. | 2931 | Wayne Hall | 2016-03-28 | Mechanical | Med Duty | ERECT | Complete | 2016-03-28 | 2016-04-14
5953 | AGRU 3 | AGRU 3 | Erect Lifting frame 3 at CCAA. | 2932 | Wayne Hall | 2016-03-28 | Mechanical | Med Duty | ERECT | Complete | 2016-03-28 | 2016-04-14
5954 | AGRU 3 | AGRU 3 | Erect Lifting frame 4 at CCAA. | 2933 | Wayne Hall | 2016-03-28 | Mechanical | Med Duty | ERECT | Complete | 2016-03-28 | 2016-04-14
5955 | INLET | INLET STORE | Pipe spool stands in Laydown area x3. | 2934 | Kevin Hegarty | 2016-03-28 | scaffolding | Med Duty | ERECT | complete | 2016-04-03 | 2016-04-03
5956 | INLET | INLET, GAGA 1st/2nd Level | Provide access to remove large orang spool at GAGA. Access to allow unbolting of flanges, access to then be modified to allow remoall of spool, install of flow meter than flange git up and tensioning again. Additional access may be required for the rigger to attach riggnig gear. | 2937 | Mark Farley | 2016-03-31 | Mechanical | Med Duty | ERECT | Complete | 2016-04-20 | 2016-04-21
5957 | TAFA | TAFA | Erect scaffold ground level of TAFA Western side to access pipe to remove lagging and install blank. | 2941 | Steve Walker | 2016-04-01 | Chevron | Med Duty | ERECT | Not Started | ASAP
5958 | INLET | INLET/MEG, Injection Pumps | Re-instate access to outlet piping in pipe rack. | 2938 | Steven Cameron | 2016-04-01 | Mechanical | Med Duty | ERECT | Complete | 2016-04-02 | 2016-04-14
5959 | INLET | INLET/MEG, Injection Pump No 3 | Install work bench no West side of pump no 3 MEG Injection pump. | 2939 | Steven Cameron | 2016-04-01 | Mechanical | Med Duty | ERECT | Complete | 2016-04-02 | 2016-04-21
5961 | ABAF | ABAF | Extension to existing scaffold on top of MRU for access to fit off and test gas monitor. | 2942 | Paul Slocombe | 2016-04-01 | Mechanical | Med Duty | MODIFY | Complete | 2016-04-01 | 2016-04-12
5962 | DAAA | DAAA | Erect scaffold for Hertel to access vessel to apply Chartec module DAAA Scaff TAG#955 | 2943 | Craig Coombe | 2016-04-01 | scaffolding | Med Duty | ERECT | Complete | 2016-04-04 | 2016-04-04
5962 | DAAA | DAAA | Dismantle Scaffold | 4308 | Trevor Pike | 2016-05-14 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-20 | 2016-05-12
5962 | DAAA | Domgas | Dismantle | 4377 | Trevor Pike | 2016-05-16 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-16 | 2016-05-16
5963 | TRAIN 2 | TRAIN 2- TBF1 Module (A) | Require a scaffold built to access a hatch on the fin fans to complete works inside the confined space. Scaffold boards also need to be installed inside as a work platform. | 2944 | Jason Princen | 2016-04-01 | Mechanical | Med Duty | ERECT | Complete | 2016-04-10 | 2016-05-01
5964 | TRAIN 2 | TRAIN 2- TBF1 Module (B) | Require a scaffold built to access a hatch on the fin fans to complete works inside the confined space. Scaffold boards also need to be installed inside as a work platform. | 2945 | Jason Princen | 2016-04-01 | Mechanical | Med Duty | ERECT | Complete | 2016-04-10 | 2016-05-10
5965 | TRAIN 2 | TRAIN 2- TBG1 Module (A) | Require a scaffold built to access a hatch on the fin fans to complete works inside the confined space. Scaffold boards also need to be installed inside as a work platform. | 2946 | Jason Princen | 2016-04-01 | Mechanical | Med Duty | ERECT | complete | 2016-04-10 | 2016-04-29
5965 | TRAIN 1 | MR FANS T1 | Small extension to existing scaffold at each fan. | 4278 | Patrick Thomas | 2016-05-11 | Mechanical | Med Duty | MODIFY | Complete | 2016-05-12 | 2016-05-16
5965 | TRAIN 1 | MR FANS T1 | Small extension to existing scaffold at each fan. | 4317 | Patrick Thomas | 2016-05-11 | Mechanical | Med Duty | MODIFY | Complete | 2016-05-12 | 2016-05-16
5966 | TRAIN 2 | TRAIN 2- TBG1 Module (B) | Require a scaffold built to access a hatch on the fin fans to complete works inside the confined space. Scaffold boards also need to be installed inside as a work platform. | 2947 | Jason Princen | 2016-04-01 | Mechanical | Med Duty | ERECT | Complete | 2016-04-10 | 2016-04-14
5966 | TRAIN 1 | MR FANS T1 | Small extension to existing scaffold at each fan. | 4277 | Patrick Thomas | 2016-05-11 | Mechanical | Med Duty | MODIFY | Complete | 2016-05-12 | 2016-05-13
5966 | TRAIN 1 | MR FANS T1 | Small extension to existing scaffold at each fan. | 4316 | Patrick Thomas | 2016-05-11 | Mechanical | Med Duty | MODIFY | Complete | 2016-05-12 | 2016-05-13
5967 | TRAIN 3 | TRAIN 3- TCF1 Module (A) | Require a scaffold built to access a hatch on the fin fans to complete works inside the confined space. Scaffold boards also need to be installed inside as a work platform. | 2948 | Jason Princen | 2016-04-01 | Mechanical | Med Duty | ERECT | Complete | 2016-04-10 | 2016-04-18
5968 | TRAIN 3 | TRAIN 3- TCF1 Module (B) | Require a scaffold built to access a hatch on the fin fans to complete works inside the confined space. Scaffold boards also need to be installed inside as a work platform. | 2949 | Jason Princen | 2016-04-01 | Mechanical | Med Duty | ERECT | Complete | 2016-04-10 | 2016-04-18
5969 | TRAIN 3 | TRAIN 3- TCG1 Module (A) | Require a scaffold built to access a hatch on the fin fans to complete works inside the confined space. Scaffold boards also need to be installed inside as a work platform. | 2950 | Jason Princen | 2016-04-01 | Mechanical | Med Duty | ERECT | Complete | 2016-04-10 | 2016-04-18
5970 | TRAIN 3 | TRAIN 3- TCG1 Module (B) | Require a scaffold built to access a hatch on the fin fans to complete works inside the confined space. Scaffold boards also need to be installed inside as a work platform. | 2951 | Jason Princen | 2016-04-01 | Mechanical | Med Duty | ERECT | Complete | 2016-04-10 | 2016-04-18
5971 | GAHK | GAHK | Level 1 NE Ground Stairs. TAKEOVER Scaff TAG# G217 | 2957 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-05-18
5972 | GAHK | GAHK | Level 1 South. TAKEOVER Scaff TAG# G924 | 2958 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-14
5973 | GAHK | GAHK | Level 2 North. TAKEOVER Scaff TAG# G706 | 2959 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-19
5974 | GAHK South | GAHK South | TAKEOVER. Scaff TAG #G715 | 2960 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-19
5975 | GACA | GACA | Ground Level Mobile. TAKEOVER. Scaff TAG# G1507 | 2961 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-10
5976 | GACA | GACA | Level 1 West. TAKEOVER. Scaff TAG# G1202 | 2962 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-03-25
5977 | GACA | GACA | Level 1 Centre. TAKEOVER. Scaff TAG# G1254 | 2963 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-19
5977 | GACA | Sitewide | Modify Scaffold 5977GACA | 4420 | Rick Muston | 2016-05-19 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-19 | 2016-05-24
5978 | GACA | GACA | Level 1 Centre. TAKEOVER. Scaff TAG# G1482 | 2964 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-07
5979 | GACA | GACA | South Level 1 . TAKEOVER. Scaff TAG# G846 | 2965 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-19
5980 | GACA | GACA | Level 1 South. TAKEOVER. Scaff TAG# G813 | 2966 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-19
5981 | GACA | GACA | Level 1 North. TAKEOVER. Scaff TAG# G1451 | 2967 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-07
5982 | GACA | GACA | Level 2 North West. TAKEOVER. Scaff TAG# G1556 | 2968 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-05-18
5982 | GACA | INLET- GACA LVL 2 | Take ownership of CKJV Scaffold G11556 | 2968 | Mark Orr | 2016-04-08 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-08 | 2016-04-08
5983 | GACA | GACA | Level 2 Centre. TAKEOVER. Scaff TAG# G1136 | 2969 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-07
5984 | GACA | GACA | Level 2. TAKEOVER. Scaff TAG# G655 A&B | 2970 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-05-18
5984 | GACA | INLET- GACA | Level 2 TAKEOVER Scaff TAG# G655 A&B | 2970 | Mark Orr | 2016-04-08 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-08 | 2016-04-08
5985 | GACA | GACA | Level 2. TAKEOVER. Scaff TAG# G1555 | 2971 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-05-18
5985 | GACA | INLET- GACA | Take ownership of CKJV Scaffold G1555 | 2971 | Mark Orr | 2016-04-08 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-08 | 2016-04-08
5986 | GACA | GACA | Level 2.5 North side. TAKEOVER. Scaff TAG# G1092 | 2972 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-09
5987 |  | Painters Container Abutment | Erect shelving in 10ft & 20ft Container | 2973 | Mark Orr | 2015-07-25 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-07-25 | 2016-04-09
5987 | GACA | GACA | Level 3. TAKEOVER. Scaff TAG# G106 | 2973 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-05-18
5988 | GACA | GACA | Level 3. TAKEOVER. Scaff TAG# G105 | 2974 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-09
5989 | GACA | GACA | Level 3 North. TAKEOVER. Scaff TAG# G1324 | 2975 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-09
5990 | GACA | GACA | Level 3 . TAKEOVER. Scaff TAG# G1139 | 2976 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-09
5991 | GACA | GACA | Level 3 SE . TAKEOVER. Scaff TAG# G1326 | 2977 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-09
5992 | GACA | GACA | Level 3 SOUTH EAST . TAKEOVER. Scaff TAG# G1138 | 2978 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-09
5993 | GAHL Lvl 1 | GAHL Lvl 1 | TAKEOVER. Scaff TAG# G1178 | 2979 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-07
5994 | JACA Lvl 3 | JACA Lvl 3 | Mobile scaffold. TAKEOVER. Scaff TAG# G1705 | 2980 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-19
5995 | JACA Lvl 3 | JACA Lvl 3 | Mobile. TAKEOVER. Scaff TAG# G1712 | 2981 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-19
5996 | GAHJ | GAHJ | North East Ground stairs to access. TAKEOVER. Scaff TAG# G377 | 2982 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-06
5997 | GAHJ - Level 3 | GAHJ - Level 3 | Handrail Level 3 GAHJ. TAKEOVER. Scaff TAG# G1022 | 2983 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-06
5998 | GAHJ - Level 2 | GAHJ - Level 2 | TAKEOVER. Scaff TAG# G378 | 2984 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-06
5999 | GAHJ - Level 2 | GAHJ - Level 2 | TAKEOVER. Scaff TAG# G379 | 2985 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-06
6000 | GAHJ - Level 1 | GAHJ - Level 1 | TAKEOVER. Scaff TAG# G451 | 2986 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-19
6001 | JADA - Level 2 | JADA - Level 2 | TAKEOVER. Scaff TAG# G1183 | 2987 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-04
6002 | JADA - Level 2 | JADA - Level 2 | TAKEOVER. Scaff TAG# G981 | 2988 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-04
6003 | JADA - Level 2 | JADA - Level 2 | TAKEOVER. Scaff TAG# G1488 | 2989 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-04
6004 | JADA - Level 2 | JADA - Level 2 | TAKEOVER. Scaff TAG# G714 | 2990 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-04
6005 | JADA - Level 2 | JADA - Level 2 | TAKEOVER. Scaff TAG# G1277 | 2991 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-04
6006 | GAGA - Level 2 | GAGA - Level 2 | TAKEOVER. Scaff TAG# G927 | 2992 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-05-18
6007 | GAGA - Level 2 | GAGA - Level 2 | TAKEOVER. Scaff TAG# G1144 | 2993 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-05
6008 | GAGA - Level 2 | GAGA - Level 2 | TAKEOVER. Scaff TAG# G984 | 2994 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-05
6009 | GAGA - Level 2 | GAGA - Level 2 | TAKEOVER. Scaff TAG# G0792 | 2995 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-05
6010 | GAGA - Level 2 | GAGA - Level 2 | TAKEOVER. Scaff TAG# G1050 | 2996 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-05
6011 | GAGA - Level 1 | GAGA - Level 1 | TAKEOVER. Scaff TAG# G812 | 2997 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-04
6012 | GAGA - Level 1 | GAGA - Level 1 | TAKEOVER. Scaff TAG# G1106 | 2998 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-04
6013 | GAGA - Level 1 | GAGA - Level 1 | TAKEOVER. Scaff TAG# GW608 | 2999 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-04
6014 | JADA | JADA | TAKEOVER. Scaff TAG# 1171 | 3000 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-04
6015 | Top of ladder - UAMA Heater | Top of ladder - UAMA Heater | TAKEOVER. Scaff TAG# 1155 | 3001 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-14
6016 | RBAN | RBAN | TAKEOVER. Scaff TAG# 1100 | 3002 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-06
6017 | RBAL | RBAL | TAKEOVER. Scaff TAG# 1111 | 3003 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-06
6018 | RBAN | RBAN | TAKEOVER. Scaff TAG# 1103 | 3004 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-02
6019 | RBAN | RBAN | TAKEOVER. Scaff TAG# 1104 | 3005 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-06
6020 | UAMA | UAMA | TAKEOVER. Scaff TAG# 1109 | 3006 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-14
6021 | UAMA | UAMA | TAKEOVER. Scaff TAG# 1110 | 3007 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-14
6022 | RBAL/GAHL | RBAL/GAHL | TAKEOVER. CKJV SCAFF (no number) | 3008 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-06
6023 | UAMA GATE | UAMA GATE | TAKEOVER. Scaff TAG# G1639 | 3009 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-14
6024 | UAMA Mobile | UAMA Mobile | TAKEOVER. Scaff TAG# G1330 | 3010 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-14
6025 | UAMA | UAMA | TAKEOVER. Scaff TAG# G1512 | 3011 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-14
6026 | JACA Ground | JACA Ground | TAKEOVER. Scaff TAG# G1188 | 3012 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-19
6027 | GAGA Level 2 | GAGA Level 2 | TAKEOVER. Scaff TAG# G1298 | 3013 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-05
6028 | GAGA Level 2 | GAGA Level 2 | TAKEOVER. Scaff TAG# G1112 | 3014 | Joel Gray | 2016-04-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-10 | 2016-04-19
6029 | GACA | GACA | GACA HM-1989 Erect mobile scaffold to be used as an eye wash station. | 2952 | James Halliday | 2016-04-01 | Hertel | Med Duty | ERECT | Complete | 2016-04-06 | 2016-04-20
6030 | RBAE | RBAE-RBAC up ladder | Request access. Needs modifications. | 2953 | Blur | 2016-04-01 | APS | Med Duty | MODIFY | Complete | 2016-04-07 | 2016-05-15
6031 | AGRU 2 | Agru 2 | 1. Scaffold stair access and hand rail to existing stairs on frac tank required. 2. 2 x hope over for acess into small bund. 3. Install hard barricade around han hole cover to install temp drains. 4. Scaffold access platform, ladder and handrail to empty tank marked on drawing for inspection and drains to run into. | 2954 | Todd Lyons | 2016-04-02 | Mechanical | Med Duty | ERECT | Not Started | 2016-04-03
6032 | Condensate Tanks | Condensate Tanks | Please erect mobile scaffold (humpie) with work bench. Wheel type. | 2955 | Robert Hanley | 2016-04-02 | Mechanical | Med Duty | ERECT | complete | 2016-04-02 | 2016-04-28
6032 | SAH1 | Condensate Tanks | Dismantle 6032 | 4363 | Craig Coombe | 2016-05-15 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-15 | 2016-05-17
6033 | Condensate Tanks | Condensate Tanks | Please erect mobile scaffold (humpie) with work bench. Wheel type. | 2956 | Robert Hanley | 2016-04-02 | Mechanical | Med Duty | ERECT | complete | 2016-04-02 | 2016-04-28
6034 | TACA Top Level | TACA Top Level | Erect access to remove lagging and access flange ono 1400 spool vessel tops. Train 1 Remediation Works CUX. Iterim TAG #5009 | 3015 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | ERECT | COMPLETE | 2016-04-03 | 2016-04-03
6035 | TACA Top Level | TACA Top Level | Erect access to remove lagging and access flange ono 1400 spool vessel tops. Train 1 Remediation Works CUX. Iterim TAG #5005 | 3016 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | ERECT | COMPLETE | 2016-04-03 | 2016-04-03
6035 | TACA | TACA - Train 1 top level | Dismantle Scaffold | 4303 | Barry Baker | 2016-05-14 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-20 | 2016-05-16
6036 | TACA Top Level | TACA Top Level | Erect access to remove lagging and access flange ono 1400 spool vessel tops. Train 1 Remediation Works CUX. Iterim TAG #5006 | 3017 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | ERECT | COMPLETE | 2016-04-03 | 2016-04-03
6036 | TACA | TACA - Train 1 top level | Dismantle Scaffold | 4306 | Barry Baker | 2016-05-14 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-20 | 2016-05-16
6037 | TACA Top Level | TACA Top Level | Erect access to remove lagging and access flange ono 1400 spool vessel tops. Train 1 Remediation Works CUX. Iterim TAG #5007 | 3018 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | ERECT | COMPLETE | 2016-04-03 | 2016-04-03
6037 | TACA | TACA - Train 1 top level | Dismantle Scaffold | 4301 | Barry Baker | 2016-05-14 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-20 | 2016-05-16
6038 | TACA Top Level | TACA Top Level | Erect access to remove lagging and access flange ono 1400 spool vessel tops. Train 1 Remediation Works CUX. Iterim TAG #5008 | 3019 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | ERECT | COMPLETE | 2016-04-03 | 2016-04-03
6038 | TACA | TACA - Train 1 top level | Dismantle Scaffold | 4304 | Barry Baker | 2016-05-14 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-20 | 2016-05-16
6039 | TACA Top Level | TACA Top Level | Erect access to remove lagging and access flange ono 1400 spool vessel tops. Train 1 Remediation Works CUX. Iterim TAG #5010 | 3020 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | ERECT | COMPLETE | 2016-04-03 | 2016-04-03
6040 | Train 1 Fin Fan Modules | Train 1 Fin Fan Modules | Erect access to high point vent nozzles. Train 1 Remediation Works CUX. Interim TAG# Level 4 Fin Fans | 3021 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | ERECT | COMPLETE | 2016-04-03 | 2016-04-03
6040 | Train 1 Fin Fan Modules | Train 1 Fin Fan Modules | Dismantle Shutdown | 3021 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | SHUTDOWN-DISMANTLE | Complete | 2016-04-03 | 2016-04-29
6041 | Train 1 Fin Fan Modules | Train 1 Fin Fan Modules | Erect access to high point vent nozzles. Train 1 Remediation Works CUX. Interim TAG# Level 4 Fin Fans | 3022 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | ERECT | COMPLETE | 2016-04-03 | 2016-04-03
6041 | Train 1 Fin Fan Modules | Train 1 Fin Fan Modules | Dismantle Shutdown | 3022 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | SHUTDOWN-DISMANTLE | Complete | 2016-04-03 | 2016-04-29
6042 | Train 1 Fin Fan Modules | Train 1 Fin Fan Modules | Erect access to high point vent nozzles. Train 1 Remediation Works CUX. Interim TAG# Level 4 Fin Fans | 3023 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | ERECT | COMPLETE | 2016-04-03 | 2016-04-03
6042 | Train 1 Fin Fan Modules | Train 1 Fin Fan Modules | Dismantle Shutdown | 3023 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | SHUTDOWN-DISMANTLE | Complete | 2016-04-03 | 2016-04-29
6043 | Train 1 Fin Fan Modules | Train 1 Fin Fan Modules | Erect access to high point vent nozzles. Train 1 Remediation Works CUX. Interim TAG# Level 4 Fin Fans | 3024 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | ERECT | COMPLETE | 2016-04-03 | 2016-04-03
6043 | Train 1 Fin Fan Modules | Train 1 Fin Fan Modules | Dismantle Shutdown | 3024 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | SHUTDOWN-DISMANTLE | Complete | 2016-04-03 | 2016-04-29
6044 | Train 1 Fin Fan Modules | Train 1 Fin Fan Modules | Erect access to high point vent nozzles. Train 1 Remediation Works CUX. Interim TAG# Level 4 Fin Fans | 3025 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | ERECT | COMPLETE | 2016-04-03 | 2016-04-03
6044 | Train 1 Fin Fan Modules | Train 1 Fin Fan Modules | Dismantle Shutdown | 3025 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | SHUTDOWN-DISMANTLE | Complete | 2016-04-03 | 2016-04-29
6045 | Train 1 Fin Fan Modules | Train 1 Fin Fan Modules | Erect access to high point vent nozzles. Train 1 Remediation Works CUX. Interim TAG# Level 4 Fin Fans | 3026 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | ERECT | COMPLETE | 2016-04-03 | 2016-04-03
6045 | Train 1 Fin Fan Modules | Train 1 Fin Fan Modules | Dismantle Shutdown | 3026 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | SHUTDOWN-DISMANTLE | Complete | 2016-04-03 | 2016-04-29
6046 | Train 1 Fin Fan Modules | Train 1 Fin Fan Modules | Erect access to high point vent nozzles. Train 1 Remediation Works CUX. Interim TAG# Level 4 Fin Fans | 3027 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | ERECT | COMPLETE | 2016-04-03 | 2016-04-03
6046 | Train 1 Fin Fan Modules | Train 1 Fin Fan Modules | Dismantle Shutdown | 3027 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | SHUTDOWN-DISMANTLE | Complete | 2016-04-03 | 2016-04-29
6047 | Train 1 Fin Fan Modules | Train 1 Fin Fan Modules | Erect access to high point vent nozzles. Train 1 Remediation Works CUX. Interim TAG# Level 4 Fin Fans | 3028 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | ERECT | COMPLETE | 2016-04-03 | 2016-04-03
6047 | Train 1 Fin Fan Modules | Train 1 Fin Fan Modules | Dismantle Shutdown | 3028 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | SHUTDOWN-DISMANTLE | Complete | 2016-04-03 | 2016-04-29
6048 | Train 1 Fin Fan Modules | Train 1 Fin Fan Modules | Erect access to high point vent nozzles. Train 1 Remediation Works CUX. Interim TAG# Level 4 Fin Fans | 3029 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | ERECT | COMPLETE | 2016-04-03 | 2016-04-03
6048 | Train 1 Fin Fan Modules | Train 1 Fin Fan Modules | Dismantle Shutdown | 3029 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | SHUTDOWN-DISMANTLE | Complete | 2016-04-03 | 2016-04-29
6049 | Train 1 Fin Fan Modules | Train 1 Fin Fan Modules | Erect access to high point vent nozzles. Train 1 Remediation Works CUX. Interim TAG# Level 4 Fin Fans | 3030 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | ERECT | COMPLETE | 2016-04-03 | 2016-04-03
6049 | Train 1 Fin Fan Modules | Train 1 Fin Fan Modules | Dismantle Shutdown | 3030 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | SHUTDOWN-DISMANTLE | Complete | 2016-04-03 | 2016-04-29
6050 | Train 1 Fin Fan Modules | Train 1 Fin Fan Modules | Erect access to high point vent nozzles. Train 1 Remediation Works CUX. Interim TAG# Level 4 Fin Fans | 3031 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | ERECT | COMPLETE | 2016-04-03 | 2016-04-03
6050 | Train 1 Fin Fan Modules | Train 1 Fin Fan Modules | Dismantle Shutdown | 3031 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | SHUTDOWN-DISMANTLE | Complete | 2016-04-03 | 2016-04-29
6051 | TACA LVL 3 | TACA LVL 3 | Erect access to valve on vessel. Train 1 Remediation works. CUX Interim TAG# 5004 | 3032 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | ERECT | COMPLETE | 2016-04-03 | 2016-04-04
6051 | TACA LVL 3 | TACA LVL 3 | Erect access to valve on vessel. Train 1 Remediation works. CUX Interim TAG# 5004 | 4279 | Martin Riegert | 2016-05-12 | scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-12 | 2016-05-12
6052 | TACA LVL 3 | TACA LVL 3 | Erect access to valve on vessel. Train 1 Remediation works. CUX Interim TAG# 5003 | 3033 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | ERECT | COMPLETE | 2016-04-03 | 2016-04-04
6053 | TACA LVL 4 | TACA LVL 4 | Erect mobile scaffold to de-lag vessel. Train 1 Remediation works. TACA LVL 4. Interim TAG#5002 | 3034 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | ERECT | COMPLETE | 2016-04-03 | 2016-04-04
6054 | TACA LVL 4 | TACA LVL 4 | Erect mobile scaffold to de-lag vessel. Train 1 Remediation works. TACA LVL 4. Interim TAG#5001 | 3035 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | ERECT | COMPLETE | 2016-04-03 | 2016-04-04
6055 | Train 1 Fin Fan Modules | Train 1 Fin Fan Modules | Erect access to high point vent nozzles. Train 1 Remediation Works CUX. Interim TAG# Level 4 Fin Fans | 3036 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | ERECT | COMPLETE | 2016-04-03 | 2016-04-03
6055 | Train 1 Fin Fan Modules | Train 1 Fin Fan Modules | Erect access to high point vent nozzles. Train 1 Remediation Works CUX. Interim TAG# Level 4 Fin Fans | 3036 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | DISMANTLE | Complete | 2016-04-03 | 2016-04-29
6056 | TAJA | TAJA Level 3 | Erect access to high point valve and flange for removal. Train 1 Remediation Works. CUX | 3037 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | ERECT | Complete | 2016-04-03 | 2016-04-04
6057 | TACA | TACA Top Level | Erect access to valve to remove lagging (South West CNR Valve) Train 1 Remediation Works. CUX | 3038 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | ERECT | Complete | 2016-04-03 | 2016-04-04
6058 | TACA | TACA Level 3 | Erect extension to valve Train 1 Remediation Works. CUX. TAG# 5910B | 3039 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | ERECT | Complete | 2016-04-03 | 2016-03-31
6059 | TACA | TACA Level 4 | Erect mobile scaffold to access lagging. Train 1 Remediation Works. CUX Interim TAG# 2016331B | 3040 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | ERECT | Complete | 2016-04-03 | 2016-03-31
6060 | TACA | TACA Level 5 | Erect mobile scaffold to access lagging. Train 1 Remediation Works. CUX Interim TAG# 2016331A (Erected by NS) | 3041 | Martin Riegert | 2016-04-03 | scaffolding | Med Duty | ERECT | Complete | 2016-04-03 | 2016-04-03
6061 | Jetty | JETTY HEAD | Scaffold to be installed to complete punchlisting items | 3042 | Grant Percy | 2016-04-02 | Electrical | Med Duty | ERECT | Complete | 2016-04-04 | 2016-05-05
6062 | Jetty AREA 2 | JETTY AREA 2 | Install hand rail around capsan ono MD2 West to allow for pre-comm works on capstan. Note: Need access to capstan only. May need to block access to east side capstans and south f MD2. | 3043 | John Ledo | 2016-04-03 | Pre-comm | Med Duty | ERECT | Complete | 2016-04-06 | 2016-04-14
6063 | GADA | GADA | Modify scaffold on Vessel 1080 on 3rd level. Remove boards and tubes for installation of 2 inch stainless line then reinstate. | 2538 | Paul Velonias | 2016-03-15 | Mechanical | Med Duty | MODIFY | Cancelled | 2016-03-20
6065 | GAGA | GAGA LVL 2, NORTH EAST CORNER OF MODULE | Scaffold already built, requiring an inspection and tag. Please see attached model shot. | 3044 | Mark Farley | 2016-04-03 | Mechanical | Med Duty | ERECT | Complete | 2016-04-05 | 2016-04-18
6066 | AGRU 2 | AGRU 2 | Scaffold deck to access High point and low point drains. South West Corner of AGRU2. | 3045 | Todd Lyons | 2016-04-04 | Mechanical | Med Duty | ERECT | Not Started | 2016-04-04
6067 | RBAE | RBAE | RBAE HM-1902 encapsulation frame needed for chartek works ono shearkey south east end second column. | 3046 | Felise Emelio | 2016-04-11 | Hertel | Med Duty | ERECT | Complete | 2016-04-04 | 2016-04-18
6068 | TRAIN 2 TBAA | TRAIN 2 TBAA | Dismantle rated anchor humpy, top south. | 3049 | George Fomin | 2016-04-05 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-05 | 2016-04-03
6069 | TRAIN 2 TBAA | TRAIN 2 TBAA | Dismantle anchor point for catalyst, top south. Scaff TAG# 5262 | 3048 | George Fomin | 2016-04-05 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-05 | 2016-04-05
6070 | TRAIN 2 TBAA | TRAIN 2 TBAA | Dismantle humpy, top south. Scaff TAG# 5259 | 3047 | George Fomin | 2016-04-05 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-05 | 2016-04-05
6071 | LNG TANK AREA | LNG TANK AREA | Dismantle scaffold humpy North end of LNG Tanks. | 3050 | George Fomin | 2016-04-05 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-05 | 2016-04-03
6072 | ABAH | ABAH | Hand rail extension and new ladder access. | 3051 | Paul Slocombe | 2016-04-04 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-04-04 | 2016-04-14
6073 | RBAQ North | RBAQ North | Takeover Scaff TAG# H1922 | 3052 | Joel Gray | 2016-04-11 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-04 | 2016-05-18
6074 | RBAQ North | RBAQ North | Modify. Scaff TAG# H903 | 3053 | Joel Gray | 2016-04-11 | scaffolding | Med Duty | MODIFY | Complete | 2016-04-04 | 2016-05-20
6074 | RBAQ North | RBAQ North | Takeover. Scaff TAG# H903 | 3053 | Joel Gray | 2016-04-11 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-04 | 2016-05-20
6074 | RBAQ North | RBAQ North | Dismantle Scaff TAG# H903 | 3053 | Joel Gray | 2016-04-11 | scaffolding | Med Duty | DISMANTLE | Complete | 2016-04-04 | 2016-05-21
6075 | RBAQ North | RBAQ North | Modify Scaff TAG# H1185 | 3054 | Joel Gray | 2016-04-11 | scaffolding | Med Duty | MODIFY | Complete | 2016-04-04 | 2016-05-20
6075 | RBAQ North | RBAQ North | Takeover. Scaff TAG# H1185 | 3054 | Joel Gray | 2016-04-11 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-04 | 2016-05-20
6075 | RBAQ North | RBAQ North | Dismantle Scaff TAG# H1185 | 3054 | Joel Gray | 2016-04-11 | scaffolding | Med Duty | DISMANTLE | Complete | 2016-04-04 | 2016-05-21
6076 | RBAQ North | RBAQ North | Modify. Scaff TAG# H1890 | 3055 | Joel Gray | 2016-04-11 | scaffolding | Med Duty | MODIFY | Complete | 2016-04-04 | 2016-05-20
6076 | RBAQ North | RBAQ North | Takeover. Scaff TAG# H1890 | 3055 | Joel Gray | 2016-04-11 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-04 | 2016-05-20
6076 | RBAQ North | RBAQ North | Dismantle Scaff TAG# H1890 | 3055 | Joel Gray | 2016-04-11 | scaffolding | Med Duty | DISMANTLE | Complete | 2016-04-04 | 2016-05-21
6077 | RBAQ North | RBAQ North | Modify Scaff TAG#H1896 | 3056 | Joel Gray | 2016-04-11 | scaffolding | Med Duty | MODIFY | Complete | 2016-04-04 | 2016-05-20
6077 | RBAQ North | RBAQ North | Takeover. Scaff TAG#H1896 | 3056 | Joel Gray | 2016-04-11 | scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-04 | 2016-05-20
6077 | RBAQ North | RBAQ North | Dismantle Scaff TAG#H1896 | 3056 | Joel Gray | 2016-04-11 | scaffolding | Med Duty | DISMANTLE | Complete | 2016-04-04 | 2016-05-21
6078 | INLET GAGA | INLET GAGA | Please provide access to allow removal and installation of pipe support steel work allowing for full encapsulation. | 3057 | Mark Farley | 2016-04-05 | Mechanical | Med Duty | ERECT | Complete | 2016-04-05 | 2016-04-18
6079 | TAJA | level 2 TAJA | Build scaffold to reach flange bolts on eastern side of pipe on level 2 TAJA SHUT DOWN | 3061 | Dave Dundon | 2016-04-07 | scaffolding | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-07 | 2016-04-06
6080 | TAJA | TAJA | Build hanging scaffold at good height to weld beams to support blind SHUT DOWN | 3062 | Dave Dundon | 2016-04-07 | scaffolding | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-07 | 2016-04-04
6081 | TACA | level 3 TACA | Erect scaffold hand rails around all vessels on level 3 for confined space entry SHUT DOWN | 3063 | Dave Dundon | 2016-04-07 | scaffolding | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-07 | 2016-04-03
6082 | TAFA | TAFA | Build scaffold on southern side of PR Compressor to access bolts to remove lids SHUT DOWN | 3064 | Dave Dundon | 2016-04-07 | scaffolding | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-07 | 2016-04-02
6083 | TAFA | TAFA | Build scaffold on northern side of PR Compressor to access bolts to remove lids SHUT DOWN | 3065 | Dave Dundon | 2016-04-07 | scaffolding | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-07 | 2016-03-30
6084 | TAFA | TAFA | Build scaffold work benches for all trades to utilise SHUT DOWN | 3066 | Dave Dundon | 2016-04-07 | scaffolding | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-07 | 2016-03-30
6085 | TAFA | TAFA | Build scaffold from ground level up to pipe to remove blind (approx. 6m deck) SHUT DOWN | 3109 | Dave Dundon | 2016-04-07 | scaffolding | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-07 | 2016-03-30
6085 | TAFA | TAFA | Build scaffold from ground level up to pipe to remove blind (approx. 6m deck) SHUT DOWN | 3067 | Dave Dundon | 2016-04-07 | scaffolding | Med Duty | DISMANTLE | Complete | 2016-04-07 | 2016-04-07
6086 | TACA | TACA | Erect scaffold on top level of TACA, mirror image of existing UGL scaffold SHUT DOWN | 3068 | Dave Dundon | 2016-04-07 | scaffolding | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-07 | 2016-04-01
6087 | TACA | TACA | Additinoal scaffolds to UGL scaffolds to access blinds / flanges. SHUT DOWN | 3069 | Dave Dundon | 2016-04-07 | scaffolding | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-07 | 2016-04-04
6087 | TACA | TACA | Modify scaffolds to UGL scaffolds to access blinds / flanges. SHUT DOWN | 3069 | Dave Dundon | 2016-04-07 | scaffolding | Med Duty | SHUTDOWN-MODIFY | Complete | 2016-04-07 | 2016-04-29
6087 | TRAIN 1 | TACA | Dismantle scaffolding N/W corner Level 4 of TACA ARV valves. | 4205 | Steven Linton | 2016-05-09 | KJV | Med Duty | DISMANTLE | Complete | 2016-05-09 | 2016-05-09
6088 | TACA | TACA | Additinoal scaffolds to UGL scaffolds to access blinds / flanges. SHUT DOWN | 3070 | Dave Dundon | 2016-04-07 | scaffolding | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-07 | 2016-04-06
6088 | TACA | TACA | Additinoal scaffolds to UGL scaffolds to access blinds / flanges. SHUT DOWN | 3070 | Dave Dundon | 2016-04-29 | scaffolding | Med Duty | SHUTDOWN-MODIFY | Complete | 2016-04-29 | 2016-04-29
6088 | TRAIN 1 | TACA | Dismantle scaffolding N/W corner Level 4 of TACA ARV valves. | 4205 | Steven Linton | 2016-05-09 | KJV | Med Duty | DISMANTLE | Complete | 2016-05-09 | 2016-05-09
6089 | TACA | TACA | Additinoal scaffolds to UGL scaffolds to access blinds / flanges. SHUT DOWN | 3071 | Dave Dundon | 2016-04-07 | scaffolding | Med Duty | SHUTDOWN-MODIFY | Complete | 2016-04-07 | 2016-04-08
6089 | TACA | TACA | Modify scaffolds to UGL scaffolds to access blinds / flanges. SHUT DOWN | 3071 | Dave Dundon | 2016-04-07 | scaffolding | Med Duty | SHUTDOWN-MODIFY | Complete | 2016-04-07 | 2016-04-29
6089 | TBCA | TBCA Train 3 | ERECT SCAFFOLD LEVEL 2 OF TRAIN 3 INSIDE VESSEL 1 SHUT DOWN | 3071 | Dave Dundon | 2016-04-08 | scaffolding | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-08 | 2016-04-06
6090 | TBCA | TBCA Train 3 | ERECT SCAFFOLD HANDRAILS AROUND TANK 1 SHUT DOWN | 3072 | Dave Dundon | 2016-04-06 | scaffolding | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-06 | 2016-04-06
6090 | TACA | TACA | Additinoal scaffolds to UGL scaffolds to access blinds / flanges. SHUT DOWN | 3072 | Dave Dundon | 2016-04-07 | scaffolding | Med Duty | SHUTDOWN-MODIFY | Complete | 2016-04-07 | 2016-04-08
6090 | TACA | TACA | Additinoal scaffolds to UGL scaffolds to access blinds / flanges. SHUT DOWN | 3072 | Dave Dundon | 2016-04-29 | scaffolding | Med Duty | SHUTDOWN-MODIFY | Complete | 2016-04-29 | 2016-04-29
6090 | TRAIN 1 | TACA | Dismantle scaffold inside vessel 1531 train 1 level 3 | 4206 | Trevor Pike | 2016-05-09 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-09 | 2016-05-09
6091 | TBCA | TBCA Train 3 | ERECT SCAFFOLD LEVEL 2 OF TRAIN 3 INSIDE VESSEL 2 SHUT DOWN | 3073 | Dave Dundon | 2016-04-08 | scaffolding | Med Duty | ERECT | Cancelled | 2016-04-08
6092 | TBCA | TBCA Train 3 | ERECT SCAFFOLD HANDRAILS AROUND TANK 2 SHUT DOWN | 3074 | Dave Dundon | 2016-04-06 | scaffolding | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-06 | 2016-04-06
6092 | TACA | TACA | Additinoal scaffolds to UGL scaffolds to access blinds / flanges. SHUT DOWN | 3074 | Dave Dundon | 2016-04-07 | scaffolding | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-07 | 2016-04-08
6092 | TACA | TACA | Modify scaffolds to UGL scaffolds to access blinds / flanges. SHUT DOWN | 3074 | Dave Dundon | 2016-04-29 | scaffolding | Med Duty | SHUTDOWN-MODIFY | Complete | 2016-04-29 | 2016-04-29
6092 | TRAIN 1 | TACA | Dismantle scaffold inside vessel 1532 train 1 level 3 | 4207 | Trevor Pike | 2016-05-09 | Mechanical | Med Duty | SHUTDOWN-DISMANTLE | Complete | 2016-05-09 | 2016-05-09
6093 | TACA | TACA | Additinoal scaffolds to UGL scaffolds to access blinds / flanges. SHUT DOWN | 3075 | Dave Dundon | 2016-04-07 | scaffolding | Med Duty | SHUTDOWN-MODIFY | Complete | 2016-04-07 | 2016-04-06
6093 | TBCA | TBCA Train 3 | ERECT SCAFFOLD HANDRAILS AROUND TANK 3 SHUT DOWN | 3075 | Dave Dundon | 2016-04-08 | scaffolding | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-08 | 2016-04-08
6094 | TBCA | TBCA Train 3 | ERECT SCAFFOLD LEVEL 2 OF TRAIN 3 INSIDE VESSEL 3 SHUT DOWN | 3076 | Dave Dundon | 2016-04-08 | scaffolding | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-08 | 2016-04-08
6095 | TACA | TACA | Additinoal scaffolds to UGL scaffolds to access blinds / flanges. SHUT DOWN | 3077 | Dave Dundon | 2016-04-07 | scaffolding | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-07 | 2016-04-06
6095 | TBCA | TBCA Train 3 | ERECT SCAFFOLD HANDRAILS AROUND TANK 4 SHUT DOWN | 3077 | Dave Dundon | 2016-04-08 | scaffolding | Med Duty | ERECT | Complete | 2016-04-08 | 2016-04-08
6095 | TRAIN 1 | TACA | Dismantle scaffolds for ARV valves, top of train 1 TACA Western side. Scaffold numbers 6093, 6092, 6095, 6090. | 4208 | Trevor Pike | 2016-05-09 | Mechanical | Med Duty | SHUTDOWN-DISMANTLE | Complete | 2016-05-09 | 2016-05-09
6096 | TBCA | TBCA Train 3 | ERECT SCAFFOLD LEVEL 2 OF TRAIN 3 INSIDE VESSEL 4 SHUT DOWN | 3078 | Dave Dundon | 2016-04-08 | scaffolding | Med Duty | ERECT | Complete | 2016-04-08 | 2016-04-08
6097 | ABAA | 1ST Level S/E AGRU2 | Scaffold to be built to install support structure, Cable ladder, cable on RL 20 | 3060 | Gunther Grossinger | 2016-04-07 | Mechanical | Med Duty | ERECT | complete | 2016-04-07 | 2016-04-28
6098 | SADA | SADA | SADA level 1 central HM - 1906 need to dismantle top lift scaffold 1043 adjacent scaffold 1042 to allow for insulation works | 3079 | Felise Emelio | 2016-04-08 | Hertel | Med Duty | DISMANTLE | Complete | 2016-04-13 | 2016-04-10
6099 | SADA | SADA | SADA West of module level 2 hook up HM - 1904 need to modify scaffold to allow for insulation work | 3080 | Felise Emelio | 2016-04-08 | Hertel | Med Duty | DISMANTLE | Complete | 2016-04-13 | 2016-04-10
6100 | SADA | SADA | SADA level 1 central HM - 1905 need to dismantle top lift scaffold 1043 adjacent scaffold 1042 to allow for insulation works | 3081 | Felise Emelio | 2016-04-08 | Hertel | Med Duty | DISMANTLE | Complete | 2016-04-13 | 2016-04-10
6101 | GAAF | GAAF | Scaffold deck for Actuator removal on two Valves on the eastern side of GAAF | 3082 | Lennie Haira | 2016-04-08 | CSU | Med Duty | ERECT | Complete | 2016-04-13 | 2016-04-13
6101 | GAAF | GAAF | Dismantle 6101 | 3225 | Lennie Haira | 2016-04-08 | CSU | Med Duty | DISMANTLE | Complete | 2016-04-13 | 2016-04-14
6101 | GAAF | GAAF | Scaffold deck for Actuator removal on two Valves on the eastern side of GAAF | 3225 | Lennie Haira | 2016-04-08 | CSU | Med Duty | MODIFY | Complete | 2016-04-13 | 2016-04-14
6102 | Gorgon Slug Catcher | Gorgon Slug Catcher | Scaffold required for 2 x ISO containers north end of gorgon slug catcher Access to the top with hand rail to access two openings for internal inspection. | 3083 | Todd Lyons | 2016-04-09 | Mechanical | Med Duty | ERECT | Complete | 2016-04-10 | 2016-04-13
6102 | Gorgon Slug Catcher | Gorgon Slug Catcher | Dismantle scaffold 6102 | 3083 | Todd Lyons | 2016-04-09 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-04-10 | 2016-04-29
6102 | inlet | Gorgon slug catcher north end | Please reomove scaffold to tanks so they can be transorted away on the 20thThese will be getting pumped out During the day on the 19th so will still require the access till night shift that night. 6102 | 3365 | Todd Lyons | 2016-04-17 | Mechanical | Med Duty | MODIFY | Complete | 2016-04-19 | 2016-04-19
6103 | SADA TOP LVL | SADA TOP LVL | Erect SCAFFOLDING , TOP LEVEL OF SADA MODULE EAST SIDE | 3058 | Dave Dundon | 2016-04-05 | scaffolding | Med Duty | ERECT | Complete | 2016-04-05 | 2016-04-04
6103 | SADA TOP LVL | SADA TOP LVL | DISMANTLE SCAFFOLDING , TOP LEVEL OF SADA MODULE EAST SIDE | 3058 | Dave Dundon | 2016-04-05 | scaffolding | Med Duty | DISMANTLE | Complete | 2016-04-05 | 2016-04-05
6104 | SADA TOP LVL | SADA TOP LVL | Erect SCAFFOLDING , TOP LEVEL OF SADA MODULE EAST SIDE | 3059 | Dave Dundon | 2016-04-05 | scaffolding | Med Duty | ERECT | Complete | 2016-04-05 | 2016-04-04
6104 | SADA TOP LVL | SADA TOP LVL | DISMANTLE SCAFFOLDING , TOP LEVEL OF SADA MODULE EAST SIDE | 3059 | Dave Dundon | 2016-04-05 | scaffolding | Med Duty | DISMANTLE | Complete | 2016-04-05 | 2016-04-05
6105 | TACA | Train 1 Level 1 - TACA | Heavy duty support bench for actuator | 3084 | Dave Dundon | 2016-04-08 | Shutdown | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-08 | 2016-04-08
6106 | TACA | Train 1 Level 1 - TACA | Scaffold bench for actuators on train 1 level 1 | 3085 | Dave Dundon | 2016-04-08 | Shutdown | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-08 | 2016-04-08
6106 | TACA | Train 1 Level 1 - TACA | Scaffold bench for actuators on train 1 level 1 | 3085 | Dave Dundon | 2016-04-08 | Shutdown | Med Duty | SHUTDOWN-DISMANTLE | Complete | 2016-04-08 | 2016-04-29
6106 | TACA | TACA Train 1 Shutdown | Dismantle Loading Table on TACA first floor 6106 | 3735 | Mark orr | 2016-04-29 | Chevron | Med Duty | SHUTDOWN-DISMANTLE | Complete | 2016-04-29 | 2016-04-29
6107 | TACA | Train 1 Level 1 - TACA | Heavy duty support bench for actuator in train 1 on level 1 | 3086 | Dave Dundon | 2016-04-08 | Shutdown | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-08 | 2016-04-08
6107 | TACA | Train 1 Level 1 - TACA | Heavy duty support bench for actuator in train 1 on level 1 | 3086 | Dave Dundon | 2016-04-08 | Shutdown | Med Duty | SHUTDOWN-DISMANTLE | Complete | 2016-04-08 | 2016-04-29
6107 | TACA | TACA Train 1 Shutdown | Dismantle Loading Table on TACA first floor 6107 | 3736 | Mark orr | 2016-04-29 | Chevron | Med Duty | SHUTDOWN-DISMANTLE | Complete | 2016-04-29 | 2016-04-29
6108 | TACA | Train 1 Level 1 - TACA | Heavy duty support bench for actuator in train 1 on level 1 | 3087 | Dave Dundon | 2016-04-08 | Shutdown | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-08 | 2016-04-08
6108 | TACA | Train 1 Level 1 - TACA | Heavy duty support bench for actuator in train 1 on level 1 | 3087 | Dave Dundon | 2016-04-08 | Shutdown | Med Duty | SHUTDOWN-DISMANTLE | Complete | 2016-04-08 | 2016-04-29
6108 | TACA | TACA Train 1 Shutdown | Dismantle Loading Table on TACA first floor 6108 | 3737 | Mark orr | 2016-04-29 | Chevron | Med Duty | SHUTDOWN-DISMANTLE | Complete | 2016-04-29 | 2016-04-29
6109 | TACA | Train 1 Ground Level - TACA | Erect scaffold to remove flange bolts on actuator on ground level, train 1. | 3088 | Vim Vyadury | 2016-04-08 | Chevron | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-08 | 2016-04-08
6109 | TACA | TACA Ground level | dismantle Scaffold to access LVC 1510 A. Hertel require to strip off lagging. | 3477 | Adam Stark | 2016-04-22 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-22 | 2016-04-24
6110 | TACA | Train 1 Ground Level - TACA | Erect scaffold to remove flange bolts on actuator on ground level, train 1. | 3089 | Vim Vyadury | 2016-04-08 | Chevron | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-08 | 2016-04-08
6110 | TACA | TACA Ground level | Build Scaffold to access LVC 1510 B. Hertel require to strip off lagging. | 3478 | Adam Stark | 2016-04-22 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-22 | 2016-04-24
6111 | TACA | Train 1 Ground Level - TACA | Erect scaffold to remove flange bolts on actuator on ground level, train 1. | 3090 | Vim Vyadury | 2016-04-08 | Chevron | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-08 | 2016-04-08
6111 | TACA | TACA Ground level | Build Scaffold to access LVC 1510 C. Hertel require to strip off lagging. | 3479 | Adam Stark | 2016-04-22 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-22 | 2016-04-24
6112 | TACA | Train 1 Ground Level - TACA | Erect scaffold supports to land actuator valves on for work bench, train 1. | 3091 | Vim Vyadury | 2016-04-08 | Chevron | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-08 | 2016-04-08
6112 | TACA | Train 1 Ground Level - TACA | Mod scaffold supports to land actuator valves on for work bench, train 1. | 3091 | Vim Vyadury | 2016-04-08 | Chevron | Med Duty | SHUTDOWN-MODIFY | Complete | 2016-04-08 | 2016-04-08
6112 | TACA | Train 1 Ground Level - TACA | Dismantle scaffold supports to land actuator valves on for work bench, train 1. | 3091 | Vim Vyadury | 2016-04-08 | Chevron | Med Duty | SHUTDOWN-DISMANTLE | Complete | 2016-04-08 | 2016-04-30
6113 | TACA | Train 1 Ground Level - TACA | Modify scaffold supports to land actuator on ground level, train 1. | 3092 | Vim Vyadury | 2016-04-08 | Chevron | Med Duty | SHUTDOWN-MODIFY | Complete | 2016-04-08 | 2016-04-08
6113 | TACA | Train 1 Ground Level - TACA | Erect scaffold supports to land actuator on ground level, train 1. | 3092 | Vim Vyadury | 2016-04-08 | Chevron | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-08 | 2016-04-29
6113 | TACA | Train 1 Ground Level - TACA | Dismantle scaffold supports to land actuator on ground level, train 1. | 3092 | Vim Vyadury | 2016-04-08 | Chevron | Med Duty | SHUTDOWN-DISMANTLE | Complete | 2016-04-08 | 2016-04-30
6114 | TACA | Train 1 Ground Level - TACA | Erect scaffold supports to land actuator on ground level, train 1. | 3093 | Vim Vyadury | 2016-04-08 | Chevron | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-08 | 2016-04-08
6114 | TACA | Train 1 Ground Level - TACA | Dismantle 6114 | 3093 | Vim Vyadury | 2016-04-08 | Chevron | Med Duty | SHUTDOWN-DISMANTLE | Complete | 2016-04-08 | 2016-04-29
6114 | TACA | Train 1 Ground Level - TACA | Modify scaffold supports to land actuator on ground level, train 1. | 3093 | Vim Vyadury | 2016-04-08 | Chevron | Med Duty | SHUTDOWN-MODIFY | Complete | 2016-04-08 | 2016-04-29
6115 | TACA | Train 1 Ground Level - TACA | Shutdown works required scaffold, train 1 ground level | 3094 | Colin Maguire | 2016-04-06 | Chevron | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-06 | 2016-04-06
6116 | TAJA | TAJA Level 2 | Shutdown works requre Scaffold - TBA | 3095 | Colin Maguire | 2016-04-03 | Chevron | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-03 | 2016-04-03
6117 | TACA | Train 1 Level 3 - TACA | Shutdown works requre Scaffold - TBA | 3096 | Colin Maguire | 2016-04-03 | Chevron | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-03 | 2016-04-03
6118 | TAFA | TAFA PR Compressor | Shutdown works requre Scaffold - TBA | 3097 | Colin Maguire | 2016-03-30 | Chevron | Med Duty | SHUTDOWN-ERECT | Complete | 2016-03-30 | 2016-03-30
6119 | TAFA | TAFA PR Compressor | Shutdown works requre Scaffold - TBA | 3098 | Colin Maguire | 2016-03-30 | Chevron | Med Duty | SHUTDOWN-ERECT | Complete | 2016-03-30 | 2016-03-30
6120 | TAFA | TAFA PR Compressor | Shutdown works requre Scaffold - TBA | 3099 | Colin Maguire | 2016-03-30 | Chevron | Med Duty | SHUTDOWN-ERECT | Complete | 2016-03-30 | 2016-03-30
6121 | TAFA | TAFA Ground level | Shutdown works requre Scaffold - TBA | 3100 | Colin Maguire | 2016-04-01 | Chevron | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-01 | 2016-04-01
6122 | TACA | Train 1 TOP Level - TACA | Shutdown works requre Scaffold - TBA | 3101 | Colin Maguire | 2016-04-06 | Chevron | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-06 | 2016-04-06
6123 | TACA | Train 1 TOP Level - TACA | Shutdown works requre Scaffold - TBA | 3102 | Colin Maguire | 2016-04-06 | Chevron | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-06 | 2016-04-06
6124 | TACA | Train 1 Level 1 - TACA | Engineered loading bay at TACA Train 1 to Remove Actuators | 3103 | Colin Maguire | 2016-04-09 | Chevron | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-09 | 2016-04-09
6124 | TACA | TR1 1st Level TACA | Dismantle engineered lifting frame and complete gearlist | 3644 | Mark orr | 2016-04-27 | Chevron | Med Duty | DISMANTLE | Not Started | 2016-04-30
6125 | GACA | NE Crn Elev 31 GACA | Hand Rail to be rasied so that an access ladder and be used to install a lighting | 3104 | Bruce Stephenson | 2016-04-08 | Electrical | Med Duty | ERECT | complete | 2016-04-08 | 2016-04-24
6126 | Agru 2 | AGRU 2, RL33 | build scaffold to access and install mercury sample unit. check with SMP supervision on accurate size of build as we may need to factor in where the instrument tubing will run. | 3107 | David Goodes | 2016-04-05 | Mechanical | Med Duty | ERECT | Complete | 2016-04-08 | 2016-04-14
6127 | Agru 3 | Agru 3 sth east Level 1 | Erect Scaffold Platform for access to man way flang of vessel South East side on L1 of Agru 3 Ladder Beam and inertial reel to be installed | 3108 | Andrew Ledingham | 2016-04-10 | Sulzer | Med Duty | ERECT | Complete | 2016-04-10 | 2016-04-10
6128 | Area 10 | Oliver Yard | Dismantle Scaffold old Humpy | 2142 | Matty Hodges | 2016-02-12 | Common User | Med Duty | DISMANTLE | Complete | 2016-02-13 | 2016-02-13
6129 | Condensate Tanks | Condensate Tanks | North end on Bunt Wall at 400NB spool - WO-026 SAH1 | 3110 | Paul Velonias | 2016-04-08 | Mechanical | Med Duty | ERECT | Complete | 2016-04-10 | 2016-04-09
6130 | GAAF | GAAF East side CSU | Scaffold deck for Actuator removal on two Valves on the eastern side of GAAF | 3111 | Lennie Haira | 2016-04-09 | CSU | Med Duty | ERECT | Complete | 2016-04-11 | 2016-04-14
6130 | GAAF | GAAF East side CSU | Scaffold deck for Actuator removal on two Valves on the eastern side of GAAF | 3226 | Lennie Haira | 2016-04-09 | CSU | Med Duty | MODIFY | Complete | 2016-04-11 | 2016-04-20
6131 | Inlet | Inlet Work Shop | Erect frame to support piping 1 | 3112 | Shane Shillabeer | 2016-04-09 | Mechanical | Med Duty | ERECT | Cancelled | 2016-04-10
6132 | Inlet | Inlet Work Shop | Erect frame to support injection pumps 2 | 3113 | Shane Shillabeer | 2016-04-09 | Mechanical | Med Duty | ERECT | Complete | 2016-04-11 | 2016-04-14
6133 | Inlet | Inlet Work Shop | Erect frame to support piping 3 | 3114 | Shane Shillabeer | 2016-04-09 | Mechanical | Med Duty | ERECT | Cancelled | 2016-04-10
6134 | DAAA | South West Stairs - DAAA | Require Encapsulated Work Area For Welding Repair On Hose Cabinet Door | 3115 | Damien Yerkovic | 2016-04-10 | Mechanical | Med Duty | ERECT | Complete | 2016-04-16 | 2016-04-15
6134 | DAAA | Domgas | Dismantle | 4378 | Trevor Pike | 2016-05-16 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-16 | 2016-05-17
6135 | Condensate Tanks | Condensate Tanks 3 & 4 | Bridge over Pipe works & Bunt Wall - Condensate Tanks 3 & 4 | 3116 | Paul Velonias | 2016-04-08 | Mechanical | Med Duty | ERECT | Complete | 2016-04-10 | 2016-04-12
6136 | TAF1 | TAF1 | TAF1 HM-1938 Erect scaffold deck to access horizontal and vertical pipe sections for insulation works. Note 150mm clearance required for insulation. Please call Hertel Scaffold Coordinator to walk job before starting to erect. Tetra 842378 | 3117 | James Halliday | 2016-03-10 | Hertel | Med Duty | ERECT | complete | 2016-04-20 | 2016-04-26
6136 | TAFA | TAFA | Dismantle 6136 | 4414 | Jared Ngaheu | 2016-05-19 | Scaffolding | Med Duty | Dismantle | Not Started | 2016-05-19
6137 | TAF1 | TAF1 | TAF1 HM-1939 Erect scaffold deck on top of steel beams to access pipe work for P2 installation. Line # 1H-41043 & 1H-41057 Note 150mm clearance required for insulation. | 3118 | James Halliday | 2016-04-10 | Hertel | Med Duty | ERECT | complete | 2016-04-21 | 2016-04-26
6137 | TAFA | TAFA | Dismantle 6137 | 4415 | Jared Ngaheu | 2016-05-19 | Scaffolding | Med Duty | Dismantle | Not Started | 2016-05-19
6138 | TAF1 | TAF1 | TAF1 HM-1940 Erect scaffold deck to chase pipe work to give access for P2 installation. Line # 1B-15181 & 1B-15183 Note 150mm clearance required for insulation. | 3119 | James Halliday | 2016-04-10 | Hertel | Med Duty | ERECT | Complete | 2016-04-22 | 2016-04-20
6138 | TAFA | TAFA | Dismantle 6138 | 4413 | Jared Ngaheu | 2016-05-19 | Scaffolding | Med Duty | Dismantle | Not Started | 2016-05-19
6139 | TAF1 | TAF1 | TAF1 HM-1941 Erect scaffold deck to give access for P2 installation. Deck to be same height as grid mesh and extend 1m past pipe elbow. Line # 1B-15187 Note 150mm clearance required for insulation. | 3120 | James Halliday | 2016-04-10 | Hertel | Med Duty | ERECT | Cancelled | 2016-04-22
6140 | TAF1 | TAF1 | TAF1 HM-1942 Erect scaffold deck to give access for P2 installation. Note 150mm clearance required for insulation. | 3121 | James Halliday | 2016-04-10 | Hertel | Med Duty | ERECT | Cancelled | 2016-04-24
6141 | TAG1 | TAG1 | TAG1 HM-1943 Erect scaffold deck to give access for P2 installation. Note 150mm clearance required for insulation. | 3122 | James Halliday | 2016-04-10 | Hertel | Med Duty | ERECT | Complete | 2016-04-24 | 2016-04-30
6142 | SADA | SADA | SADA HM-1935 SASB hook up need to erect frame for chartek works. Remove tubes pinned to beams and keep any standards off sheer keys. One humpy to capture both beams. | 3123 | Felise Emelio | 2016-04-10 | Hertel | Med Duty | ERECT | Complete | 2016-04-17 | 2016-04-11
6143 | SADA | SADA | SADA HM-1936 SASB hook up need to erect frame for chartek works. Keep any standards off sheer keys. As shown to Craig Coombes | 3124 | Felise Emelio | 2016-04-10 | Hertel | Med Duty | ERECT | Complete | 2016-04-18 | 2016-04-11
6144 | SADA | SADA | SADA HM-1944 Sth Est under Fin Fan Lvl Access needed forinstallation of caps for clamps and the application of sealant. | 3125 | Felise Emelio | 2016-04-10 | Hertel | Med Duty | ERECT | Complete | 2016-04-17 | 2016-04-10
6144 | SADA | SADA | Dismantle Scaffold in SADA Bog Compressor tag no: | 3631 | Bob Brevker | 2016-04-26 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-30 | 2016-05-08
6145 | UACA | UACA | Takeover A1645 UACA | 3135 | Adam Stark | 2016-04-10 | Chevron | Med Duty | TAKEOVER | Complete | 2016-04-17 | 2016-04-17
6145 | AAAA | AAAA level 1 central | AAAA HM-1937 level 1 west central need access to complete insulation/cladding works. Keep 225mm clearance from pipe. May need two access points east and west of scaffold. | 3126 | Felise Emelio | 2016-04-10 | Hertel | Med Duty | ERECT | Complete | 2016-04-17 | 2016-04-19
6146 | AAAA | AAAA level 1 central | AAAA HM-1946 level 1 west central need access to complete insulation/cladding works. Keep 225mm clearance from pipe. May need two access points east and west of scaffold. /PAAAA00-1P-11371.01 | 3127 | Felise Emelio | 2016-04-10 | Hertel | Med Duty | ERECT | Complete | 2016-04-19 | 2016-04-19
6147 | AAAA | AAAA level 1 central | AAAA HM-1948 level 1 west central need access to complete insulation/cladding works. Keep 225mm clearance from pipe. May need two access points east and west of scaffold. /PAAAA00-1P-11375.01 | 3128 | Felise Emelio | 2016-04-10 | Hertel | Med Duty | ERECT | Complete | 2016-04-18 | 2016-04-19
6148 | AGRU 3 | AGRU 3, RL33 | Erect scaffold to access pipe support installation on line 3P11260 | 3129 | David Goodes | 2016-04-10 | Mechanical | Med Duty | ERECT | Not Started | 2016-04-14
6153 | UACA | UACA | Dismantle 5996 UACA | 3134 | Adam Stark | 2016-04-10 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-17 | 2016-04-15
6154 | UACA | UACA | Dismantle A1645 UACA | 3135 | Adam Stark | 2016-04-10 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-17 | 2016-05-19
6157 | Condensate Tanks | SR3138-Bund wall Northern end of Condensate Tank | Access for platform North West corner (Outside) wall | 3138 | Paul Velonias | 2016-04-08 | Mechanical | Med Duty | ERECT | Complete | 2016-04-10 | 2016-04-18
6157 | SAH1 | 6157 - SAH1 adjacent condensate pumps outside north bund wall | Modify and extend existing scaffold 6157 outside north bund wall adjacent condensate pumps to allow for cable ladder and cable installation. Please see attached 3D model shot. Please call Glenn Beckett to walk through job prior to starting. | 4287 | Glenn Beckett | 2016-05-13 | Mechanical | Med Duty | MODIFY | Not Started | 2016-05-20
6157 | SAH1 | SAH1 adjacent condensate pumps outside north bund wall | Modify existing scaffold 6157 outside north bund wall adjacent condensate pumps to allow for cable ladder, support bracket and cable installation. Please call Glenn Beckett 842776 to walk through job prior to starting. | 4510 | Glenn Beckett | 2016-05-23 | Mechanical | Med Duty | MODIFY | Not Started | 2016-05-28
6158 | Agru 3 | Agru 3 Level 1 | erect scaffold to access pipe flange attached to vessel on level 1 agru 3 South East | 3139 | Mark Orr | 2016-04-11 | Hertel | Med Duty | ERECT | Complete | 2016-04-12 | 2016-04-11
6159 | SAGB | SAGB top level | Takover I 2803 | 3141 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-18
6160 | SAGB | SAGB top level | Takover I 2800 | 3142 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-18
6161 | SAGB | SAGB top level | Takover I 3046 | 3143 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-19
6162 | Condensate Tanks | Condensate Tanks | Build 1x mobile scaffolds that can be lifted by cranes | 3144 | Carl Seyb | 2016-04-12 | Mechanical | Med Duty | ERECT | complete | 2016-04-12 | 2016-04-28
6163 | Condensate Tanks | Condensate Tanks | Build 1x mobile scaffolds that can be lifted by cranes | 3145 | Carl Seyb | 2016-04-12 | Mechanical | Med Duty | ERECT | complete | 2016-04-12 | 2016-04-28
6164 | SAH | SAH | Takeover 2225 | 3146 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-19
6165 | UACA | UACA | Take over A1779 UACA | 3136 | Adam Stark | 2016-04-10 | Chevron | Med Duty | TAKEOVER | Complete | 2016-04-17 | 2016-04-17
6165 | UACA | UACA | Dismantle A1779 UACA | 3136 | Adam Stark | 2016-04-10 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-17 | 2016-05-19
6165 | Condensate Tanks | Condensate Tanks | Takeover 2632 - I 2634 | 3147 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-12 | 2016-04-26
6166 | UACA | UACA | Dismantle A2054 UACA | 3137 | Adam Stark | 2016-04-10 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-17 | 2016-04-17
6166 | UACA | UACA | Takeover A2054 UACA | 3137 | Adam Stark | 2016-04-10 | Chevron | Med Duty | TAKEOVER | Complete | 2016-04-17 | 2016-04-17
6166 | SATE | SAT | Takeover 2909 | 3148 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-19
6166 | UACA | UACA | Dismantle Scaffold | 4314 | Trevor Pike | 2016-05-14 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-15 | 2016-05-17
6167 | SASN | SASN | Takeover 1948 | 3149 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-17
6168 | DAAA | DAFA | Takeover I 954 | 3150 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-17
6169 | SAF1 | SAF1 | Takeover I 3026 | 3151 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-16
6170 | SAF1 | SAF1 | Takeover I 1983 | 3152 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-16
6171 | SAH1 | SAH1 Condensate tank skid | Takeover I 2179 | 3153 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-16
6172 | SAH1 | SAH1 Condensate tank skid | Takeover i2547 | 3154 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-17
6173 | SAH1 | SASM - SAH1 | Takeover i1268 | 3155 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-17
6174 | SAH1 | SAH1 Condensate tank 2 skid | Takeover i2475 | 3156 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-18
6175 | SAH1 | SAH1 Condensate tank 2 skid | Takeover i2476 | 3157 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-18
6176 | SAH1 | SAH1 Condensate tank 2 skid | Takeover i2477 | 3158 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-18
6177 | SAH1 | SAH1 Condensate tank 2 skid | Takeover i2016 | 3159 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-18
6178 | SAH1 | SAH1 Condensate tank 2 skid | Takeover i2639 | 3160 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-18
6179 | SAH1 | SAH1 Condensate tank 2 skid | Takeover i2632 | 3161 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-17
6179 | SAH1 | SAH1 Condensate tank 2 skid | Takeover i2632 | 3161 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-04-12
6180 | SAH1 | SAH1 Condensate tank 2 skid | Takeover i1608 | 3162 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-18
6181 | SAH1 | SAH1 Condensate tank 2 skid | Takeover i2732 | 3163 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-19
6182 | SAH1 | SAH1 Condensate tank 2 skid | Takeover i1860 | 3164 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-18
6183 | SARA | SARA | Takeover i871 | 3165 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-15
6184 | SARA | SARA | Takeover i1668 | 3166 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-15
6185 | SARA | SARA | Takeover i2110 | 3167 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-16
6186 | SARA | SARA | Takeover i2384 | 3168 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-16
6187 | SARA | SARA on Skid | Takeover i1609 | 3169 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-16
6188 | SAF1 | SAF1 | Takeover i2969 | 3170 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-15
6189 | SAF1 | UAEB | Takeover i2970 | 3171 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-15
6190 | SAF1 | UAEB | Takeover i2470 | 3172 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-12
6191 | MAJ2 | South East Tank 2 | Takeover i2927 | 3173 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-19
6192 | SAF1 | South East Tank 2 / BEHIND BOG FLARES | Takeover i2582 | 3174 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-19
6193 | SAF1 | SAF1 BEHIND BOG FLARES | Takeover GW162 - UNDER THIS TAG NO: I 2971 | 3175 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-19
6194 | LNG Tank 1 | LNG Tank 1VAAA | Takeover i2128 | 3176 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-19
6195 | SAP | RBFD / E North | Takeover A1019 | 3177 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-18
6196 | SAP | RBFD / E North | Takeover A1016 | 3178 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-14
6197 | SAP | RBFC / FD North | Takeover A1015 | 3179 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-19
6198 | SAP | RBFB / C North | Takeover A1012 - I2879 | 3180 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-12 | 2016-04-26
6199 | SASD | SASD | Takeover GW158 NOT THIS TAG ANYMORE - USETHIS ONE I 3074 | 3181 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-21
6200 | SAP | RBFB | Takeover i2821 - I 1813 | 3182 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-19
6201 | SAP | RBFB | Takeover GW654 - 2506 | 3183 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-19
6202 | SASD | SASD | Takeover i2990 - I1154 | 3184 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-21
6203 | SASC | SASC | Takeover i1202 - 657 | 3185 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-21
6204 | SASD | SASD | Takeover NOT UDNER THIS TAG GW273 - USE THIS ONE i3072 | 3186 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-21
6205 | SASG | SASG by sada toilets to access lagging for hertel | Takeover A1013 - USE TAG NO: 859 | 3187 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-18
6206 | SAP | Area 9 | Takeover i1950 Stairs | 3188 | Joel Gray | 2016-04-12 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-12 | 2016-04-19
6207 | GAH1 | GAH1 | Deck to be built to access line no PGAH 400-OE-09881.01 ub system 09LOO-01 | 3189 | Charlie Bryce | 2016-04-13 | Mechanical | Med Duty | ERECT | Complete | 2016-04-13 | 2016-04-16
6208 | TACA | Train 1 TACA | Erect Humpy and Encapsulate for Trades to Grind tags from Vessels | 3190 | George Fomin | 2016-04-14 | Chevron | Med Duty | ERECT | Complete | 2016-04-14 | 2016-04-18
6209 | AGRU 3 | Agru 3 RL | Erect scaffold deck to access pipe 3p11261 and 2P11262 | 3191 | David Goodes | 2016-04-15 | Mechanical | Med Duty | ERECT | Not Started | 2016-04-15
6210 | DAAA | Dom Gas LVL 1 sth end | Dom gas Area first level south end middle of substation | 3192 | Craig Coombe | 2016-04-15 | Scaffolding | Med Duty | ERECT | Not Started | 2016-04-15
6211 | SARA | building 782 at the interim mercury management facility, adjacent to area 10. | Scaffolding required to work over a pit, covered with unrated checkerplate to install conduits and cabling. See attached photos .Location is in building 782 at the interim mercury management facility, adjacent to area 10. | 3194 | Glenn Beckett | 2016-04-13 | Mechanical | Med Duty | ERECT | Complete | 2016-04-13 | 2016-04-22
6211 | SARA | building 782 at the interim mercury management facility, adjacent to area 10. | Scaffolding required to work over a pit, covered with unrated checkerplate to install conduits and cabling. See attached photos .Location is in building 782 at the interim mercury management facility, adjacent to area 10. | 3194 | Glenn Beckett | 2016-04-13 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-04-13 | 2016-04-24
6212 | Area 18 | Inlet - Injection Pumps | Seq86 pump c as per model shot erect deck under flooring and temp handrail for gridmesh removal | 3195 | Shane Shillabeer | 2016-04-11 | Mechanical | Med Duty | ERECT | Complete | 2016-04-12 | 2016-04-12
6213 | Area 18 | Inlet - Injection Pumps | Seq115 pump c as per model shot erect deck under flooring and temp handrail for gridmesh removal | 3196 | Shane Shillabeer | 2016-04-11 | Mechanical | Med Duty | ERECT | Complete | 2016-04-12 | 2016-04-12
6214 | AAAA | AAA3 HM-1949 south/east tag 1071 | Takeover 1070 AAAA | 3198 | Felise Emelio | 2016-04-13 | Hertel | Med Duty | TAKEOVER | complete | 2016-04-18 | 2016-04-18
6215 | AAAA | AAA3 HM-1949 south/east tag 1071 | AAA3 HM-1949 south/east need to extend deck east to allow for insulation works must keep 225mm clearance from pipe including hail rails. | 3198 | Felise Emelio | 2016-04-13 | Hertel | Med Duty | MODIFY | Complete | 2016-04-18 | 2016-04-19
6216 | AAAA | AAA3 HM-1950 south/east tag 1071 | AAA3 HM-1950 east need to extend deck north to allow for insulation works must keep 225mm clearance from pipe including hail rails. | 3199 | Felise Emelio | 2016-04-13 | Hertel | Med Duty | MODIFY | Complete | 2016-04-14 | 2016-04-20
6217 | AAAA | AAA3 HM-1951 east need Tag 1071 | AAA3 HM-1951 east need to add extra deck to complete insulation/cladding works must keep 225mm clearance from pipe including hail rails. | 3200 | Felise Emelio | 2016-04-13 | Hertel | Med Duty | MODIFY | Complete | 2016-04-18 | 2016-04-23
6218 | SADA | SAGA tag 2549 | Remove/ Modify access to allow spade removal and spacer installation Scaffold required to be reinstated as soon as spacer installed to insulate pipe See attached document for Clarity | 3211 | Jeff Menzie | 2016-04-13 | Mechanical | Med Duty | MODIFY | Complete | 2016-03-14 | 2016-04-14
6219 | GAHK | GAHK upper deck | Scaffold deck required for welding - platform pn GAHK upper deck | 3210 | Rick Muston | 2016-04-13 | Mechanical | Med Duty | ERECT | Complete | 2016-03-14 | 2016-04-18
6219 | GAHK | GAHK | Modify scaffold for pipe weld temp spools middle level as per photo | 3474 | Steven Cameron | 2016-04-22 | Mechanical | Med Duty | MODIFY | complete | 2016-04-25 | 2016-04-26
6220 | Agru 3 | ACA3 RL44 | Erect scaffold to access CW and supports on lines ACA3-3A47G03-01, ACA3-3B62410-03, ACA3-3G48AR5-01 | 3209 | David Goodes | 2016-04-12 | Mechanical | Med Duty | ERECT | Cancelled | 2016-03-14
6221 | AGRU 2 | Agru MRU Tank | Install scaffold to accesss installation of vertical cable ladder & Brackets please see request for further details. | 3203 | Geoff Haren | 2016-04-13 | Electrical | Med Duty | ERECT | Complete | 2016-01-15 | 2016-01-15
6221 | AGRU 2 | Agru MRU Tank | Modify scaffold to accesss installation of vertical cable ladder & Brackets please see request for further details. | 3730 | Geoff Haren | 2016-04-28 | Electrical | Med Duty | MODIFY | complete | 2016-05-06 | 2016-04-30
6221 | AGRU 2 | Agru MRU Tank | Modify scaffold to accesss installation of vertical cable ladder & Brackets please see request for further details. | 3730 | Geoff Haren | 2016-04-28 | Electrical | Med Duty | DISMANTLE | Complete | 2016-05-06 | 2016-05-04
6223 | Condensate Tanks | SR3138-Bund wall Northern end of Condensate Tank | Bridge over Pipe works & Bunt Wall - Condensate Tanks 3 & 4 | 3205 | Paul Velonias | 2016-04-12 | Mechanical | Med Duty | ERECT | Cancelled | 2016-03-14
6224 | Agru 3 | ACA3 RL44 | Erect scaffold to access CW5 & CW6 on line ACA3-3B11523-01 | 3207 | David Goodes | 2016-04-12 | Mechanical | Med Duty | ERECT | Cancelled | 2016-03-14
6225 | Agru 3 | ACA3 RL44 | Erect scaffold to access CW on lines ACA3-3P11267-02, ACA3-3P11268-01, ACA3-3H11024-02 | 3208 | David Goodes | 2016-04-12 | Mechanical | Med Duty | ERECT | Cancelled | 2016-03-14
6227 | GAA1 | GAA1 | Takeover / Re-instate scaffold H 1896 | 3215 | John Pouroula | 2016-04-13 | Electrical | Med Duty | TAKEOVER | Complete | 2016-03-14 | 2016-04-19
6227 | GAA1 | GAA1 | DISMANTLE 6227 the Takeover / Re-instate scaffold H 1897 | 3215 | John Pouroula | 2016-04-13 | Electrical | Med Duty | DISMANTLE | Complete | 2016-03-14 | 2016-04-20
6227 | GAA1 | GAA1 | Raise deck to the same height as Tag 5810 next to this scaffold | 3215 | John Pouroula | 2016-04-13 | Electrical | Med Duty | MODIFY | Complete | 2016-03-14 | 2016-04-20
6228 | SADA | SADA, inlet guide vane scaffold stradling BOG compressor 3401 and 3402 | Strip 2of jump up scaffolds at SADA module used to access the IGV controller. These need to be stripped to allow commissioing to progress | 3216 | Boyd Edwards | 2016-04-13 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-14 | 2016-04-14
6228 | SADA | SADA, inlet guide vane scaffold stradling BOG compressor 3401 and 3402 | Takeover I3093 | 3216 | Boyd Edwards | 2016-04-13 | Chevron | Med Duty | TAKEOVER | Complete | 2016-03-14 | 2016-04-14
6229 | SADA | SADA, inlet guide vane scaffold stradling BOG compressor 3401 and 3402 | Strip 2of jump up scaffolds at SADA module used to access the IGV controller. These need to be stripped to allow commissioing to progress | 3217 | Boyd Edwards | 2016-04-13 | Chevron | Med Duty | DISMANTLE | Complete | 2016-03-14 | 2016-04-14
6229 | SADA | SADA, inlet guide vane scaffold stradling BOG compressor 3401 and 3402 | Takeover I3092 | 3217 | Boyd Edwards | 2016-04-13 | Chevron | Med Duty | TAKEOVER | Complete | 2016-03-14 | 2016-04-14
6230 | ? | 3V1510 Dustcover | Build Scaffold to access for removal of bolts to take out dust cover plate. Build independent bays on both sides of pipe and hand rail across the top of the | 3218 | Mark orr | 2016-04-14 | Chevron | Med Duty | ERECT | Complete | 2016-03-14 | 2016-04-15
6230 | Train 3 | TR3 3V1510 Dustcover | Dismantle scaffold 6230 on Tr3 | 4073 | Mark orr | 2016-04-30 | Chevron | Med Duty | SHUTDOWN-DISMANTLE | Complete | 2016-04-30 | 2016-05-03
6231 | ? | 3V1510 Dustcover | Build Scaffold to access for removal of bolts to take out dust cover plate. Build independent bays on both sides of pipe and hand rail across the top of the | 3219 | Mark orr | 2016-04-14 | Chevron | Med Duty | ERECT | Complete | 2016-03-14 | 2016-04-15
6231 | Train 3 | TR3 3V1510 Dustcover | Dismantle scaffold 6231 on Tr3 | 4072 | Mark orr | 2016-04-30 | Chevron | Med Duty | SHUTDOWN-DISMANTLE | Complete | 2016-04-30 | 2016-05-03
6232 | TAFA | TAFA Compresso | Erect bottom cassing @ TAFA Compressor | 3220 | Dave Dundon | 2016-04-14 | Scaffolding | Med Duty | ERECT | Complete | 2016-03-14 | 2016-04-13
6232 | TAFA | TAFA Compresso | Erect bottom cassing @ TAFA Compressor | 3220 | Dave Dundon | 2016-04-15 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-03-14 | 2016-04-15
6233 | TAFA | TAFA Compresso | Gin Wheel @ TAFA Compressor | 3221 | Dave Dundon | 2016-04-14 | Scaffolding | Med Duty | ERECT | Complete | 2016-03-14 | 2016-04-13
6233 | TAFA | TAFA Compresso | Gin Wheel @ TAFA Compressor | 3221 | Dave Dundon | 2016-04-15 | Scaffolding | Med Duty | ERECT | Complete | 2016-03-14 | 2016-04-15
6234 | RBDE | RBDE | RBDE HM-1959 00-0P-42052.70 erect scaffold to access insulation works. Deck height on top of pipes. Keeping 225mm clearance around pipe marked in blue. | 3222 | Felise Emelio | 2016-04-14 | Hertel | Med Duty | ERECT | Complete | 2016-04-20 | 2016-04-15
6235 | RBDE | RBDE | RBDE HM-1960 south of module erect scaffold to complete insulation/cladding works. Keep 225mm clearance from pipe. | 3223 | Felise Emelio | 2016-04-14 | Hertel | Med Duty | ERECT | Complete | 2016-04-21 | 2016-05-11
6236 | RBDD | RBDD | RBDD HM-1961 south of module erect scaffold to complete insulation/cladding works. Keep 225mm clearance from pipe. | 3224 | Felise Emelio | 2016-04-14 | Hertel | Med Duty | ERECT | Cancelled | 2016-04-22
6237 | Train 3 | 3V150 Train 3 | Erect Internal Scaffold 3V150 Train 3 | 3227 | Mark orr | 2016-04-14 | Scaffolding | Med Duty | ERECT | complete | 2016-03-14 | 2016-04-16
6237 | Train 3 | 3V150 Train 3 | Dismantled Internal Scaffold 3V150 Train 3 | 3227 | Mark orr | 2016-04-14 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-03-14 | 2016-04-29
6238 | inlet | Inlet injection Pumbs | Erect scaffold to access pump A outlet | 3233 | Shane Shillabeer | 2016-04-14 | Mechanical | Med Duty | ERECT | Complete | 2016-04-15 | 2016-04-23
6239 | Inlet | Inlet injection Pumbs | Erect scaffold to access pump A | 3228 | Shane Shillabeer | 2016-04-14 | Mechanical | Med Duty | ERECT | complete | 2016-04-15 | 2016-04-29
6240 | Inlet | Inlet injection Pumbs | Erect scaffold to access pump B | 3229 | Shane Shillabeer | 2016-04-14 | Mechanical | Med Duty | ERECT | complete | 2016-04-15 | 2016-04-24
6241 | Inlet | Inlet injection Pumbs | Erect scaffold to access pump C | 3230 | Shane Shillabeer | 2016-04-14 | Mechanical | Med Duty | ERECT | Complete | 2016-04-15 | 2016-04-23
6242 | Inlet | Inlet injection Pumbs | Erect scaffold to access pump B inlet butt repair | 3231 | Shane Shillabeer | 2016-04-14 | Mechanical | Med Duty | ERECT | Complete | 2016-04-18 | 2016-04-20
6243 | Inlet | Injection Worksop | Erect scaffold in workshop yard for welding humpy | 3232 | Shane Shillabeer | 2016-04-14 | Mechanical | Med Duty | ERECT | complete | 2016-04-15 | 2016-04-24
6244 | SADA | SADA - East level 1 | errect chevron urgent deck in sada east side lel 1 | 3237 | Mark orr | 2016-04-15 | Chevron | Med Duty | ERECT | Complete | 2016-04-15 | 2016-04-16
6244 | SADA | SADA - East level 1 | Dismantlechevron urgent deck in sada east side lel 1 | 3237 | Mark orr | 2016-04-15 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-15 | 2016-04-30
6244 | SADA | SADA - East level 1 | Dismantle Scaffold in SADA Bog Compressor tag no: | 3629 | Bob Brevker | 2016-04-26 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-30 | 2016-04-30
6245 | SADA | SADA - East level 1 | errect chevron urgent deck in sada east side lel 1 | 3238 | Mark orr | 2016-04-15 | Chevron | Med Duty | ERECT | Complete | 2016-04-15 | 2016-04-17
6245 | SADA | SADA - East level 1 | Modify chevron urgent deck in sada east side lel 1 | 3238 | Mark orr | 2016-04-15 | Chevron | Med Duty | MODIFY | Complete | 2016-04-15 | 2016-04-18
6245 | SADA | SADA | Dismantle Scaffold in SADA Bog Compressor tag no: MAS Tag holder no tag attached | 3626 | Bob Brevker | 2016-04-26 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-30 | 2016-04-30
6245 | SADA | SADA - East level 1 | Dismantle chevron urgent deck in sada east side lel 1 | 3238 | Mark orr | 2016-04-29 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-29 | 2016-04-30
6246 | UACA | UACA | A2032 | 3246 | Chistopher Reachy | 2016-04-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-15 | 2016-04-20
6247 | UACA | UACA | A205 | 3245 | Chistopher Reachy | 2016-04-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-15 | 2016-04-19
6248 | UACA | UACA | A1685 STAIR TOWER TO ACCESS 3 LAGGING LINES FOR HERTEL | 3244 | Chistopher Reachy | 2016-04-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-15 | 2016-04-20
6249 | UACA | UACA | A2170 | 3243 | Chistopher Reachy | 2016-04-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-15 | 2016-04-20
6249 | UACA | UACA | Dismantle Scaffold | 4312 | Trevor Pike | 2016-05-14 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-15 | 2016-05-19
6249 | UACA | UACA | Modifiy the takeover to be useable | 3243 | Chistopher Reachy | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-04-15 | 2016-04-20
6250 | UACA | UACA | A1771 | 3242 | Chistopher Reachy | 2016-04-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-15 | 2016-04-20
6251 | UACA | UACA | A1910 | 3241 | Chistopher Reachy | 2016-04-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-15 | 2016-04-17
6252 | UACA | UACA | A705 | 3240 | Chistopher Reachy | 2016-04-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-15 | 2016-04-17
6253 | UACA | UACA | A1085 | 3239 | Chistopher Reachy | 2016-04-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-15 | 2016-04-20
6254 | UACA | UACA | A2336 | 3253 | Chistopher Reachy | 2016-04-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-15 | 2016-04-19
6254 | UACA | UACA | A2336 | 3253 | Chistopher Reachy | 2016-04-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-15 | 2016-04-19
6255 | UACA | UACA | A2218 | 3252 | Chistopher Reachy | 2016-04-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-15 | 2016-04-17
6256 | UACA | UACA | A1772 | 3251 | Chistopher Reachy | 2016-04-15 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-15
6257 | UACA | UACA | A1775 ADD 1800X1200 | 3250 | Chistopher Reachy | 2016-04-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-04-15 | 2016-04-20
6257 | UACA | UACA | A1775 | 3250 | Chistopher Reachy | 2016-04-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-15 | 2016-04-20
6258 | UACA | UACA | A2324 | 3249 | Chistopher Reachy | 2016-04-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-15 | 2016-04-20
6258 | UACA | UACA | Dismantle | 3249 | Chistopher Reachy | 2016-04-15 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-04-15 | 2016-05-17
6258 | UACA | UACA | A2324 | 3249 | Chistopher Reachy | 2016-04-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-15 | 2016-05-17
6258 | UACA | UACA | Dismantle Scaffold | 4313 | Trevor Pike | 2016-05-14 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-15 | 2016-05-19
6259 | GAGA | Level 2 GAGA | Erect build 2meter humpy for encapulation for removal of lugs | 3257 | Charlie Bryce | 2016-04-15 | Mechanical | Med Duty | ERECT | Complete | 2016-04-17 | 2016-04-17
6260 | TAJD | train 1 TAJD | fitt and weld 4'' drain line and pipe supports in train1 tajd | 3256 | Mike Knott | 2016-04-15 | Electrical | Med Duty | ERECT | Complete | 2016-04-17 | 2016-05-01
6260 | TAJD | Train 1 - TAJD | extend scaff deck past round collumn to allow for pipe cut and weld note this smp work is TQ and was not in the original scope | 4282 | Mike Knott | 2016-05-12 | Electrical | Med Duty | MODIFY | Complete | 2016-05-12 | 2016-05-26
6261 | Agru 2 | agru 2 | fitt and weld 3 of 2'' utility lines require the same set up as AGRU 2 | 3254 | Mike Knott | 2016-04-15 | Electrical | Med Duty | ERECT | complete | 2016-04-22 | 2016-04-26
6262 | GACA | GACA 1st level NE cnr | we require access to inspect fire system beacon 060UB2056R mounted on top of pole near hand rail see marked up drawing G1-TD-J-6000-GAD0122 | 3258 | Bruce Stephenson | 2016-04-15 | Mechanical | Med Duty | ERECT | complete | 2016-04-17 | 2016-04-29
6263 | GAGA | Top Level GAGA | Dismantle scaffold top level GAGA tag 5677 double up of tag 5677 | 3259 | Charlie Bryce | 2016-04-15 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-04-17 | 2016-03-21
6264 | SADA | SADA east sdie | Erect scaffold to trungeon for SMP to access bolts | 3260 | Jared Ngaheu | 2016-04-15 | Scaffolding | Med Duty | ERECT | Complete | 2016-04-17 | 2016-04-18
6264 | SADA | SADA east sdie | Erect scaffold to trungeon for SMP to access bolts | 3260 | Jared Ngaheu | 2016-04-15 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-04-17 | 2016-04-20
6265 | GAA1 | GAA1 | Erect scaffold at ground level west side of GAA1 at access installation of pipe supports | 3261 | Charlie Bryce | 2016-04-15 | Mechanical | Med Duty | ERECT | Complete | 2016-04-17 | 2016-04-20
6266 | INLET | Inlet injection Pumps | Erect scaffold to access fans at A pump | 3262 | Shane Shillabeer | 2016-04-16 | Mechanical | Med Duty | ERECT | complete | 2016-04-17 | 2016-04-18
6267 | SADA | SADA - 3rd Level | Dismantle mobile scaffold | 3268 | Mark Orr | 2016-04-15 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-04-17 | 2016-04-15
6268 | SADA | SADA - Top level | Dismantle top level of SADA | 3267 | Mark Orr | 2016-04-15 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-04-17 | 2016-04-15
6269 | INLET | Inlet injection Pumps | Erect scaffold to access fans at B pump | 3265 | Shane Shillabeer | 2016-04-17 | Mechanical | Med Duty | ERECT | complete | 2016-04-18 | 2016-04-21
6270 | INLET | Inlet injection Pumps | Erect scaffold to access fans at C pump | 3266 | Shane Shillabeer | 2016-04-16 | Mechanical | Med Duty | ERECT | complete | 2016-04-17 | 2016-04-21
6271 | DAAA | DAAA | Replace V Cone Flow Element with an oriface plate | 3263 | Murray Tartaglia | 2016-04-15 | Mechanical | Med Duty | ERECT | Not Started | 2016-04-17
6272 | Inlet | Pig Receiver | Takeover Scaffold TAG NO: H1225 | 3269 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-19
6273 | Inlet | Pig Receiver | Takeover Scaffold TAG NO: H1655 | 3270 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-19
6274 | Inlet | Pig Receiver | Takeover Scaffold TAG NO: H1519 | 3271 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-19
6275 | RBAL-RBAK | Inlet | Modify Takeover Scaffold TAG NO: G0757 - G1309 - G0039 - G0032 - G0176 | 3272 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | MODIFY | Complete | 2016-04-16 | 2016-05-21
6275 | RBAL-RBAK | Inlet | Takeover Scaffold TAG NO: G0757 - G1309 - G0039 - G0032 - G0176 | 3272 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-05-21
6276 | jada | JADA GROUND | Takeover Scaffold TAG NO: g1017 | 3273 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-23
6277 | RBAL | RBAL - Inlet | Takeover Scaffold TAG NO: H1591 | 3274 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-18
6277 | RBAL | RBAL - Inlet | Modify the take over of H1591 - G879 | 3274 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | MODIFY | Complete | 2016-04-16 | 2016-04-24
6278 | RBAB | RBAB | Takeover Scaffold TAG NO: h2095 | 3275 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-23
6279 | RBAA | RBAA - RBAC | Takeover Scaffold TAG NO: 1120 | 3276 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-23
6280 | RBAA | RBAA - RBAC | Takeover Scaffold TAG NO: 1116 | 3277 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-03-29
6281 | RBAB | RBAB - TAG 1095 | Takeover Scaffold TAG NO: 1095 | 3278 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-03-29
6282 | RBAB | RBAB | Takeover Scaffold TAG NO: 1094 | 3279 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-03-29
6283 | RBAE | RBAE | Takeover Scaffold TAG NO: H 2068 | 3280 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-24
6284 | GAA1 | GAA1 INLET CAGE -EASTERN CAGE | Takeover Scaffold TAG NO: H1841 | 3281 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-24
6285 | GAA1 | GAA1 INLET | Takeover Scaffold TAG NO: H2061 | 3282 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-24
6285 | SAH1 | Condi tanks east wall SAH1 | Existing scaffold requires modification to install cable ladders to the east wall. Please call Glenn Beckett 842776 for information. | 4535 | Glenn Beckett | 2016-05-25 | Mechanical | Med Duty | MODIFY | Not Started | 2016-06-01
6286 | GAA1 | GAA1 INLET CAGE -EASTERN CAGE | Takeover Scaffold TAG NO: H1840 | 3283 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-24
6287 | RBAC | RCAC | Takeover Scaffold TAG NO: 3284 / G1305 | 3284 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-24
6288 | RBAC | RCAC | Takeover Scaffold TAG NO: 3285 / 1114 | 3285 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-24
6289 | RBAC | RBAC | Takeover Scaffold TAG NO: 1093 | 3286 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-03-29
6290 | RBAH | RBAH | Takeover Scaffold TAG NO: H1431 | 3287 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-16 | 2016-04-24
6291 | GACA | GACA | Takeover Scaffold TAG NO: G1636 | 3288 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-16 | 2016-04-26
6292 | RBAJ | RBAJ | Takeover Scaffold TAG NO: G463 | 3289 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-16 | 2016-04-29
6293 | RBAJ | nother / South piperack | Takeover Scaffold TAG NO: G1452 | 3290 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-05-21
6294 | SITEWIDE - TBA | Site Wide | Takeover Scaffold TAG NO: | 3291 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-05-08
6295 | SITEWIDE - TBA | Site Wide | Takeover Scaffold TAG NO: | 3292 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-05-08
6296 | SITEWIDE - TBA | Site Wide | Takeover Scaffold TAG NO: H 1778 | 3293 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-05-12
6297 | SITEWIDE - TBA | Site Wide | Dismantle Scaffold TAG NO: H1993 / DNC 6297 | 3294 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-04-16 | 2016-05-12
6297 | SITEWIDE - TBA | Site Wide | Takeover Scaffold TAG NO: h 1993 | 3294 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-05-12
6298 | RBAE | Inlet | Takeover Scaffold TAG NO: H1776 | 3295 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-05-18
6299 | RBAE | Inlet | Modify Scaffold TAG NO: H1775 | 3296 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | MODIFY | Complete | 2016-04-16 | 2016-05-19
6299 | RBAE | Inlet | Takeover Scaffold TAG NO: H1775 | 3296 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-05-19
6300 | RBAE | Site Wide | Modify Scaffold TAG NO: H-1774 | 3297 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | MODIFY | Complete | 2016-04-16 | 2015-05-19
6300 | RBAE | Site Wide | Takeover Scaffold TAG NO: H-1774 | 3297 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2015-05-19
6301 | RBAE | Inlet | Modify scaffold to access | 3298 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | MODIFY | Complete | 2016-04-16 | 2016-05-18
6301 | RBAE | Inlet | Takeover Scaffold TAG NO: H1773 | 3298 | Jamie Macmimi | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-05-18
6302 | SAHA | Condy tanks | Takeover Scaffold TAG NO: I 2637 | 3299 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-18
6303 | SITEWIDE - TBA | Site Wide | Takeover Scaffold TAG NO:I 2478 | 3300 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-18
6304 | Condensate Tanks | Condy tank 2 nth east crn | Takeover Scaffold TAG NO:i2659 | 3301 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-18
6305 | SAHA | Site Wide | Takeover Scaffold TAG NO: I 2637 | 3302 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-18
6306 | SITEWIDE - TBA | Site Wide | Takeover Scaffold TAG NO: I 2094 | 3303 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-18
6307 | Condensate Tanks | Tank 3 | Takeover Scaffold TAG NO: 1080 | 3304 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-18
6308 | Condensate Tanks | tank 3 west | Takeover Scaffold TAG NO: 1153 | 3305 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-18
6309 | SITEWIDE - TBA | Site Wide | Takeover Scaffold TAG NO: I 2218 | 3306 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-18
6310 | SADA | SADA level 3 East face | Takeover Scaffold TAG NO: i3079 | 3307 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-23
6310 | SADA | SADA | Dismantle Scaffold in SADA Bog Compressor 6310 | 3623 | Bob Brevker | 2016-04-25 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-27 | 2016-04-25
6311 | SADA | SADA level 3 East face | Takeover Scaffold TAG NO: i2942 | 3308 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-23
6311 | SADA | SADA | Dismantle Scaffold in SADA Bog Compressor tag no: i2942 | 3625 | Bob Brevker | 2016-04-26 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-30 | 2016-05-03
6312 | SADA | Level 2 | Takeover Scaffold TAG NO: I 1039 | 3309 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-23
6312 | SADA | SADA | Dismantle Scaffold in SADA Bog Compressor tag no: | 3640 | Bob Brevker | 2016-04-27 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-30 | 2016-05-03
6313 | SADA | Level 2 | Takeover Scaffold TAG NO: I 3081 | 3310 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-23
6313 | SADA | SADA | Dismantle Scaffold in SADA Bog Compressor tag no: | 3636 | Bob Brevker | 2016-04-27 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-30 | 2016-04-27
6314 | SADA | S/W crn | Takeover Scaffold TAG NO: I 1030 & I 1031 | 3311 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-23
6315 | SADA | Site Wide | Takeover Scaffold TAG NO: I 1030 & I 1031 | 3312 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-23
6315 | SADA | SADA | Dismantle Scaffold in SADA Bog Compressor tag no: | 3637 | Bob Brevker | 2016-04-27 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-30 | 2016-05-07
6316 | SADA | Site Wide | Takeover Scaffold TAG NO: I 2920 | 3313 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-23
6316 | SADA | SADA | Dismantle Scaffold in SADA Bog Compressor tag no: | 3634 | Bob Brevker | 2016-04-26 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-30 | 2016-05-08
6317 | SADA | Site Wide | Takeover Scaffold TAG NO: I 3045 | 3314 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-23
6317 | SADA | SADA | Dismantle Scaffold in SADA Bog Compressor tag no: | 3632 | Bob Brevker | 2016-04-26 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-30 | 2016-04-26
6318 | SADA | Site Wide | Takeover Scaffold TAG NO: no tag MAS holder tho | 3315 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-23
6318 | SADA | SADA | Dismantle Scaffold in SADA Bog Compressor tag no: | 3630 | Bob Brevker | 2016-04-26 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-30 | 2016-04-30
6319 | SADA | Site Wide | Takeover Scaffold TAG NO: no tag MAS holder tho | 3316 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-23
6319 | SADA | SADA | Dismantle Scaffold in SADA Bog Compressor tag no: i3060 | 3627 | Bob Brevker | 2016-04-26 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-30 | 2016-05-01
6320 | SADA | Site Wide | Takeover Scaffold TAG NO: I 3060 | 3317 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-23
6320 | SADA | SADA | Dismantle Scaffold in SADA Bog Compressor tag no: | 3639 | Bob Brevker | 2016-04-27 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-30 | 2016-04-30
6321 | SADA | Site Wide | Takeover Scaffold TAG NO: I 2860 | 3318 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-23
6321 | SADA | SADA | Dismantle Scaffold in SADA Bog Compressor tag no: | 3638 | Bob Brevker | 2016-04-27 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-30 | 2016-05-03
6322 | SADA | Site Wide | Takeover Scaffold TAG NO: i2841 | 3319 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-23
6322 | SADA | SADA | Dismantle Scaffold in SADA Bog Compressor tag no: i2841 | 3624 | Bob Brevker | 2016-04-26 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-30 | 2016-05-03
6323 | SADA | Site Wide | Takeover Scaffold TAG NO: I 3061 | 3320 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-16 | 2016-04-23
6323 | SADA | Site Wide | Modfiy Scaffold 6323 | 3320 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | MODIFY | complete | 2016-04-16 | 2016-04-30
6323 | SADA | Site Wide | DismantleScaffold 6323 | 3320 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-04-16 | 2016-05-01
6323 | SADA | SADA | Dismantle Scaffold in SADA Bog Compressor tag no: | 3635 | Bob Brevker | 2016-04-27 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-30 | 2016-05-01
6324 | SADA | SADA lagging accesss level | Takeover Scaffold TAG NO: i1041 | 3321 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-19
6325 | SADA | SADA lagging accesss level 1 | Takeover Scaffold TAG NO: i1042 | 3322 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-19
6325 | SADA | SADA lagging accesss level 1 | Takeover Scaffold TAG NO: i1042 | 3322 | Jared Ngaheu | 2016-04-16 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-04-16 | 2016-05-03
6326 | SADA | SADA | Takeover Scaffold TAG NO: I 1073 | 3323 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-19
6326 | SADA | SADA | Takeover Scaffold TAG NO: I 1073 | 3323 | Jared Ngaheu | 2016-04-16 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-04-16 | 2016-05-03
6327 | SADA | SADA | Modify Takeover Scaffold TAG NO: i2888 | 3324 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | MODIFY | complete | 2016-04-16 | 2016-04-19
6327 | SADA | SADA | Takeover Scaffold TAG NO: i2888 | 3324 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-16 | 2016-04-19
6327 | SADA | SADA | Dismantle | 3324 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-04-16 | 2016-05-21
6327 | SADA | SADA East Side, Near Road | Dismantle Scaffold - All works completed | 3413 | Wayne McCarthy | 2016-04-21 | Mechanical | Med Duty | Erect | Not Started | 2016-04-27
6328 | SADA | Site Wide | Takeover Scaffold TAG NO: I 3060 | 3325 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-23
6328 | SADA | SADA | Dismantle Scaffold in SADA Bog Compressor tag no: | 3628 | Bob Brevker | 2016-04-26 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-30 | 2016-04-30
6329 | SADA | SADA | Takeover Scaffold TAG NO:mas tag holder no number | 3326 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-16 | 2016-04-19
6330 | Area 8 | LNG Tank 2 | Takeover Scaffold TAG NO:1051 | 3327 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-23
6331 | SADA |  | Takeover Scaffold TAG NO: I 1013 | 3328 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-23
6332 | SAH | Utilities LNG tank ground level | Takeover Scaffold TAG NO: i2857 | 3329 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-21
6333 | RBFB | RBFB west of lng 2 | Takeover Scaffold TAG NO: i2821 | 3330 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-21
6334 | AREA 8 | UTILITIES LNG TANK 2 LOWER DECK EAST SIDE | Takeover Scaffold TAG NO: 919 | 3331 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-16 | 2016-04-21
6335 | SAH | Utilities LNG tank 1 top Centre | Takeover Scaffold TAG NO: 918 | 3332 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-21
6336 | SAH | Utilities LNG tank 1 top Centre | Takeover Scaffold TAG NO: 886 | 3333 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-21
6337 | SAH | Utilities LNG tank 1 top eastern landing | Takeover Scaffold TAG NO: 1201 | 3334 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-21
6338 | SAH | Utilities LNG tank 1 lower level eastern face | Takeover Scaffold TAG NO: | 3335 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-21
6339 | GAEA | GAEA | Takeover Scaffold TAG NO: A2361 | 3336 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-16 | 2016-04-24
6340 | Area 10 | mech Work Shop container cyclone prep - Area10 | Takeover Scaffold TAG NO: 970 | 3337 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-21
6341 | Area 10 | mech Work Shop container cyclone prep - Area11 | Takeover Scaffold TAG NO: 971 | 3338 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-21
6342 | Area 10 | mech Work Shop container cyclone prep - Area11 | Takeover Scaffold TAG NO:954 | 3339 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-21
6343 | Area 10 | mech Work Shop container cyclone prep - Area11 | Takeover Scaffold TAG NO: 956 | 3340 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-21
6344 | Area 10 | Court Yard Humpy | Takeover Scaffold TAG NO: 689 | 3341 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-21
6345 | Area 10 | Court Yard Humpy | Takeover Scaffold TAG NO: 574 | 3342 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-21
6346 | Area 10 | mech Work Shop container cyclone prep - Area11 | Takeover Scaffold TAG NO: 742 | 3343 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-21
6347 | Area 10 | Zrigging store | Takeover Scaffold TAG NO:575 | 3344 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-21
6348 | Agru 2 | Level 1 S/E cable tray access | Takeover Scaffold TAG NO: 1381 mas | 3345 | Joel Gray | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-22
6349 | Area 10 | Boiler workshop | Takeover Scaffold TAG NO: 703 | 3346 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-21
6350 | MOF | SASF | Takeover Scaffold TAG NO: 269 | 3347 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-16 | 2016-04-24
6351 | TBAA | level 1 | Takeover Scaffold TAG NO: intrim 2P12022 | 3348 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-24
6351 | TBAA | level 1 | Dismantle | 3348 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-04-16 | 2016-05-17
6352 | TBAA | Level 1 Hydro 2P13001 Valve access | Takeover Scaffold TAG NO: intrim | 3349 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-16 | 2016-04-28
6352 | TBAA | Level 1 Hydro 2P13001 Valve access | Dismantle | 3349 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-04-16 | 2016-05-17
6353 | TBAA | level 3 N/E light | Takeover Scaffold TAG NO: 621 | 3350 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | ERECT | Complete | 2016-04-16 | 2016-04-23
6353 | TBBA | TBAA VESSEL 2V-1201 TRAIN 2 | As per attached model shots and scaffold tag numbers. | 4225 | Brett Taane | 2016-05-11 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-14 | 2016-05-16
6354 | TBAA | Level 12 N/E confine space | Takeover Scaffold TAG NO: 622 | 3351 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | ERECT | Complete | 2016-04-16 | 2016-04-21
6354 | TBBA | TBAA VESSEL 2V-1201 TRAIN 2 | As per attached model shots and scaffold tag numbers. | 4226 | Brett Taane | 2016-05-11 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-14 | 2016-05-22
6355 | SITEWIDE - TBA | Site Wide | Takeover Scaffold TAG NO: | 3352 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-04-16
6356 | TBBA | Level 1 south | Takeover Scaffold TAG NO: intrim Reboilers | 3353 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-23
6356 | TBBA | TBBA TRAIN 2 RE-BOILERS | As per attached model shots and scaffold tag numbers. | 4221 | Brett Taane | 2016-05-11 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-14 | 2016-05-15
6357 | SITEWIDE - TBA | Site Wide | Takeover Scaffold TAG NO: | 3354 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-23
6357 | TBBA | TBBA TRAIN 2 RE-BOILERS | As per attached model shots and scaffold tag numbers. | 4217 | Brett Taane | 2016-05-11 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-14 | 2016-04-23
6358 | TBBA | Site Wide | Takeover Scaffold TAG NO: | 3355 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-04-23
6358 | TBBA | Train2 | Dismantle | 3355 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-04-16 | 2016-05-15
6359 | SITEWIDE - TBA | Site Wide | Takeover Scaffold TAG NO: | 3356 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-04-16
6360 | SITEWIDE - TBA | Train2 | Takeover Scaffold TAG NO: | 3357 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-16 | 2016-03-23
6361 | SITEWIDE - TBA | Site Wide | Takeover Scaffold TAG NO: | 3358 | Chistopher Reachy | 2016-04-16 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-16 | 2016-04-24
6362 | SADA | SADA | SADA HM-1974 Need to dismantle scaffold to allow works on bottom flange. HM-248 | 3360 | Felise Emelio | 2016-04-16 | Hertel | Med Duty | DISMANTLE | Complete | 2016-04-24 | 2016-04-17
6363 | SADA | SADA | SADA HM-1974 level 2 west Need to dismantle scaffold. HM-249 | 3361 | Felise Emelio | 2016-04-16 | Hertel | Med Duty | DISMANTLE | Complete | 2016-04-24 | 2016-04-16
6363 | SADA | SADA | SADA HM-1974 level 2 west Need to dismantle scaffold. HM-249 | 3361 | Felise Emelio | 2016-04-16 | Hertel | Med Duty | DISMANTLE | Complete | 2016-04-24 | 2016-04-17
6364 | TAF1 | TAF1 | Scaffold required in train1 PR turbine enclosure auxiliary compartment, east side of turning gear motor to reach light fitting above void in grid mesh | 3362 | Mike Hemming | 2016-04-14 | Chevron | Med Duty | ERECT | Complete | 2016-04-17 | 2016-04-17
6366 | ACAG | AGRU 3 underside of RV platform - ACAG | scaffold required to install flat bar gridmesh support and electrical supports,posts and cable tray. please build the same as what is currantly @ AGRU 2 | 3364 | Mike Knott | 2016-04-17 | Mechanical | Med Duty | Erect | Not Started | 2016-04-24
6367 | inlet | Gorgon slug catcher north end | Please reomove scaffold to tanks so they can be transorted away on the 20thThese will be getting pumped out During the day on the 19th so will still require the access till night shift that night. 6102 | 3365 | Todd Lyons | 2016-04-17 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-04-19 | 2016-03-21
6368 | GAA1 | Inlet injection Pumps | Erect Scaffold to access outlet spool at A pump | 3366 | Shane Shillabeer | 2016-04-17 | Mechanical | Med Duty | ERECT | complete | 2016-04-18 | 2016-04-24
6369 | GAA1 | Inlet injection Pumps | Erect Scaffold to access outlet spool at B pump | 3367 | Shane Shillabeer | 2016-04-17 | Mechanical | Med Duty | ERECT | complete | 2016-04-18 | 2016-04-29
6370 | GAA1 | Inlet injection Pumps | Erect Scaffold to access outlet spool at C pump | 3368 | Shane Shillabeer | 2016-04-17 | Mechanical | Med Duty | ERECT | complete | 2016-04-18 | 2016-05-19
6371 | GADA | SR3371 - First level north east corner GADA Lube Oil Skid | Need access to PSV's (110-PSV-1613A and 110-PSV-1613B) to unbolt and remove | 3371 | Murray Tartaglia | 2016-04-17 | Mechanical | Med Duty | ERECT | Cancelled | 2016-04-18
6372 | TBAA | TBAA Train 2 4th level | Dismantle 621 | 3372 | Michael Outram | 2016-04-17 | Mechanical | Med Duty | DISMANTLE | Not Started | 2016-04-17
6373 | TBAA | TBAA Train 2 2 level North Side | Dismantle 622 | 3373 | Michael Outram | 2016-04-17 | Mechanical | Med Duty | DISMANTLE | Not Started | 2016-04-17
6374 | LPW | Jetty LPW Gang way | Lifting frame and scaffold deck to lift out two motors and pumps. LPW gangway tower | 3374 | Todd Lyons | 2016-04-18 | CSU | Med Duty | ERECT | Complete | 2016-04-18 | 2016-04-24
6374 | LPW | Jetty LPW Gang way | Lifting frame and scaffold deck to lift out two motors and pumps. LPW gangway tower | 3374 | Todd Lyons | 2016-04-18 | CSU | Med Duty | ERECT | Complete | 2016-04-18 | 2016-04-24
6375 | GAGA | 1st Level - GAGA | Build scaffold on first level of GAGA to access the installation of pipe work and supports line 0P-10996 | 3375 | Charlie Bryce | 2016-04-18 | Mechanical | Med Duty | ERECT | complete | 2016-04-20 | 2016-04-27
6375 | GAGA | 1st Level - GAGA | Modifications (Re-build) required to allow better access for pipe welds x 3 locations. | 4145 | Mark Farley | 2016-05-05 | Mechanical | Med Duty | MODIFY | Complete | 2016-05-07 | 2016-05-08
6376 | GAGA | 2nd Level - GAGA | Build scaffold on first level of GAGA to access the installation of pipe work &supports line 0P-10996 | 3376 | Charlie Bryce | 2016-04-18 | Mechanical | Med Duty | ERECT | complete | 2016-04-20 | 2016-04-27
6376 | GAGA | GAGA 2 level | Extend scaff deck north to allow welding of pipe in attached picture | 3770 | Mark Farley | 2016-04-30 | Mechanical | Med Duty | MODIFY | complete | 2016-04-02 | 2016-05-15
6385 | TRAIN 2 | TBAA | TBAA HM-2085 Tag 6354 level 1 wast scaffold not required. | 4212 | Felise Emelio | 2016-05-10 | Hertel | Med Duty | DISMANTLE | Complete | 2016-05-17 | 2016-05-12
6420 | Condensate Tanks | Condensate Tanks 3 & 4 | Missing cleet on a platform 25 missing cleet on stiar stringer | 3377 | Paul Velonias | 2016-04-18 | Mechanical | Med Duty | ERECT | complete | 2016-04-20 | 2016-04-19
6421 | RBCF | RBCF | RBCF HM-1981 tag C0529 scaffold take over need access to hole of hook up coming of this stair access. | 3378 | Felise Emelio | 2016-04-18 | Hertel | Med Duty | TAKEOVER | Complete | 2016-04-25 | 2016-04-19
6422 | RBCE | RBCE | RBCE HM-1980 tag C563 scaffold take over need access to hole of hook up coming of this stair access | 3379 | Felise Emelio | 2016-04-18 | Hertel | Med Duty | TAKEOVER | Complete | 2016-04-24 | 2016-04-19
6423 | SADA | SADA | SADA HM-1977 level 2 east Need to dismantle scaffold. HM-251 Intrim Tag | 3380 | Felise Emelio | 2016-04-18 | Hertel | Med Duty | DISMANTLE | Complete | 2016-04-24 | 2016-04-24
6423 | SADA | SADA | Takeover Intrim | 3380 | Felise Emelio | 2016-04-18 | Hertel | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-24
6424 | RBCA | RBCA | RBCA HM-1880 Access needed to Line OB-62003-03 Installation of PPE RFI 767 | 3381 | Felise Emelio | 2016-04-18 | Hertel | Med Duty | ERECT | Cancelled | 2016-04-24
6424 | RBCA | RBCA | RBCA HM-1880 Access needed to Line OB-62003-03 Installation of PPE RFI 767 | 3381 | Felise Emelio | 2016-04-18 | Hertel | Med Duty | ERECT | Not Started | 2016-04-24
6425 | RBCA | RBCA | RBCA HM-1870 Access needed to Line OB-62002.01 Installation of PPE RFI 767 | 3382 | Felise Emelio | 2016-04-18 | Hertel | Med Duty | ERECT | Complete | 2016-04-25 | 2016-05-08
6426 | RBCA | RBCA | RBCA HM-1869 Access needed to Line OB-62002.02 Installation of PPE RFI 767 | 3383 | Felise Emelio | 2016-04-18 | Hertel | Med Duty | ERECT | Complete | 2016-04-26 | 2016-05-08
6427 | RBCA | RBCA | RBCA HM-1868 Access needed to Line OB-62002.05 Installation of PPE | 3384 | Felise Emelio | 2016-04-18 | Hertel | Med Duty | ERECT | Complete | 2016-04-27 | 2016-05-02
6428 | SARA | SARA Mercury Management East | Build Access Gate to East Entrance of Area SARA Mercury Management | 3385 | Adam Keown | 2016-04-18 | Mechanical | Med Duty | ERECT | Complete | 2016-04-18 | 2016-04-21
6429 | SARA | SARA Mercury Management South | Build Access Gate to South Entrance of Area SARA Mercury Management | 3386 | Adam Keown | 2016-04-18 | Mechanical | Med Duty | ERECT | Complete | 2016-04-18 | 2016-04-20
6430 | SARA | SARA Mercury Management West | Build Access Gate to West Entrance of Area SARA Mercury Management | 3387 | Adam Keown | 2016-04-18 | Mechanical | Med Duty | ERECT | Complete | 2016-04-18 | 2016-04-19
6431 | GAEA | Top Level Westside of GAEA | Need access to PSV's (210-PSU-1613A and 210-PSU-1613B) to unbolt and remove - PSU need to be at hip height | 3388 | Murray Tartaglia | 2016-04-18 | Mechanical | Med Duty | ERECT | Cancelled | 2016-04-19
6432 | GAEA | First Level Nth - East crn GAEA Lube oil Skid | Need access to PSV's (210-PSU-1613A and 210-PSU-1613B) to unbolt and remove - PSU need to be at hip height | 3389 | Murray Tartaglia | 2016-04-18 | Mechanical | Med Duty | Erect | Not Started | 2016-04-19
6433 | Inlet | Inlet area pig reciever | Dismantle H1519 | 3390 | LENNIE HAIRA | 2016-04-18 | CSU | Med Duty | DISMANTLE | Complete | 2016-04-24 | 2016-04-24
6433 | Inlet | Inlet area pig reciever | Please dismantle/remove existing scaffold at the pig launcher area as per the hand delivered photographs at H1519 | 3390 | LENNIE HAIRA | 2016-04-18 | CSU | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-24
6434 | Inlet | Inlet area pig reciever | Take over scaffold with no Tag - CVX contact: Peter Fruzynski 840 569 | 3392 | LENNIE HAIRA | 2016-04-19 | CSU | Med Duty | DISMANTLE | Complete | 2016-04-20 | 2016-04-20
6434 | Inlet | Inlet area pig reciever | Take over scaffold with no Tag - CVX contact: Peter Fruzynski 840 569 | 3392 | LENNIE HAIRA | 2016-04-19 | CSU | Med Duty | TAKEOVER | complete | 2016-04-20 | 2016-04-25
6435 | Inlet | Inlet area pig reciever | Take over scaffold with no Tag - CVX contact: Peter Fruzynski 840 569 | 3393 | LENNIE HAIRA | 2016-04-19 | CSU | Med Duty | DISMANTLE | Complete | 2016-04-20 | 2016-04-20
6435 | Inlet | Inlet area pig reciever | Take over scaffold with no Tag - CVX contact: Peter Fruzynski 840 569 | 3393 | LENNIE HAIRA | 2016-04-19 | CSU | Med Duty | TAKEOVER | complete | 2016-04-20 | 2016-04-25
6436 | ABAA | ABAA | Handrail extension in AGRU2 on vessel 2V-1104 | 3395 | Thomas Murphy | 2016-04-19 | Mechanical | Med Duty | ERECT | Complete | 2016-04-20 | 2016-04-18
6437 | GAHK | GAHK MEG Transfer Pumps | Erect scaffold for pipe welding temp spools bottom level as per model shot | 3397 | Steven Cameron | 2016-04-19 | Mechanical | Med Duty | ERECT | Complete | 2016-04-20 | 2016-04-23
6438 | GAHK | GAHK MEG Transfer Pumps | Erect barricade for gridmesh removal mid level as per model shot | 3398 | Steven Cameron | 2016-04-19 | Mechanical | Med Duty | ERECT | complete | 2016-04-20 | 2016-04-23
6439 | Agru 1 | Agru 1 | Dismantle of Scaffold H1018 | 3399 | LENNIE HAIRA | 2016-04-19 | CSU | Med Duty | DISMANTLE | Complete | 2016-04-20 | 2016-04-21
6440 | ABAA | ABAA - RL 27 | Scaffold to be built to gain access on RL27 on to a higher level for the installation of the flare tube of the mercury sample panel | 3396 | Gunther Grossinger | 2016-04-19 | Mechanical | Med Duty | ERECT | complete | 2016-04-20 | 2016-04-24
6441 | GAH4 | GAH4 | Erect scaffold for install of structural steel and pipe support as per model shot | 3400 | Steven Cameron | 2016-04-19 | Mechanical | Med Duty | ERECT | complete | 2016-04-20 | 2016-04-23
6442 | GAH4 | GAH4 | Erect scaffold for install of temp spool as per model shot | 3401 | Steven Cameron | 2016-04-19 | Mechanical | Med Duty | ERECT | complete | 2016-04-20 | 2016-04-26
6443 | TAC1 | TAC1 | Build Scaffold to access for removal of lagging on High Point Valve | 3409 | Steve Denham | 2016-04-20 | Chevron | Med Duty | ERECT | complete | 2016-04-27 | 2016-04-23
6443 | TAC1 | TAC1 | Dismantle Scaffold to access for removal of lagging on High Point Valve | 3409 | Steve Denham | 2016-04-20 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-27 | 2016-04-24
6444 | TAAA | TAAA | Build Scaffold to access from Stairs across steelwork to access Moisture control valve and double block and bleed valve. Ensure deck is large enough for 2 persons and large exhaust fan. | 3410 | Steve Denham | 2016-04-20 | Chevron | Med Duty | ERECT | Complete | 2016-04-27 | 2016-04-21
6444 | TAAA | TAAA | Dismantle 6444 | 3410 | Steve Denham | 2016-04-20 | Chevron | Med Duty | ERECT | Complete | 2016-04-27 | 2016-04-24
6445 | MOF | MOF - Whalf | Dismantle the overhead protection etween the old security hut and toilet block 18 on the P MOF whalf | 3411 | Mike Hemming | 2016-04-20 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-27 | 2016-04-28
6446 | SADA | SADA | Scaffold erected SADA above bog compressor 3403. install ring on dry gas | 3412 | Bob Brevker | 2016-04-21 | Chevron | Med Duty | ERECT | Complete | 2016-04-27 | 2016-04-22
6446 | SADA | SADA | Modify SADA above bog compressor 3403. install ring on dry gas | 3412 | Bob Brevker | 2016-04-21 | Chevron | Med Duty | MODIFY | Complete | 2016-04-27 | 2016-04-29
6446 | SADA | SADA | Dismantle SADA above bog compressor 3403. install ring on dry gas | 3412 | Bob Brevker | 2016-04-21 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-27 | 2016-04-30
6447 | GAGA | GAGA west ground need | GAGA HM-1666 west ground need to erect scaffold to grid mesh for chartek works. Deck height 1.8 below from I-beam. Allow for encapsulation. | 3235 | Felise Emelio | 2016-04-14 | Hertel | Med Duty | ERECT | Complete | 2016-04-21 | 2016-04-20
6448 | ABAD | ABAD level 3 | ABAD HM-1986 Level 3 tag D1082 south 1200 line regen scaffold no longer neededHM-252 | 3407 | Felise Emelio | 2016-04-20 | Hertel | Med Duty | DISMANTLE | Complete | 2016-04-27 | 2016-04-27
6449 | ABAA | ABAA-ABAB | ABAA-ABAB HM-1987 Level 1 tag D0305 scaffold no longer needed HM-253 | 3408 | Felise Emelio | 2016-04-20 | Hertel | Med Duty | DISMANTLE | Complete | 2016-04-27 | 2016-04-27
6450 | TADA | Train 1 TADA | Scaffold to access installation of shim for trunion support | 3414 | Brett Taane | 2016-04-21 | Mechanical | Med Duty | SHUTDOWN-ERECT | complete | 2016-04-22 | 2016-04-29
6451 | GAHL | GAHL HM-1993 1st grid mesh level south end | GAHL HM-1993 1st grid mesh level south end need to erect scaffold to access line PGAH100-1P for paint blast works. Allow extra height on standards to encapsulate | 3419 | Felise Emelio | 2016-04-21 | Hertel | Med Duty | ERECT | complete | 2016-04-26 | 2016-04-29
6452 | GAGA | GAGA Level 2 | Build scaffold to enable the installation of pipe support on 2nd level of GAGA line number PGAGA00-OB-10152-03 | 3420 | Charlie Bryce | 2016-04-21 | Mechanical | Med Duty | ERECT | Complete | 2016-04-23 | 2016-05-07
6453 | Agru 2 | Agru 2 | Dismantle Strip existing ladder from below location the ladder location so emergency exit ladder can be installed | 3206 | David Goodes | 2016-04-12 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-03-14 | 2016-03-14
6454 | RBAQ | RBAQ | RBAQ HM-1965 Dismantle scaffold to allow works on all pipes below both decks. Note no numbers on tags. Intrim tags. | 3234 | Felise Emelio | 2016-04-14 | Hertel | Med Duty | DISMANTLE | Complete | 2016-04-21 | 2016-05-18
6455 | Train 1 | Overhead Crane repair Scaffold A Train 1 | Build Scaffold at PR compressor Train 1 to provide access to repair damage to Overhead Gantry crane (Davit Incident) | 3421 | Mark orr | 2016-04-22 | Chevron | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-21 | 2016-04-23
6456 | Train 1 | Overhead Crane repair Scaffold B | Build Scaffold at PR compressor Train 1 to provide access to repair damage to Overhead Gantry crane (Davit Incident) | 3422 | Mark orr | 2016-04-22 | Chevron | Med Duty | SHUTDOWN-ERECT | Complete | 2016-04-21 | 2016-04-23
6457 | Condensate Tanks | Condensate Container 1 | Erect Sheleving in Container 1 at Condensate Tanks | 3423 | Mark orr | 2016-04-22 | Chevron | Med Duty | ERECT | Complete | 2016-04-21 | 2016-04-24
6458 | Condensate Tanks | Condensate Container 2 | Erect Sheleving in Container 2 at Condensate Tanks | 3424 | Mark orr | 2016-04-22 | Chevron | Med Duty | ERECT | Complete | 2016-04-21 | 2016-04-24
6459 | Condensate Tanks | Condensate Container 3 | Erect Sheleving in Container 3 at Condensate Tanks | 3425 | Mark orr | 2016-04-22 | Chevron | Med Duty | ERECT | Complete | 2016-04-21 | 2016-04-24
6460 | GAA1 | Injection Pumps | Erect Scaffold to access HPV at Pump C | 3415 | Shane Shillabeer | 2016-04-20 | Mechanical | Med Duty | ERECT | complete | 2016-04-21 | 2016-04-01
6461 | GAA1 | Injection Pumps | Erect Scaffold to access HPV at Pump B | 3416 | Shane Shillabeer | 2016-04-20 | Mechanical | Med Duty | ERECT | Complete | 2016-04-21 | 2016-05-03
6462 | GAA1 | Injection Pumps | Erect Scaffold to access HPV at Pump A | 3417 | Shane Shillabeer | 2016-04-20 | Mechanical | Med Duty | ERECT | complete | 2016-04-21 | 2016-05-08
6463 | SADA | fin fan level 4 west end SADA | Access required to install fan belt to fin fan level 4 west end SADA | 3418 | John Young | 2016-04-21 | Hertel | Med Duty | ERECT | complete | 2016-04-26 | 2016-05-14
6464 | Agru 3 | Agru 3, GROUND LEVEL | build deck and humpy for CW12 on line ACA3-3P11260-01 speak with supervision for size and height as this will be built to suit at the location of build. | 3426 | David Goodes | 2016-04-22 | Mechanical | Med Duty | ERECT | Complete | 2016-04-27 | 2016-05-12
6465 | Agru 3 | Agru 3, 20.7RL | build overhead protection to allow for scaffold to continue above - same as agru 2 | 3427 | David Goodes | 2016-04-22 | Mechanical | Med Duty | ERECT | Complete | 2016-04-27 | 2016-05-01
6466 | Agru 3 | Agru 3, ground level | scaffold to access to allow fitting/prep and welding of pipework on the northern utility station. This can be replicated from AGRU2 | 3428 | David Goodes | 2016-04-22 | Mechanical | Med Duty | ERECT | Cancelled | 2016-04-27
6467 | AGRU 3 | Agru 3, MRU stairway, 33RL | build scaffold extension to capture electrical scope, welding of spools to ACAF vessel and pink steel removal. This can be replicated from AGRU2 | 3429 | David Goodes | 2016-04-22 | Mechanical | Med Duty | Erect | Not Started | 2016-04-29
6468 | AGRU 3 | Agru 3, RV platform, 45RL | Build and modify scaffold to allow handrail and walkway installation on RV deck.Scaffold will need to allow for spark encapsulation. Scaffold can be copied from AGRU 2 to allow for electrical scope. | 3430 | David Goodes | 2016-04-22 | Mechanical | Med Duty | Erect | Not Started | 2016-04-29
6469 | DAAA | DAAA level 1 | Erect Scaffold on 1st Level of DAAA on the southern end to access three valves for | 3431 | Bob Brevker | 2016-04-22 | Chevron | Med Duty | ERECT | complete | 2016-04-22 | 2016-04-27
6470 | MOF | SCAF | Takeover 2890 | 3432 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-22 | 2016-04-23
6471 | MOF | SCAH colum B1 | Takeover I0453 tag 1029 | 3433 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-22 | 2016-04-24
6472 | MOF | SCCC area 2 | Takeover I584 | 3434 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-22 | 2016-04-23
6473 | MOF | STAG | Takeover I927 | 3435 | Murray Wetere | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-04-22
6474 | MOF | MOF DAB | Takeover I1076 | 3436 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-22 | 2016-04-23
6475 | MOF | MOF | Takeover 1411 | 3437 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-22 | 2016-04-23
6476 | MOF | MOF | Takeover 1422 | 3438 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-22 | 2016-04-23
6477 | MOF | SCBA | Takeover I1500 | 3439 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-22 | 2016-04-24
6478 | MOF | SCBE | Takeover I1849 | 3440 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-22 | 2016-04-24
6479 | MOF | SCBD | Takeover I1853 refer to 751 | 3441 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-22 | 2016-04-24
6480 | MOF | SCBD | Takeover I1855 | 3442 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-22 | 2016-04-24
6481 | MOF | MOF | Takeover I1886 | 3443 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-22 | 2016-04-28
6482 | MOF | SCBB | Takeover I1913 | 3444 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-22 | 2016-04-24
6483 | MOF | MOF | Takeover I1929 | 3445 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-22 | 2016-04-24
6484 | MOF | JETTY ENTRANCE | Takeover I1942 | 3446 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-22 | 2016-04-25
6485 | MOF | JETTY END ABUTTMENT | Takeover 1943 | 3447 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-22 | 2016-04-24
6486 | MOF | MOF | Takeover 1944 | 3448 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-22 | 2016-04-23
6487 | MOF | SCBC | Takeover I1995 | 3449 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-22 | 2016-04-28
6488 | MOF | SCAC | Takeover I2174 | 3450 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-22 | 2016-04-23
6489 | MOF | MOF SCCC | Takeover 2188 | 3451 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-22 | 2016-04-21
6490 | MOF | TOP OF ROAD | Takeover I 2210 | 3452 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-22 | 2016-04-25
6491 | MOF | MOF | Takeover I2307 | 3453 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-22 | 2016-04-23
6492 | MOF | MOF | Takeover I2426 | 3454 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-22 | 2016-04-23
6493 | MOF | MOF | Takeover 2429 | 3455 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-22 | 2016-04-23
6494 | MOF | MOF - DAB | Takeover I2482 | 3456 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-22 | 2016-04-23
6495 | MOF | JETTY ENTRANCE | Takeover I2500 | 3457 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-22 | 2016-04-28
6496 | MOF | MOF | Takeover I2765 | 3458 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-22 | 2016-04-23
6497 | MOF | JETTY END ABUTTMENT | Takeover2809 | 3459 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-22 | 2016-04-25
6498 | MOF | JETTY END ABUTTMENT | Takeover 2810 | 3460 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-22 | 2016-04-28
6499 | MOF | SCBE | Takeover I2811 | 3461 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-22 | 2016-04-28
6500 | MOF | SCBJ TOP OF RAMP | Takeover I2855 | 3462 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-22 | 2016-04-24
6501 | MOF | MOF - DAB | Takeover I2869 | 3463 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-22 | 2016-04-23
6502 | MOF | SCBJ - JETTY END | Takeover 2906 | 3464 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-22 | 2016-04-28
6503 | MOF | MOF - DAB | Takeover I2922 | 3465 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-22 | 2016-04-25
6504 | MOF | MOF - DAB | Takeover I1606 REFERE TO SCAFFOLD TAG NO: 6506 (MERGED SCAFFOLD TOGTHER) | 3466 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | Cancelled | 2016-04-22
6505 | MOF | MOF - DAB | Takeover I1805 - REFERE TO SCAFFOLD TAG NO: 6506 (MERGED SCAFFOLD TOGTHER) | 3467 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | Cancelled | 2016-04-22
6506 | MOF | MOF - DAB | Takeover I333 | 3468 | Cecil Ngaheu | 2016-04-22 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-22 | 2016-04-23
6507 | SAHA | Condensate Tanks | Mobile humpy scaffold build | 3469 | Daniel Edwards | 2016-04-22 | Mechanical | Med Duty | ERECT | Complete | 2016-04-24 | 2016-05-24
6508 | SAHA | SAHA NW Corner Condensate Tanks | Scaffold build for tie-ins above bund wall | 3470 | Daniel Edwards | 2016-04-22 | Mechanical | Med Duty | Erect | Not Started | 2016-04-24
6509 | SAHA | SAHA Northern Wall Condensate Tanks | Scaffold build beneath platform to access mount on top of bund wall for grouting | 3471 | Daniel Edwards | 2016-04-22 | Mechanical | Med Duty | ERECT | complete | 2016-04-24 | 2016-04-15
6510 | SAHA | SAHA between T3/T4 Condensate Tanks | Temporary handrails / baricade for hand rail installation, temporary barricading at bottom of access-ways / stairs (x3) to be removed | 3472 | Daniel Edwards | 2016-04-22 | Mechanical | Med Duty | ERECT | Complete | 2016-04-24 | 2016-05-18
6511 | TACA | TACA Ground level | Dismantle - Doublup (Cancel DNC number 6511) | 3477 | Adam Stark | 2016-04-22 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-22 | 2016-04-24
6512 | TACA | TACA Ground level | Dismantle - Doublup (Cancel DNC number 6512) | 3478 | Adam Stark | 2016-04-22 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-22 | 2016-04-24
6513 | TACA | TACA Ground level | Dismantle - Doublup (Cancel DNC number 6513) | 3479 | Adam Stark | 2016-04-22 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-22 | 2016-04-24
6514 | Train 1 | manway M50 on 1E-1531 | Scaffold build for access to manway M50 on 1E-1531 | 3480 | Barry Baker | 2016-04-22 | Chevron | Med Duty | ERECT | Complete | 2016-04-22 | 2016-04-22
6515 | Train 1 | manway M55 on 1E-1531 | Scaffold build for access to manway M55 on 1E-1531 | 3481 | Barry Baker | 2016-04-22 | Chevron | Med Duty | ERECT | Complete | 2016-04-22 | 2016-04-22
6516 | Train 1 | manway M59 on 1E-1531 | Scaffold build for access to manway M59 on 1E-1531 | 3482 | Barry Baker | 2016-04-22 | Chevron | Med Duty | ERECT | Complete | 2016-04-22 | 2016-04-22
6517 | GAA1 | Inlet injection Pumps | Erect Scaffold to access pipe support at pump 1 PSV inlet | 3483 | Shane Shillabeer | 2016-04-19 | Mechanical | Med Duty | ERECT | Complete | 2016-04-20 | 2016-05-01
6518 | GAHK | GAHK | Modify scaffold for pipe weld temp spools middle level as per photo - Double up of DNC 6219 | 3474 | Steven Cameron | 2016-04-22 | Mechanical | Med Duty | MODIFY | Cancelled | 2016-04-25
6519 | RBAB | RBAB - Tag H1535 | Takeover H 1535 | 3476 | Thomas Murphy | 2016-04-22 | Mechanical | Med Duty | TAKEOVER | complete | 2016-04-25 | 2016-04-29
6519 | RBAB | RBAB - Tag H1535 | Dismantle of scaffold access tower RBAB fro CKJV crane access | 3476 | Thomas Murphy | 2016-04-22 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-04-25 | 2016-05-18
6520 | MOF | MOF | As discussed the scaffolding surrounding the CCTV camera 88 is apparently out of date and Kentz have been requested to reposition that camera.Could we please find a way to allow Kentz to access this camera safely so they can carry out their work. | 3484 | Mike Hemming | 2016-04-22 | Mechanical | Med Duty | ERECT | complete | 2016-04-25 | 2016-04-24
6521 | AGRU 2 | Agru 2, GROUND LEVEL Tag: LC10286 (CPB scaffold) | Modify scaffold to allow for pipe install. Strip/remove scaffold once install is complete. this scaffold will require confined space certificate to perform task. CPB erected current scaffold | 3485 | David Goodes | 2016-04-23 | Mechanical | Med Duty | TAKEOVER | Complete | 2015-04-25 | 2015-04-25
6521 | AGRU 2 | Agru 2, GROUND LEVEL | Modify scaffold to allow for pipe install. Strip/remove scaffold once install is complete. this scaffold will require confined space certificate to perform task. CPB erected current scaffold | 3485 | David Goodes | 2016-04-23 | Mechanical | Med Duty | MODIFY | Complete | 2015-04-25 | 2016-05-22
6522 | LPW | LPW-SAYE | LPW south HM-2010 Need access for paint/blast works deck height 1.5 below I-beam 1.8m x 2.1 standards to allow for encapsulation. | 3486 | Felise Emelio | 2016-04-23 | Hertel | Med Duty | ERECT | Complete | 2016-04-29 | 2016-05-05
6522 | LPW | LPW-SAYE | LPW south HM-2010 Need access for paint/blast works deck height 1.5 below I-beam 1.8m x 2.1 standards to allow for encapsulation. | 3486 | Felise Emelio | 2016-04-23 | Hertel | Med Duty | ERECT | Complete | 2016-04-29 | 2016-05-21
6522 | LPW | PW-SAYN | Dismantle | 4484 | Martin Riegert | 2016-05-21 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-28 | 2016-05-22
6523 | SAYM | LPW-SAYM | SAYM-SAYU HM-2013 Need to provide access to I-beam for paint/blast works extend standards for encapsulation | 3488 | Felise Emelio | 2016-04-23 | Hertel | Med Duty | ERECT | Complete | 2016-04-30 | 2016-05-15
6524 | SAYM | LPW-SAYM | SAYV-SAYN HM-2014 Need to provide access to I-beam for paint/blast works extend standards for encapsulation. | 3489 | Felise Emelio | 2016-04-23 | Hertel | Med Duty | ERECT | Complete | 2016-04-30 | 2016-05-03
6524 | LPW | PW-SAYN | Dismantle | 4483 | Martin Riegert | 2016-05-21 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-28 | 2016-05-22
6525 | SAYV | LPW-SAYV | SAYV HM-2015 Need to provide access to I-beam for paint/blast works extend standards for encapsulation. | 3490 | Felise Emelio | 2016-04-23 | Hertel | Med Duty | ERECT | Complete | 2016-04-30 | 2016-05-15
6526 | SAYV | LPW-SAYV | SAYV HM-2016 Need to provide access to I-beam for paint/blast works extend standards for encapsulation | 3491 | Felise Emelio | 2016-04-23 | Hertel | Med Duty | ERECT | Complete | 2016-04-30 | 2016-05-15
6527 | TBJF | TBJF Tain 2 take over E2338 | please do modification to extisting scaffolding, so we can set up for chemical flushing. We need to set up 12" lines from pipe to ground flushing. We will be setting up 12" lines from the pipe to ground. | 3492 | LENNIE HAIRA | 2016-04-23 | CSU | Med Duty | MODIFY | Complete | 2016-04-24 | 2016-04-27
6527 | TBJF | TBJF Tain 2 take over E2338 | Takeover E 2338 - for Lennie request SR 3492 | 3492 | LENNIE HAIRA | 2016-04-23 | CSU | Med Duty | Takeover | Complete | 2016-04-24 | 2016-04-27
6528 | GAEA | Level 1 North West | Take over A2461 | 3493 | Murray Tartaglia | 2016-04-23 | Mechanical | Med Duty | TAKEOVER | Complete | 2016-04-24 | 2016-04-24
6529 | GAA1 | GAA1 Injetion Pumps | erect scaffold to access support and butt welds under PSV pump A | 3494 | Shane Shillabeer | 2016-04-23 | Mechanical | Med Duty | ERECT | Complete | 2016-04-24 | 2016-05-01
6530 | LPW | LPW-SAYN | LPW south HM-2011 Need to extend deck west 1.5m for paint/blast works deck height 1.5 below I-beam allow for encapsulation. | 3487 | Felise Emelio | 2016-04-23 | Hertel | Med Duty | MODIFY | Complete | 2016-04-29 | 2016-05-05
6531 | AGRU 2 | Agru 2 - MRU Tank | Muilti Layer scaffold for access to install vertical cable ladder & brackets | 3496 | Geoff Haren | 2016-04-23 | Electrical | Med Duty | ERECT | complete | 2016-04-27 | 2016-04-30
6532 | TAF1 | TAF1 - Ground level North | Takeover Scaffold TAG NO: B5531 | 3497 | Chistopher Reachy | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-24
6533 | TAJB | Stair tower ground Level TAJB | Takeover Scaffold TAG NO: B5530 | 3498 | Chistopher Reachy | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-24
6534 | TAJB | West face ground Level TAJB | Takeover Scaffold TAG NO: B 5548 | 3499 | Chistopher Reachy | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-24
6535 | MOF | SASF TOP LEVEL S/W | Takeover Scaffold TAG NO: I3062 | 3500 | Chistopher Reachy | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-25
6536 | GADA | GADA | Takeover Scaffold TAG NO: A2406 | 3501 | Chistopher Reachy | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-26
6537 | GADA | GADA | Takeover Scaffold TAG NO: NO TAG | 3502 | Chistopher Reachy | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-26
6538 | GADA | GADA | Takeover Scaffold TAG NO: | 3503 | Chistopher Reachy | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-26
6539 | GADA | GADA | Takeover Scaffold TAG NO: a2292 | 3504 | Chistopher Reachy | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-26
6540 | GADA | GADA | Takeover Scaffold TAG NO: A2172 | 3505 | Chistopher Reachy | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-26
6541 | GADA | GADA | Takeover Scaffold TAG NO: A2253 | 3506 | Chistopher Reachy | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-26
6542 | SITEWIDE - TBA | Site Wide | Takeover Scaffold TAG NO: | 3507 | Chistopher Reachy | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-04-24
6543 | GAEA | Level 1 West Center | Takeover Scaffold TAG NO: A 2331 | 3508 | Chistopher Reachy | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-25
6544 | GAEA | GAEA | Takeover Scaffold TAG NO: A 2462 | 3509 | Chistopher Reachy | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2015-04-24
6545 | GAEA | GAEA | Takeover Scaffold TAG NO: A 420 | 3510 | Chistopher Reachy | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-24
6546 | gAEA | GAEA | Takeover Scaffold TAG NO: A 2069 | 3511 | Chistopher Reachy | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-24
6547 | GAEA | GAEA | Takeover Scaffold TAG NO: A 389 | 3512 | Chistopher Reachy | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-25
6548 | GAEA | GAEA 3RD LEVEL - MOBILE | Takeover Scaffold TAG NO: A2055 | 3513 | Chistopher Reachy | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-25
6549 | GAEA | GAEA 3RD LEVEL - MOBILE | Takeover Scaffold TAG NO: A 1438 | 3514 | Chistopher Reachy | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-24
6549 | GAEA | GAEA | Please modify the scaffold platform as per photographs to enable access to the other module bays other module bays under the fin fans at (GAEA) Tag number is 6549 | 4430 | Lennie Haira | 2016-05-20 | CSU | Med Duty | MODIFY | Not started | 2016-05-25
6550 | GAEA | GAEA 3RD LEVEL - MOBILE | Takeover Scaffold TAG NO: A1133 | 3515 | Chistopher Reachy | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-24
6551 | GAEA | GAEA | Takeover Scaffold TAG NO: A 2473 | 3516 | Chistopher Reachy | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-25
6552 | SITEWIDE - TBA | Site Wide | Takeover Scaffold TAG NO: | 3517 | Chistopher Reachy | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-04-24
6553 | Condensate Tanks | TOILET BLOCK | Takeover Scaffold TAG NO: 9723 | 3518 | Chistopher Reachy | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-26
6554 | Area 4 | crib 6 access | Takeover Scaffold TAG NO: 1089 | 3519 | Chistopher Reachy | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-28
6555 | Area 4 | crib 5 acess | Takeover Scaffold TAG NO: 1090 | 3520 | Chistopher Reachy | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-28
6556 | Area 4 | sulza stairs | Takeover Scaffold TAG NO: 696 | 3521 | Chistopher Reachy | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-28
6557 | Area 4 | elect tray frame | Takeover Scaffold TAG NO:359 | 3522 | Chistopher Reachy | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-28
6558 | Area 4 | smmokers hut-crib 9 | Takeover Scaffold TAG NO: i1113 | 3523 | Chistopher Reachy | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-28
6559 | Area 4 | Office Permit | Takeover Scaffold TAG NO: 697 | 3524 | Chistopher Reachy | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-28
6560 | Area 10 | Area 10 saffold yar hump | Takeover Scaffold TAG NO: 666 | 3525 | Chistopher Reachy | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-26
6561 | SCCG | SCCG | Takeover Scaffold TAG NO: D835 | 3526 | Joel Gray | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-26
6562 | SCCF | SCCF | Takeover Scaffold TAG NO: D25 | 3527 | Joel Gray | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-26
6563 | SCCF | SCCF | Takeover Scaffold TAG NO: D861 | 3528 | Joel Gray | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-26
6564 | SCCE | SCCE | Takeover Scaffold TAG NO: D826 | 3529 | Joel Gray | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-26
6565 | SITEWIDE - TBA | Site Wide | Takeover Scaffold TAG NO: | 3530 | Joel Gray | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-04-24
6566 | SCCD | SCCD | Takeover Scaffold TAG NO: D828 | 3531 | Joel Gray | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-26
6567 | SCCD | SCCD | Takeover Scaffold TAG NO: D 823 | 3532 | Joel Gray | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-26
6567 | DAAA | Domgas | Dismantle | 4379 | Trevor Pike | 2016-05-16 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-16 | 2016-05-16
6568 | SCAD | SCAD | Takeover Scaffold TAG NO: N/A | 3533 | Joel Gray | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-26
6569 | SCAD | SCAD | Takeover Scaffold TAG NO: I2282 | 3534 | Joel Gray | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-26
6570 | SCAD | SCAD | Takeover Scaffold TAG NO: I2196 | 3535 | Joel Gray | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-26
6571 | SCAC | SCAC | Takeover Scaffold TAG NO: N/A | 3536 | Joel Gray | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-26
6572 | DAAA | Domgas 1st Level SE corner | Build scaffold to access two Instrumnt tube end connections on SE corner of Level 1 Domgas.There is two platform ladders under the tubing connections and a similar scaffold | 3537 | Joel Gray | 2016-04-24 | Scaffolding | Med Duty | ERECT | complete | 2016-04-24 | 2016-04-28
6573 | SITEWIDE - TBA | Site Wide | Takeover Scaffold TAG NO: | 3538 | Joel Gray | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-29
6574 | AGRU 3 | Ground Level | build mobile hop up for FW16 on line ACA3-3P11261-01 | 3539 | David Goodes | 2016-04-24 | Mechanical | Med Duty | ERECT | Complete | 2016-04-24 | 2016-04-25
6575 | mof | scab sccc | Takeover Scaffold TAG NO: i2192 | 3540 | Murray Wetere | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-28
6576 | mof | scab sccc | Takeover Scaffold TAG NO: i2193 | 3541 | Murray Wetere | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-28
6577 | mof | scab sccc | Takeover Scaffold TAG NO: na | 3542 | Murray Wetere | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-28
6578 | mof | scab sccc | Takeover Scaffold TAG NO:i2191 | 3543 | Murray Wetere | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-28
6579 | mof | scab sccc | Takeover Scaffold TAG NO: I2190 | 3544 | Murray Wetere | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-24 | 2016-04-28
6580 | mof | SCAB SCCC | Takeover Scaffold TAG NO: NA | 3545 | Murray Wetere | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-24 | 2016-04-28
6581 | mof | SCCB | Takeover Scaffold TAG NO:NA | 3546 | Murray Wetere | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-24 | 2016-04-28
6582 | mof | SCCB | Takeover Scaffold TAG NO: NA | 3547 | Murray Wetere | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-24 | 2016-04-28
6583 | mof | SCAA | Takeover Scaffold TAG NO: NA | 3548 | Murray Wetere | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-24 | 2016-04-28
6584 | mof | SATT SCAA | Takeover Scaffold TAG NO: 1501 | 3549 | Murray Wetere | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-24 | 2016-04-28
6585 | MOF | SATT SCAA | Takeover Scaffold TAG NO: i1334 | 3550 | Murray Wetere | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-28
6586 | mof | sch | Takeover Scaffold TAG NO: 405 | 3551 | Murray Wetere | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-28
6587 | MOF | SATL COLUMN B1 | Takeover Scaffold TAG NO: NO TAG | 3552 | Murray Wetere | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-25
6588 | MOF | SATR COLUMN B4 | Takeover Scaffold TAG NO: NO TAG | 3553 | Murray Wetere | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-25
6589 | MOF | SATG | Takeover Scaffold TAG NO: 933 | 3554 | Murray Wetere | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-25
6590 | MOF | DAB | Takeover Scaffold TAG NO: NO TAG | 3555 | Murray Wetere | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-25
6591 | MOF | DAB | Takeover Scaffold TAG NO: HERTEL | 3556 | Murray Wetere | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-25
6592 | MOF | DAB - Area 2 | Takeover Scaffold TAG NO: I 2483 | 3557 | Murray Wetere | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-24 | 2016-04-25
6593 | MOF | DAB - Area 2 | Takeover Scaffold TAG NO: intrim | 3558 | Murray Wetere | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-04-24 | 2016-04-25
6594 | MOF | DAB | Takeover Scaffold TAG NO: 873 | 3559 | Murray Wetere | 2016-04-24 | Scaffolding | Med Duty | TAKEOVER | complete | 2016-04-24 | 2016-04-25
6595 | TAAA | TAAA east side | Erect Scaffold on Eastern side of vessel to EASTERN side of vessel tou nderside of curved top section of vessel. | 3560 | Mark orr | 2016-04-24 | Chevron | Med Duty | SHUTDOWN-ERECT | complete | 2016-04-24 | 2016-04-29
6595 | TRAIN 1 | Train 1, TACA, Level 3 | Dismantle scaffold on Train 1, level 3 vessel 1530 | 4117 | Trevor Pike | 2016-05-02 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-02 | 2016-04-02
6596 | TAAA | TAAA east side | Erect Scaffold on Eastern side of vessel to WESTERN side of vessel tou nderside of curved top section of vessel. | 3561 | Mark orr | 2016-04-24 | Chevron | Med Duty | SHUTDOWN-ERECT | complete | 2016-04-24 | 2016-04-29
6596 | TRAIN 1 | Train 1, TACA, Level 3 | Dismantle scaffold on Train 1, level 3 vessel 1530 | 4119 | Trevor Pike | 2016-05-02 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-02 | 2016-05-02
6597 | TAAA | TAAA east side | Erect Scaffold on Eastern side of vessel to EASTERN side of vessel tou nderside of curved top section of vessel. | 3562 | Mark orr | 2016-04-24 | Chevron | Med Duty | SHUTDOWN-ERECT | complete | 2016-04-24 | 2016-04-25
6597 | TRAIN 1 | Train 1, TACA, Level 3 | Dismantle scaffold on Train 1, level 3 vessel 1531 | 4118 | Trevor Pike | 2016-05-02 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-02 | 2016-05-02
6598 | TAAA | TAAA east side | Erect Scaffold on Eastern side of vessel to WESTERN side of vessel tou nderside of curved top section of vessel. | 3563 | Mark orr | 2016-04-24 | Chevron | Med Duty | SHUTDOWN-ERECT | complete | 2016-04-24 | 2016-04-26
6598 | TRAIN 1 | Train 1, TACA, Level 3 | Dismantle scaffold on Train 1, level 3 vessel 1531 | 4116 | Trevor Pike | 2016-05-02 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-02 | 2016-05-02
6599 | SARA | SARA | Build Access Gate to North Entrance of Area | 3564 | Mark orr | 2016-04-24 | Chevron | Med Duty | ERECT | complete | 2016-04-24 | 2016-04-25
6600 | BD2W | BD2W Jetty | Martin has looked and knows the job well. Erect Lift Frame for Capstan CSU scope. | 3565 | Wayne Hall | 2016-04-25 | Mechanical | Med Duty | ERECT | complete | 2016-04-27 | 2016-04-27
6601 | Agru 3 | Agru 3, GROUND LEVEL | build two small mobile scaffolds to allow welding on 750nb pipe ACAC-3P11045-02 , welding of test cap for hydro. | 3567 | Mark orr | 2016-04-25 | Chevron | Med Duty | ERECT | complete | 2016-04-27 | 2016-04-29
6635 | AAAE | TOP LEVEL AAAE | Takeover Scaffold TAG NO: MAS I 1618 | 3568 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-27
6636 | POF | POF CRIB 4 STAIR ACCESS | Takeover Scaffold TAG NO: 885 | 3569 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-29
6637 | POF | POF CRIB 3 STAIR ACCESS | Takeover Scaffold TAG NO: 884 | 3570 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-29
6638 | POF | POF CRIB 2 STAIR ACCESS | Takeover Scaffold TAG NO: 883 | 3571 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-29
6639 | POF | POF CRIB 1 STAIR ACCESS | Takeover Scaffold TAG NO: 882 | 3572 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-29
6640 | Oliver | Oliver container shelves | Takeover Scaffold TAG NO: 584 | 3573 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-29
6641 | Oliver | Oliver container shelves | Takeover Scaffold TAG NO: 582 | 3574 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-29
6642 | Oliver | Oliver container shelves | Takeover Scaffold TAG NO: 1204 | 3575 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-29
6643 | Oliver | stores right side containers / humpy access | Takeover Scaffold TAG NO: 975 | 3576 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-29
6644 | Oliver | left of stores container access | Takeover Scaffold TAG NO: 974 | 3577 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-29
6645 | Oliver | stores bench / shade protetion | Takeover Scaffold TAG NO: 614 | 3578 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-29
6646 | Oliver | Generator Cover | Takeover Scaffold TAG NO: 892 | 3579 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-29
6647 | SCCE | SCCE | Takeover Scaffold TAG NO: D827 | 3580 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-26
6648 | Oliver | sataight hard barricade | Takeover Scaffold TAG NO: 369 | 3581 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-29
6649 | Oliver | smokers humpy | Takeover Scaffold TAG NO: 98 | 3582 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-29
6650 | Oliver | Mobile Humpy | Takeover Scaffold TAG NO: 99 | 3583 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-29
6651 | MAM | Shakedown Yard sub station | Takeover Scaffold TAG NO: 1159 | 3584 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-29
6652 | MAM | Shakedown Yard sub station | Takeover Scaffold TAG NO: 1142 | 3585 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-29
6653 | SCCO | SCCO / SCCF | Takeover Scaffold TAG NO: I 239 | 3586 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-27
6654 | SCCG | SCCG | Takeover Scaffold TAG NO: 835 | 3587 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-27
6655 | SCCG | Sitewide | Takeover Scaffold TAG NO: 820 | 3588 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-27
6656 | SCCG | SCCG | Takeover Scaffold TAG NO: 834 | 3589 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-27
6657 | SCCH | SCCH MOF | Takeover Scaffold TAG NO: 821 | 3590 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-27
6658 | SCCI | MOF | Takeover Scaffold TAG NO: 822 | 3591 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-27
6659 | MOF | MOF LOOP 6 | Takeover Scaffold TAG NO: 813 | 3592 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-27
6660 | SCAH | SCAH | Takeover Scaffold TAG NO: 1029 Column B1 | 3593 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-27
6661 | SCAJ | SCAJ | Takeover Scaffold TAG NO: 1025 Column 5 | 3594 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-27
6662 | SCCK | SCCK | Takeover Scaffold TAG NO: 806 | 3595 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-27
6663 | SCCK | SCCK | Takeover Scaffold TAG NO: NO TAG | 3596 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-27
6664 | MOF | SCCK | Takeover Scaffold TAG NO: 1027 | 3597 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-28
6665 | MOF | SCCK | Takeover Scaffold TAG NO: I2454 | 3598 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-27
6666 | MOF | SCCL | Takeover Scaffold TAG NO:I2452 | 3599 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-27
6667 | MOF | SCCM | Takeover Scaffold TAG NO: 804 | 3600 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-27
6668 | MOF | SCAL | I296 | 3601 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-27
6669 | MOF | SCAM | 1024 | 3602 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-27
6670 | MOF | SCAN | 1020 | 3603 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-27
6671 | MOF | SCAN | Takeover Scaffold TAG NO: 758 | 3604 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-27
6672 | MOF | SCCQ | Takeover Scaffold TAG NO: 801 | 3605 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-27
6673 | MOF | SCCM | Takeover Scaffold TAG NO:745 | 3606 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-27
6674 | MOF | SCAQ | Takeover Scaffold TAG NO: | 3607 | Chistopher Reachy | 2016-04-25 | Scaffolding | Med Duty | Takeover | complete | 2016-04-25 | 2016-04-27
6675 | Condensate Tanks | Condensate Tanks | Need 1 mobile hot work humpies to be erected. They must also be erected for a crane to move around. They do not require wheels. | 3608 | Daniel Edwards | 2016-04-25 | Mechanical | Med Duty | ERECT | Complete | 2016-04-27 | 2016-05-01
6676 | Condensate Tanks | Condensate Tanks | Need a scaffold erected to access final tie in points, guides & associated piping. Itwill need to be erected to assist with electrical works later on down the track. | 3609a | Daniel Edwards | 2016-04-25 | Mechanical | Med Duty | ERECT | Complete | 2016-04-27 | 2016-05-05
6676 | Condensate Tanks | Condensate Tanks | Need a scaffold erected to access final tie in points, guides & associated piping. Itwill need to be erected to assist with electrical works later on down the track. | 3609b | Daniel Edwards | 2016-04-25 | Mechanical | Med Duty | ERECT | Complete | 2016-04-27 | 2016-05-05
6676 | SAH1 | Condensate Tanks | Need a scaffold erected to access final tie in points, guides & associated piping. Itwill need to be erected to assist with electrical works later on down the track. | 3609 | Daniel Edwards | 2016-04-25 | Mechanical | Med Duty | ERECT | Complete | 2016-04-27 | 2016-05-15
6676 | SAH1 | 6676-A SAH1 adjacent condensate tank3 | Extention between two existing scaffolds to allow for cable ladder and cable installation. Please see attached 3D model shot. 6676A | 4285 | Glenn Beckett | 2016-05-13 | Mechanical | Med Duty | MODIFY | Not Started | 2016-05-20
6676 | SAH1 | 6676-B SAH1 adjacent condensate tank3 | Extention between existing scaffold 6676B and north bund wall to allow for cable ladder and cable installation. Please see attached 3D model shot. Please call Glenn Beckett to walk through job prior to starting. 6676B | 4286 | Glenn Beckett | 2016-05-13 | Mechanical | Med Duty | MODIFY | Not Started | 2016-05-20
6676 | SAH | N/W corner condensate tank 3 | Scaffolds require modification to handrails and deck to install cable ladder, as discussed with Sal and Jared - DNC TAG 6676 | 4508 | Glenn Beckett | 2016-05-23 | Mechanical | Med Duty | Modify | Not Started | 2016-05-28
6676 | SAH | N/W corner condensate tank 3 | Scaffolds require modification to handrails and deck to install cable ladder, as discussed with Sal and Jared - DNC 6676 A | 4509 | Glenn Beckett | 2016-05-23 | Mechanical | Med Duty | Modify | Not Started | 2016-05-28
6677 | Condensate Tanks | Condensate Tanks | Need 2 separate scaffold platforms to be erected on the northern access staris to allow access for grouting | 3610 | Daniel Edwards | 2016-04-25 | Mechanical | Med Duty | ERECT | Complete | 2016-04-27 | 2016-05-08
6677 | SAH | North wall inside condi tanks SAH1 | Scaffold on left side of stairs requires dismantling to allow for cable ladder installation | 4674 | Glenn Beckett | 2016-05-26 | Mechanical | Med Duty | Dismantle | Not Started | 2016-05-30
6678 | Condensate Tanks | Condensate Tanks | Need 1 separate scaffold platforms to be erected on the northern access staris to allow access for grouting | 3611a | Daniel Edwards | 2016-04-25 | Mechanical | Med Duty | ERECT | Complete | 2016-04-27 | 2016-05-09
6678 | Condensate Tanks | Condensate Tanks | Need 1 separate scaffold platforms to be erected on the northern access staris to allow access for grouting | 3611b | Daniel Edwards | 2016-04-25 | Mechanical | Med Duty | ERECT | Complete | 2016-04-27 | 2016-05-09
6679 | Condensate Tanks | Condensate Tanks | Need hard barricade removed from bottom of stairs and hard barricade installed where handrail is missing to open stairs up | 3612 | Daniel Edwards | 2016-04-25 | Mechanical | Med Duty | ERECT | Complete | 2016-04-27 | 2016-05-07
6680 | Condensate Tanks | Condensate Tanks | LC9982 - stair cases at SAP area 8 | 3613 | Daniel Edwards | 2016-04-25 | Mechanical | Med Duty | Takeover | complete | 2016-04-27 | 2016-04-30
6680 | Condensate Tanks | Condensate Tanks | LC9982 - stair cases at SAP area 8 | 3613 | Daniel Edwards | 2016-04-25 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-04-27 | 2016-05-09
6681 | Condensate Tanks | Condensate Tanks | Need 1 mobile hot work humpies to be erected. They must also be erected for a crane to move around. They do not require wheels. | 3615 | Daniel Edwards | 2016-04-25 | Mechanical | Med Duty | ERECT | Complete | 2016-04-27 | 2016-05-01
6682 | DAAA | DAAA 2 level south | Build scaffold to centre line flange on the centre module of line OP24102 as per Bob Breuker's request | 3616 | Mark orr | 2016-04-25 | Chevron | Med Duty | ERECT | complete | 2016-04-27 | 2016-04-29
6682 | DAAA | Domgas | Dismantle | 4384 | Trevor Pike | 2016-05-16 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-16 | 2016-05-16
6683 | DAAA | DAAA 2 level south | Build scaffold to line OP24231 on the southern end of module as per Bob Breuker's request | 3617 | Mark orr | 2016-04-25 | Chevron | Med Duty | ERECT | complete | 2016-04-27 | 2016-04-29
6684 | GAH4 | GAH4 | Erect scaffold for install of temp spool as per discussion with Kevin Haggarty and model shot | 3619 | Steven Cameron | 2016-04-25 | Mechanical | Med Duty | ERECT | complete | 2016-04-27 | 2016-05-23
6685 | GAH1 | GAH1 | Install scaffold deck for install of pipe support guides as per model shot and discussion with Kevin Haggarty | 3620 | Steven Cameron | 2016-04-25 | Mechanical | Med Duty | ERECT | Complete | 2016-04-27 | 2016-05-07
6686 | GAH4 | GAH4 | Modify scaffold deck height for install of structural steel and pipe support as per discussion with Kevin Haggarty | 3621 | Steven Cameron | 2016-04-25 | Mechanical | Med Duty | ERECT | complete | 2016-04-27 | 2016-04-27
6687 | Condensate Tanks | Condensate Tanks | Takeover LC9984 - stair cases at SAP area 8 | 3622 | Daniel Edwards | 2016-04-25 | Mechanical | Med Duty | TAKEOVER | complete | 2016-04-27 | 2016-04-27
6687 | Condensate Tanks | Condensate Tanks | LC9984 - stair cases at SAP area 8 | 3622 | Daniel Edwards | 2016-04-25 | Mechanical | Med Duty | TAKEOVER | complete | 2016-04-27 | 2016-04-30
6687 | Condensate Tanks | Condensate Tanks | LC9984 - stair cases at SAP area 8 | 3622 | Daniel Edwards | 2016-04-25 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-04-27 | 2016-05-04
6688 | Train 1 | TR1 Fin Fan Level | Build Mobile scaffold 1200 high x 1500 long and 900 wide A | 3641 | Mark orr | 2016-04-27 | Chevron | Med Duty | ERECT | complete | 2016-04-30 | 2016-04-29
6688 | TRAIN 1 | TRAIN 1, TAJC TOP LEVEL | Dismantle 8 x mobile scaffolds on Train 1, TAJC Finfans Top Level. Scaffold numbers: 6688, 6690, 6716, 6689, 6721, 6694, 7157, 7156. | 4136a | Craig Coombe | 2016-05-05 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-12 | 2016-05-05
6689 | Train 1 | TR1 Fin Fan Level | Build Mobile scaffold 1200 high x 1500 long and 900 wide B | 3642 | Mark orr | 2016-04-27 | Chevron | Med Duty | ERECT | complete | 2016-04-30 | 2016-04-29
6689 | TRAIN 1 | TRAIN 1, TAJC TOP LEVEL | Dismantle 8 x mobile scaffolds on Train 1, TAJC Finfans Top Level. Scaffold numbers: 6688, 6690, 6716, 6689, 6721, 6694, 7157, 7156. | 4136f | Craig Coombe | 2016-05-05 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-12 | 2016-05-05
6690 | Train 1 | TR1 Fin Fan Level | Build Mobile scaffold 1200 high x 1500 long and 900 wide C | 3643 | Mark orr | 2016-04-27 | Chevron | Med Duty | ERECT | complete | 2016-04-30 | 2016-04-29
6690 | TRAIN 1 | TRAIN 1, TAJC TOP LEVEL | Dismantle 8 x mobile scaffolds on Train 1, TAJC Finfans Top Level. Scaffold numbers: 6688, 6690, 6716, 6689, 6721, 6694, 7157, 7156. | 4136h | Craig Coombe | 2016-05-05 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-12 | 2016-05-05
6691 | TBJD | Train2 - TBJD module, 1st fl, temp water pumps | Construct mobile platform (x1) to high point vent lines on overhead pipework. | 3645 | Wayne McCarthy | 2016-04-27 | Mechanical | Med Duty | ERECT | Complete | 2016-04-30 | 2016-05-04
6692 | TBJD | Train2 - TBJD module, 1st fl, temp water pumps | Construct access platform (x1) to high point vent lines on pump pipework | 3646 | Wayne McCarthy | 2016-04-27 | Mechanical | Med Duty | ERECT | Complete | 2016-04-30 | 2016-05-04
6693 | TBJD | Train2 - TBJD module, 1st fl, temp water pumps | Construct access platform (x1) to high point vent lines on pump pipework | 3647 | Wayne McCarthy | 2016-04-27 | Mechanical | Med Duty | ERECT | Complete | 2016-04-30 | 2016-05-04
6694 | Train 1 | TR1 Fin Fan Level | Build Mobile scaffold 1200 high x 1500 long and 900 wide D | 3648 | Mark orr | 2016-04-28 | Chevron | Med Duty | ERECT | complete | 2016-04-28 | 2016-04-29
6694 | TRAIN 1 | TRAIN 1, TAJC TOP LEVEL | Dismantle 8 x mobile scaffolds on Train 1, TAJC Finfans Top Level. Scaffold numbers: 6688, 6690, 6716, 6689, 6721, 6694, 7157, 7156. | 4136d | Craig Coombe | 2016-05-05 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-12 | 2016-05-05
6695 | SITEWIDE - TBA | Sitewide | Takeover Scaffold TAG NO: | 3651 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-28
6696 | MOF | SCCN SCCP | Takeover Scaffold TAG NO: 1200 - i0642 | 3652 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-28 | 2016-04-28
6697 | MOF | SCCQ | Takeover Scaffold TAG NO: 1019 | 3653 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-28 | 2016-04-28
6698 | MOF | SCAQ | Takeover Scaffold TAG NO: 931 | 3654 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-28 | 2016-04-28
6699 | MOF | Loop 3 | Takeover Scaffold TAG NO: 754 | 3655 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-28 | 2016-04-28
6700 | MOF | SCCJ | Takeover Scaffold TAG NO: 755 | 3656 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-28 | 2016-04-28
6701 | MOF | SCCT | Takeover Scaffold TAG NO: 778 | 3657 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-28 | 2016-04-28
6702 | MOF | MOF Loop 3 | Takeover Scaffold TAG NO: I 0794 | 3658 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-28 | 2016-04-28
6703 | MOF | MOF Loop 3 | Takeover Scaffold TAG NO: 757 | 3659 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-28 | 2016-04-28
6704 | MOF | SCCY | Takeover Scaffold TAG NO: 752 | 3660 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | complete | 2016-04-28 | 2016-04-29
6705 | MOF | SCCN | Takeover Scaffold TAG NO: NO TAG | 3661 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | complete | 2016-04-28 | 2016-04-29
6706 | MOF | SCBC | Takeover Scaffold TAG NO:i1556 | 3662 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | complete | 2016-04-28 | 2016-04-28
6707 | MOF | SCCV | Takeover Scaffold TAG NO: 762 | 3663 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | complete | 2016-04-28 | 2016-04-29
6708 | MOF | SCBC | Takeover Scaffold TAG NO: 753 | 3664 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | complete | 2016-04-28 | 2016-04-29
6709 | MOF | SCBD | Takeover Scaffold TAG NO: NO TAG | 3665 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | complete | 2016-04-28 | 2016-04-29
6710 | MOF | SCBD | Takeover Scaffold TAG NO: NO TAG | 3666 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | complete | 2016-04-28 | 2016-04-28
6711 | MOF | SCDB | Takeover Scaffold TAG NO: 1854 | 3667 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | complete | 2016-04-28 | 2016-04-28
6712 | MOF | SCBD | Takeover Scaffold TAG NO: 761 | 3668 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | complete | 2016-04-28 | 2016-04-29
6713 | MOF | MOF 1 loop 2 | Construct 13 x Scaffolds to allow access to Weld Packers on Pipe rack at SCCT, SCCS, SCCR, SCCQ, SCCP, SCCN, SCCG, SCCE & SCCD OLD TAG 756 | 991 | Shane shillabeer | 2015-09-18 | Mechanical | Med Duty | MODIFY | Complete | 2015-09-20 | 2015-09-22
6713 | MOF | MOF 1 loop 1 | Modify KJV scaffold support SHIMS 5 bays of loop1 shoes access old TAG 756 | 991 | Martin Reiget | 2015-09-22 | Scaffolding | Med Duty | MODIFY | Complete | 2015-09-22 | 2015-09-22
6713 | MOF | SCAB | Takeover Scaffold TAG NO: 756 | 3669 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | complete | 2016-04-28 | 2016-04-29
6714 | GAGA | Inlet, GAGA ground Level / South west corner piping | Please provide small deck for access to allow installation of pipe support steel work allowing for full encapsulation Number 1 GAGA, Ground level south west corner near small skid | 3670 | Rick Muston | 2016-04-28 | Mechanical | Med Duty | ERECT | Complete | 2016-04-02 | 2016-05-07
6715 | GAGA | Inlet, GAGA ground Level / South west corner piping | Please provide small deck for access to allow installation of pipe support steel work allowing for full encapsulation Number 2 GAGA, Ground level south west corner near small skid | 3671 | Rick Muston | 2016-04-28 | Mechanical | Med Duty | ERECT | Complete | 2016-04-02 | 2016-05-07
6716 | Train 2 | TR1 Fin Fan Level | Build Mobile scaffold 1200 high x 1500 long and 900 wide F | 3673 | Mark orr | 2016-04-28 | Chevron | Med Duty | ERECT | complete | 2016-04-28 | 2016-04-29
6716 | TRAIN 1 | TRAIN 1, TAJC TOP LEVEL | Dismantle 8 x mobile scaffolds on Train 1, TAJC Finfans Top Level. Scaffold numbers: 6688, 6690, 6716, 6689, 6721, 6694, 7157, 7156. | 4136g | Craig Coombe | 2016-05-05 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-12 | 2016-05-05
6717 | L13/14 | Jetty L13/L14 | Modify Tubes and Kick boards to allow access for welding tag NA | 3674 | Adam Keown | 2016-04-28 | Electrical | Med Duty | MODIFY | Complete | 2016-05-04 | 2016-05-03
6718 | L11/12 | Jetty L11/L12 | Modify Tubes and Kick boards to allow access for welding tag 625 | 3675 | Adam Keown | 2016-04-28 | Electrical | Med Duty | MODIFY | Complete | 2016-05-04 | 2016-05-04
6719 | L7/8 | Jetty L7/L8 | Modify Tubes and Kick boards to allow access for welding tag 15 L7 | 3676 | Adam Keown | 2016-04-28 | Electrical | Med Duty | MODIFY | Complete | 2016-05-04 | 2016-05-04
6720 | L5/6 | SR3679 - Jetty L5/L6 | Please remove temp handrailing to allow access for the welding of handrail butts | 3679 | Adam Keown | 2016-04-28 | Electrical | Med Duty | MODIFY | Complete | 2016-05-05 | 2016-05-03
6721 | Train 1 | TR1 Fin Fan Level | Build Mobile scaffold 1200 high x 1500 long and 900 wide E | 3672 | Mark orr | 2016-04-28 | Chevron | Med Duty | ERECT | complete | 2016-04-28 | 2016-04-29
6721 | TRAIN 1 | TRAIN 1, TAJC TOP LEVEL | Dismantle 8 x mobile scaffolds on Train 1, TAJC Finfans Top Level. Scaffold numbers: 6688, 6690, 6716, 6689, 6721, 6694, 7157, 7156. | 4136e | Craig Coombe | 2016-05-05 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-12 | 2016-05-05
6722 | Jetty | MD4W | Takeover Scaffold TAG NO: 858 | 3680 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-28 | 2016-04-30
6723 | Jetty | MD4W | Takeover Scaffold TAG NO: no tag | 3681 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-28 | 2016-04-30
6724 | Jetty | BD4W | Takeover Scaffold TAG NO: no tag | 3682 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-28 | 2016-04-30
6725 | Jetty | BD4W | Takeover Scaffold TAG NO: 137 | 3683 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-28 | 2016-04-30
6726 | Jetty | BD4W | Takeover Scaffold TAG NO: 1041 | 3684 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-28 | 2016-04-30
6727 | A | Jetty | Takeover Scaffold TAG NO: 904 a | 3685 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | ERECT | complete | 2016-04-28 | 2016-04-29
6728 | A | Jetty | Takeover Scaffold TAG NO: 903 abuttment work shop | 3686 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | ERECT | complete | 2016-04-28 | 2016-04-29
6729 | A | Jetty | Takeover Scaffold TAG NO: 49A | 3687 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | ERECT | complete | 2016-04-28 | 2016-04-29
6730 | A | Jetty | Takeover Scaffold TAG NO: 226 Abutt office | 3688 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | ERECT | complete | 2016-04-28 | 2016-04-29
6731 | MOF | SCBE | Takeover Scaffold TAG NO: I 852 | 3689 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | complete | 2016-04-28 | 2016-04-28
6732 | A | Jetty | Offfice stairs Takeover Scaffold TAG NO: 420 | 3690 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | ERECT | complete | 2016-04-28 | 2016-04-29
6732 | A | Jetty | Dismantle - Offfice stairs Takeover Scaffold TAG NO: 420 | 3690 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-04-28 | 2016-05-10
6733 | A | Jetty | Takeover Scaffold TAG NO: 437 - 2nd lvl | 3691 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | ERECT | complete | 2016-04-28 | 2016-04-29
6734 | A | Jetty | Takeover Scaffold TAG NO: stair access to tug boat | 3692 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | ERECT | complete | 2016-04-28 | 2016-04-29
6734 | MOF | MOF | Dismantle bridge scaffold @ bottom of Abbutmemt | 4529 | George Fomin | 2016-05-24 | Mechanical | Med Duty | ERECT | Complete | 2016-05-24 | 2016-05-24
6735 | A | Jetty | Takeover Scaffold TAG NO: 455 ie room humpy | 3693 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | ERECT | complete | 2016-04-28 | 2016-04-29
6736 | A | Jetty | Takeover Scaffold TAG NO: 50 A | 3694 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | ERECT | complete | 2016-04-28 | 2016-04-29
6737 | A | Jetty | Modify Scaffold TAG NO: 646 | 3695 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | MODIFY | complete | 2016-04-28 | 2016-04-29
6737 | A | Jetty | Takeover Scaffold TAG NO: 646 | 3695 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | complete | 2016-04-28 | 2016-04-29
6737 | A | Jetty | Dismantled Scaffold TAG NO: 646 | 3695 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-04-28 | 2016-05-10
6738 | A | Jetty | Takeover Scaffold TAG NO: 52 A | 3696 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | ERECT | complete | 2016-04-28 | 2016-04-29
6739 | A | Jetty | Takeover Scaffold TAG NO: 516 | 3697 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | ERECT | complete | 2016-04-28 | 2016-04-29
6740 | A | Jetty | Takeover Scaffold TAG NO: 48A | 3698 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | ERECT | complete | 2016-04-28 | 2016-04-29
6741 | A | Jetty | Takeover Scaffold TAG NO: 945 | 3699 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | ERECT | complete | 2016-04-28 | 2016-04-29
6742 | A | Jetty | Takeover Scaffold TAG NO: 516 A | 3700 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | ERECT | complete | 2016-04-28 | 2016-04-29
6743 | A | Jetty | Takeover Scaffold TAG NO: 47 A | 3701 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | ERECT | complete | 2016-04-28 | 2016-04-29
6744 | A | Jetty | Takeover Scaffold TAG NO: NO TAG | 3702 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | ERECT | complete | 2016-04-28 | 2016-04-30
6745 | MOF | SCBK | Takeover Scaffold TAG NO: 610a | 3703 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | complete | 2016-04-28 | 2016-04-29
6746 | MOF | JETTY ABUTT | Takeover Scaffold TAG NO: NO TAG | 3704 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | complete | 2016-04-28 | 2016-04-29
6747 | SITEWIDE - TBA | Sitewide | Takeover Scaffold TAG NO: | 3705 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | complete | 2016-04-28 | 2016-04-29
6748 | MOF | JETTY ABUTT | Takeover Scaffold TAG NO: 990 | 3706 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | complete | 2016-04-28 | 2016-04-29
6749 | MOF | SCBJ | Takeover Scaffold TAG NO: NO TAG | 3707 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | complete | 2016-04-28 | 2016-04-29
6750 | MOF | SCJB | Takeover Scaffold TAG NO: 991 | 3708 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | complete | 2016-04-28 | 2016-04-29
6751 | MOF | mof | Takeover Scaffold TAG NO: NO TAG | 3709 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | complete | 2016-04-28 | 2016-04-29
6752 | MOF | SCBF | Takeover Scaffold TAG NO: I2925 | 3710 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | complete | 2016-04-28 | 2016-04-29
6753 | MOF | SCBF | Takeover Scaffold TAG NO: 993 | 3711 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | complete | 2016-04-28 | 2016-04-29
6754 | MOF | JETTY ABUTT | Takeover Scaffold TAG NO: 215a | 3712 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | complete | 2016-04-28 | 2016-04-29
6755 | Jetty | BD3W | Takeover Scaffold TAG NO: 662 | 3713 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-28 | 2016-04-30
6756 | Jetty | BD3W | Takeover Scaffold TAG NO: 823 | 3714 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-28 | 2016-04-30
6756 | Jetty | LPW | Dismantle 6756 | 4514 | Chris Hampson | 2016-05-24 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-24 | 2016-05-24
6756 | LPW | LPW | Dismantle up & over access on LPW | 4515 | Chris Hampson | 2016-05-24 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-24 | 2016-05-24
6757 | Jetty | LPW LEVEL 1 | Takeover Scaffold TAG NO: NO tag | 3715 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-28 | 2016-04-30
6757 | Jetty | LPW LEVEL 1 | Dismantle 6757 | 3715 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-04-28 | 2016-05-10
6758 | Jetty | LPW | Takeover Scaffold TAG NO: 449 | 3716 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-28 | 2016-04-30
6758 | LPW | LPW | Dismantle hung up & over access on LPW | 4514 | Chris Hampson | 2016-05-24 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-24 | 2016-05-24
6759 | Jetty | LPW TOP LEVEL | Takeover Scaffold TAG NO: 1072 | 3717 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-28 | 2016-04-30
6759 | Jetty | LPW TOP LEVEL | Dismantle 6759 | 3717 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-04-28 | 2016-05-10
6760 | Jetty | LPW | Takeover Scaffold TAG NO: 468 | 3718 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-28 | 2016-04-29
6761 | SITEWIDE - TBA | Sitewide | Takeover Scaffold TAG NO: | 3719 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-28 | 2016-05-02
6761 | LPW | PW-SAYN | Dismantle | 4485 | Martin Riegert | 2016-05-21 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-28 | 2016-05-22
6762 | SITEWIDE - TBA | Sitewide | Takeover Scaffold TAG NO: | 3720 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-28 | 2016-05-02
6763 | SITEWIDE - TBA | Sitewide | Takeover Scaffold TAG NO: | 3721 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-28
6764 | SITEWIDE - TBA | Sitewide | Takeover Scaffold TAG NO: | 3722 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-28 | 2016-05-02
6765 | SITEWIDE - TBA | Sitewide | Takeover Scaffold TAG NO: | 3723 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-28 | 2016-05-01
6766 | SITEWIDE - TBA | Sitewide | Takeover Scaffold TAG NO: | 3724 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-28 | 2016-05-02
6767 | SITEWIDE - TBA | Sitewide | Takeover Scaffold TAG NO: | 3725 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-28 | 2016-05-01
6768 | SITEWIDE - TBA | Sitewide | Takeover Scaffold TAG NO: | 3726 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-28 | 2016-05-02
6769 | SITEWIDE - TBA | Sitewide | Takeover Scaffold TAG NO: | 3727 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-28 | 2016-05-02
6770 | SITEWIDE - TBA | Sitewide | Takeover Scaffold TAG NO: | 3728 | Murray Wetere | 2016-04-28 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-28 | 2016-05-02
6771 | AGRU 2 | AGRU 2 TAG D1410 | Takeover Scaffold TAG NO: D1410 AGRU 2 ABAA HM-2007 level 3 south needs to extend scaffold north 2m from hand rails to access line 2H 11001 for insulation/painting works, keep a 225mm clearance from pipe works | 3729 | TROY BRAND | 2016-04-28 | Hertel | Med Duty | Takeover | Complete | 2016-04-28 | 2016-05-01
6771 | Agru 2 | AGRU2 | Takeover scaffold D1410 as per email request from Hertel | 3759 | TROY BRAND | 2016-04-29 | Hertel | Med Duty | Takeover | Complete | 2016-04-01 | 2016-05-02
6771 | Agru 2 | AGRU2 | Dismantle scaffold D1410 as per email request from Hertel | 3759 | TROY BRAND | 2016-04-29 | Hertel | Med Duty | DISMANTLE | Complete | 2016-04-08 | 2016-05-02
6772 | Inlet | enermech yard | URGENT SCAFFOLD REQUIRED TO INSTALL ACUATOR BACK ON TOP OF 40TONNE VALVE FOR TESTING AT THE ENERMECH YARD. | 3732 | Rick Muston | 2016-04-29 | Mechanical | Med Duty | ERECT | Complete | 2016-04-29 | 2016-05-07
6773 | Train 3 | TR3 3V 1510 | Dismantle all Internal scaffolding from vessel. | 3733 | Mark orr | 2016-04-29 | Chevron | Med Duty | DISMANTLE | Complete | 2016-04-29 | 2016-04-29
6774 | Train 1 | TR1 Fin Fan Level | Build Mobile scaffold 1200 high x 1500 long and 900 wide G | 3734 | Mark orr | 2016-04-29 | Chevron | Med Duty | ERECT | Complete | 2016-04-29 | 2016-04-30
6775 | SADA | SADA | SADA HM-2038 Line# OB-62170-04 Sub System RSI720 Access needed to pipe for installation of ZAP Protection Est location on line. | 3738 | Troy Brand | 2016-04-29 | Hertel | Med Duty | ERECT | Complete | 2016-05-05 | 2016-05-06
6776 | SADA | SADA | SADA HM-2039 Line# OB-62170-04 Sub System RSI720 Access needed to pipe for installation of ZAP Protection Wst location on line. | 3739 | Troy Brand | 2016-04-29 | Hertel | Med Duty | ERECT | Complete | 2016-05-05 | 2016-05-04
6777 | SADA | SADA | SADA HM-2040 Line# OB-62170-04 Sub System RSI720 Access needed to pipe for installation of ZAP Protection Wst location on line. | 3740 | Troy Brand | 2016-04-29 | Hertel | Med Duty | ERECT | Complete | 2016-05-05 | 2016-05-04
6778 | INLET | Inlet laydown area | Erect scaffolding humpy and hard barricading for laydown area. | 3741 | Kevin Hegarty | 2016-04-29 | Scaffolding | Med Duty | ERECT | Complete | 2016-05-05 | 2016-05-23
6779 | INLET | Inlet laydown area | erect scaffold storage racks in container 2 | 3742 | Kevin Hegarty | 2016-04-29 | Scaffolding | Med Duty | ERECT | complete | 2016-05-05 | 2016-05-24
6780 | INLET | Inlet laydown area | erect scaffold storage racks in container | 3743 | Kevin Hegarty | 2016-04-29 | Scaffolding | Med Duty | ERECT | complete | 2016-05-05 | 2016-05-24
6781 | INLET | Inlet laydown area | Erect scaffold storage rack | 3744 | Kevin Hegarty | 2016-04-29 | Scaffolding | Med Duty | ERECT | Not Started | 2016-05-05
6782 | Jetty | Jetty | modify stairwell at tug pens | 703 | Mark Orr | 2015-07-26 | scaffolding | Med Duty | MODIFY | Complete | 2015-07-26 | 2015-07-26
6782 | Jetty | Jetty | modify stairwell at tug pens | 703 | Mark Orr | 2015-07-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-07-26 | 2015-07-26
6783 | Jetty | L6 | Scaff required at L6 DOMGAS, as per model shot SR166 | 705 | Mark Orr | 2015-08-21 | scaffolding | Med Duty | MODIFY | Complete | 2015-08-21 | 2015-08-21
6783 | Jetty | L6 | Scaff required at L6 DOMGAS, as per model shot SR166 | 705 | Mark Orr | 2015-08-21 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-08-21 | 2015-08-21
6784 | Jetty | Jetty - L13 | Scaffold Modification at L13 to fit Life buoy | 428 | Mark Orr | 2015-08-02 | scaffolding | Med Duty | ERECT | Complete | 2015-08-02 | 2015-08-02
6785 | Jetty | Jetty - LPW-Road side | Erect Scaffold to allow access to Flange | 435 | Mark Orr | 2015-08-02 | scaffolding | Med Duty | MODIFY | Complete | 2015-08-02 | 2015-08-02
6785 | Jetty | Jetty - LPW-Road side | Erect Scaffold to allow access to Flange | 435 | Mark Orr | 2015-08-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-08-02 | 2015-08-02
6786 | Jetty | JAA1 | JAA Ground level under grid mesh please errect scaffold to access pipe weld for blasting and painting | 450 | Mark Orr | 2015-08-24 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-08-24 | 2015-08-24
6787 | Jetty | Jetty | Extend existing scaffolding at right hand side of tee intersection to support new cable ladde as per existing setup. | 454 | Mark Orr | 2015-08-24 | scaffolding | Med Duty | MODIFY | Complete | 2015-08-24 | 2015-08-24
6787 | Jetty | Jetty | Extend existing scaffolding at right hand side of tee intersection to support new cable ladde as per existing setup. | 454 | Mark Orr | 2015-08-24 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-08-24 | 2015-08-24
6788 | Jetty | Jetty - MD4W | Install scaffold gates to allow for Rope access personnel to remove grid Mesh | 402 | Mark Orr | 2015-07-31 | scaffolding | Med Duty | MODIFY | Complete | 2015-07-31 | 2015-07-31
6788 | Jetty | Jetty - MD4W | Install scaffold gates to allow for Rope access personnel to remove grid Mesh | 402 | Mark Orr | 2015-07-31 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-07-31 | 2015-07-31
6789 | Jetty | Jetty - LPW | Erect Scaffold for LPW flange access | 427 | Mark Orr | 2015-08-02 | scaffolding | Med Duty | MODIFY | Complete | 2015-08-02 | 2015-08-02
6789 | Jetty | Jetty - LPW | Erect Scaffold for LPW flange access | 427 | Mark Orr | 2015-08-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-08-02 | 2015-08-02
6790 | Jetty | Jett - L11 | Scaffold Modification at L11 to fit Life buoy | 429 | Mark Orr | 2015-08-02 | scaffolding | Med Duty | MODIFY | Complete | 2015-08-02 | 2015-08-02
6790 | Jetty | Jett - L11 | Scaffold Modification at L11 to fit Life buoy | 429 | Mark Orr | 2015-08-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-08-02 | 2015-08-02
6791 | Jetty | Jetty JH5 | Extend esisting scaffold at right hand side of Tee intersection to support new cable ladder as per existing set up | 449 | Mark Orr | 2015-08-24 | scaffolding | Med Duty | MODIFY | Complete | 2015-08-24 | 2015-08-24
6791 | Jetty | Jetty JH5 | Extend esisting scaffold at right hand side of Tee intersection to support new cable ladder as per existing set up | 449 | Mark Orr | 2015-08-24 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-08-24 | 2015-08-24
6792 | Jetty | Jetty - Berthing Docks East | Remove existing scaffold Build Underside Deck-Install/weld Access stairs | 406 | Mark Orr | 2015-07-31 | scaffolding | Med Duty | MODIFY | Complete | 2015-07-31 | 2015-07-31
6792 | Jetty | Jetty - Berthing Docks East | Remove existing scaffold Build Underside Deck-Install/weld Access stairs | 406 | Mark Orr | 2015-07-31 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-07-31 | 2015-07-31
6793 | Jetty | LPW SAYV | Removal of lifting lug access € | 342 | Mark Orr | 2015-07-27 | scaffolding | Med Duty | MODIFY | Complete | 2015-07-27 | 2015-07-27
6793 | Jetty | LPW SAYV | Removal of lifting lug access € | 342 | Mark Orr | 2015-07-27 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-07-27 | 2015-07-27
6794 | Jetty | Jetty-LPE | Erect scaffold to access light bracket to weld | 1247 | Mark Orr | 2015-10-24 | scaffolding | Med Duty | MODIFY | Complete | 2015-11-18 | 2015-11-18
6794 | Jetty | Jetty-LPE | Erect scaffold to access light bracket to weld | 1247 | Mark Orr | 2015-10-24 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-11-18 | 2015-11-18
6795 | Jetty | LPE & LPW | Provide Access to install Cable Tray and tubing for Cannon @ LPE & LPW | 966 | Mark Orr | 2015-09-14 | scaffolding | Med Duty | MODIFY | Complete | 2015-09-21 | 2015-09-21
6795 | Jetty | LPE & LPW | Provide Access to install Cable Tray and tubing for Cannon @ LPE & LPW | 966 | Mark Orr | 2015-09-14 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-09-21 | 2015-09-21
6796 | Jetty | Jetty - M5 | Install Scaffold at M5 | 615 | Mark Orr | 2015-07-16 | scaffolding | Med Duty | MODIFY | Complete | 2015-07-16 | 2015-07-16
6796 | Jetty | Jetty - M5 | Install Scaffold at M5 | 615 | Mark Orr | 2015-07-16 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-07-16 | 2015-07-16
6797 | Jetty | Jetty | Need to modify existing scaffold to modify Pipe positioning | 382 | Mark Orr | 2015-06-02 | scaffolding | Med Duty | MODIFY | Complete | 2015-06-02 | 2015-06-02
6797 | Jetty | Jetty | Need to modify existing scaffold to modify Pipe positioning | 382 | Mark Orr | 2015-06-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-06-02 | 2015-06-02
6798 |  | Centre over cable tray on beams | Modify Barricading for mesh removal | 510 | Mark Orr | 2015-09-07 | scaffolding | Med Duty | MODIFY | Complete | 2015-09-07 | 2015-09-07
6798 |  | Centre over cable tray on beams | Barricading for mesh removal | 510 | Mark Orr | 2015-09-07 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-09-07 | 2015-09-07
6798 |  | Centre over cable tray on beams | Dismantle 6798 | 510 | Mark Orr | 2015-09-07 | scaffolding | Med Duty | DISMANTLE | Complete | 2015-09-07 | 2015-12-07
6799 | Jetty | Jetty | Erect Scaffold to Cabinet for Hole Drilling works | 383 | Mark Orr | 2015-07-29 | scaffolding | Med Duty | MODIFY | Complete | 2015-07-29 | 2015-07-29
6799 | Jetty | Jetty | Erect Scaffold to Cabinet for Hole Drilling works | 383 | Mark Orr | 2015-07-29 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-07-29 | 2015-07-29
6800 | Jetty | Jetty - LPW - Containers | Erect scaffold tube frame-work for Humpy Build between 2 x Containers | 519 | Mark Orr | 2015-07-03 | scaffolding | Med Duty | MODIFY | Complete | 2015-07-03 | 2015-07-03
6800 | Jetty | Jetty - LPW - Containers | Erect scaffold tube frame-work for Humpy Build between 2 x Containers | 519 | Mark Orr | 2015-07-03 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-07-03 | 2015-07-03
6801 | Jetty | Jetty - T4 Caisson | Erect Humpy for Touch up's | 535 | Mark Orr | 2015-07-07 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-07-07 | 2015-07-07
6802 | Jetty | M4 | Required at M4 as per model shot on req SR163 | 702 | Mark Orr | 2015-07-26 | scaffolding | Med Duty | MODIFY | Complete | 2015-07-26 | 2015-07-26
6802 | Jetty | M4 | Required at M4 as per model shot on req SR163 | 702 | Mark Orr | 2015-07-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-07-26 | 2015-07-26
6803 | Jetty | Jetty - SAYV | Access required to Brackets for Blasting & Painting | 527 | Mark Orr | 2015-09-07 | scaffolding | Med Duty | MODIFY | Complete | 2015-09-07 | 2015-09-07
6803 | Jetty | Jetty - SAYV | Access required to Brackets for Blasting & Painting | 527 | Mark Orr | 2015-09-07 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-09-07 | 2015-09-07
6804 | Jetty | Jetty-L7 SCLZ Fire water | Erect Scaffold around instrumentation ladder for when in stalling cables SCLZ Firewater | 686 | Mark Orr | 2015-08-21 | scaffolding | Med Duty | MODIFY | Complete | 2015-08-21 | 2015-08-21
6804 | Jetty | Jetty-L7 SCLZ Fire water | Erect Scaffold around instrumentation ladder for when in stalling cables SCLZ Firewater | 686 | Mark Orr | 2015-08-21 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-08-21 | 2015-08-21
6805 | Jetty | M1 & M2 | building two permit huts with two entrys | 706 | Mark Orr | 2015-08-21 | scaffolding | Med Duty | MODIFY | Complete | 2015-08-21 | 2015-08-21
6805 | Jetty | M1 & M2 | building two permit huts with two entrys | 706 | Mark Orr | 2015-08-21 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-08-21 | 2015-08-21
6806 | Jetty | Jetty - LPE Module Tie In | Remove top Humpy tubes on upper deck and erect Intermediate Deck to access Uttility Lines | 528 | Mark Orr | 2015-06-30 | scaffolding | Med Duty | ERECT | Complete | 2015-06-30 | 2015-06-30
6807 | Jetty | CT1E | Scaffold along side of CTIE walkway to allow welding of light pole | 2020 | Mark Orr | 2015-10-07 | scaffolding | Med Duty | ERECT | Complete | 2015-10-17 | 2015-10-17
6808 | Jetty | Jetty - SCM1 Substation MOP | Craneable Scaffold Stair Access - Temporary Access to Substation | 392 | Mark Orr | 2015-06-01 | scaffolding | Med Duty | ERECT | Complete | 2015-06-01 | 2015-06-01
6808 | Jetty | Jetty - SCM1 Substation MOP | Craneable Scaffold Stair Access - Temporary Access to Substation | 392 | Mark Orr | 2015-06-01 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-06-01 | 2015-06-01
6809 | Jetty | L10 | Required as per model shot on req SR165 | 701 | Mark Orr | 2015-07-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-07-26 | 2015-07-26
6810 | Jetty | Jetty - MD5W | Install scaffold gates to allow for Rope access personnel to remove grid Mesh | 403 | Mark Orr | 2015-07-31 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-07-31 | 2015-07-31
6811 | Jetty | Jetty | Extend existing scaffold at right hand side of tee intersection to support new cable ladder as per set up. | 458 | Mark Orr | 2015-08-03 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-08-03 | 2015-08-03
6812 | Jetty | Jetty - SCM1 W012 | Erect Scaffold to support 900mm cable tray Ladderat Fer Building - SCM1 | 425 | Mark Orr | 2015-06-06 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-06-06 | 2015-06-06
6813 | Jetty | MAB1-BD2E-BD1E | Scaffold Required to allow workers to access West Side of Bridge Between BD2E & BD4E | 998 | Mark Orr | 2015-09-19 | scaffolding | Med Duty | ERECT | Complete | 2015-09-20 | 2015-09-20
6813 | Jetty | MAB1-BD2E-BD1E | Takeover KJV | 998 | Mark Orr | 2015-09-19 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-09-20 | 2015-09-20
6814 | Jetty | Jetty-LPE | Erect scaffold to access light bracket to weld | 1246 | Mark Orr | 2015-10-24 | scaffolding | Med Duty | ERECT | Complete | 2015-11-17 | 2015-11-17
6815 | Jetty | L10 | Required as per model shot on req SR164 | 700 | Mark Orr | 2015-07-26 | scaffolding | Med Duty | ERECT | Complete | 2015-07-26 | 2015-07-26
6816 | Jetty | M5 | Erect 2 Scaffolds at M5 | 502 | Mark Orr | 2015-08-26 | scaffolding | Med Duty | ERECT | Complete | 2015-08-26 | 2015-08-26
6816 | Jetty | M5 | Takeover KJV | 502 | Mark Orr | 2015-08-26 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-08-26 | 2015-08-26
6817 | Jetty | Jetty - T5 Caisson | Erect Humpy for Touch up's | 534 | Mark Orr | 2015-07-07 | scaffolding | Med Duty | ERECT | Complete | 2015-07-07 | 2015-07-07
6817 | Jetty | Jetty - T5 Caisson | Takeover KJV | 534 | Mark Orr | 2015-07-07 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-07-07 | 2015-07-07
6818 | Jetty | Jetty - SAYV | Modify Scaffold to bolt holes for Painting | 525 | Mark Orr | 2015-07-04 | scaffolding | Med Duty | MODIFY | Complete | 2015-07-04 | 2015-07-04
6818 | Jetty | Jetty - SAYV | Takeover | 525 | Mark Orr | 2015-07-04 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-07-04 | 2015-07-04
6819 | Jetty | MAB2-BD3E-BD4E | Scaffold Required to allow workers to access West Side of Bridge Between BD3E & BD4E | 999 | Mark Orr | 2015-09-19 | scaffolding | Med Duty | MODIFY | Complete | 2015-09-20 | 2015-09-20
6819 | Jetty | MAB2-BD3E-BD4E | Takeover | 999 | Mark Orr | 2015-09-19 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-09-20 | 2015-09-20
6819 | Jetty | L5 | Dismantle L5 acccesss blocking valve on top of SCKH | 4522 | Chris Hampson | 2016-05-24 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-24 | 2016-05-24
6819 | L5/6 | L5 jetty | Dismantle access blocking valve on top of the SCKH module at L5 | 4522 | Chris Hampson | 2016-05-24 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-24 | 2016-05-24
6820 | Jetty | Jetty - LPE | Extend H/Rail on edge of LPE to allow permanent H/rail removal - Jackup W/Way | 414 | Mark Orr | 2015-06-05 | scaffolding | Med Duty | MODIFY | Complete | 2015-06-05 | 2015-06-05
6820 | Jetty | Jetty - LPE | Takeover | 414 | Mark Orr | 2015-06-05 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-06-05 | 2015-06-05
6821 | Jetty | Jetty LPE | Req no HM087 LPE North East Access neede for fire water line brackets and painting. | 886 | Mark Orr | 2015-09-02 | scaffolding | Med Duty | MODIFY | Complete | 2015-09-15 | 2015-09-15
6821 | Jetty | Jetty LPE | take over | 886 | Mark Orr | 2015-09-02 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-09-15 | 2015-09-15
6824 | Jetty | Jetty - HLF | Scaffold required to hold Temporary MEG Line - Craneable | 415 | Mark Orr | 2015-08-01 | scaffolding | Med Duty | MODIFY | Complete | 2015-08-01 | 2015-08-01
6824 | Jetty | Jetty - HLF | Scaffold required to hold Temporary MEG Line - Craneable | 415 | Mark Orr | 2015-08-01 | scaffolding | Med Duty | TAKEOVER | Complete | 2015-08-01 | 2015-08-01
6825 | SAH1 | SAH1 - Condy tank area | Erect scaffold - SAH1 see attached module | 3745 | Mathew Poole | 2016-04-29 | Electrical | Med Duty | ERECT | Complete | 2016-05-05 | 2016-05-16
6825 | SAH1 | SAH1 - Condy tank area | Modify scaffold extention | 3745 | Mathew Poole | 2016-04-29 | Electrical | Med Duty | MODIFY | Complete | 2016-05-05 | 2016-05-17
6826 | SAH1 | SAH1 - Condy tank area | Erect scaffold - SAH1 see attached module | 3746 | Mathew Poole | 2016-04-29 | Electrical | Med Duty | Erect | Not Started | 2016-05-05
6827 | SAH1 | SAH1 - Condy tank area | Erect scaffold - SAH1 see attached module | 3747 | Mathew Poole | 2016-04-29 | Electrical | Med Duty | ERECT | Complete | 2016-05-05 | 2016-05-13
6828 | SAH1 | SAH1 - Condy tank area | Erect scaffold - SAH1 see attached module | 3748 | Mathew Poole | 2016-04-29 | Electrical | Med Duty | ERECT | Complete | 2016-05-05 | 2016-05-07
6828 | SAH | Condi tanks east wall SAH1 | Modification in three locations at scaffold on west side of condensate tank 3 to allow for cable ladder to be installed | 4502 | Glenn Beckett | 2016-05-22 | Mechanical | Med Duty | ERECT | Not Started | 2016-05-28
6829 | SADA | SADA | FABRICATE SCAFFOLD UNDERNEATH 0K-3401-KM1A TO ALLOW RELOCATION OF VIBRATION SENSORS FROM INSIDE THE GUARD TO EXTERNAL OF MOTOR HOUSING | 3749 | Brian Gray | 2016-04-29 | Electrical | Med Duty | ERECT | Complete | 2016-05-06 | 2016-05-08
6830 | SADA | SADA | FABRICATE SCAFFOLD UNDERNEATH 0K-3401-KM1B TO ALLOW RELOCATION OF VIBRATION SENSORS FROM INSIDE THE GUARD TO EXTERNAL OF MOTOR HOUSING | 3750 | Brian Gray | 2016-04-29 | Electrical | Med Duty | ERECT | Complete | 2016-05-06 | 2016-05-08
6831 | SADA | SADA | FABRICATE SCAFFOLD UNDERNEATH 0K-3402-KM1A TO ALLOW RELOCATION OF VIBRATION SENSORS FROM INSIDE THE GUARD TO EXTERNAL OF MOTOR HOUSING | 3751 | Brian Gray | 2016-04-29 | Electrical | Med Duty | ERECT | Complete | 2016-05-06 | 2016-05-08
6832 | SADA | SADA | FABRICATE SCAFFOLD UNDERNEATH 0K-3402-KM1B TO ALLOW RELOCATION OF VIBRATION SENSORS FROM INSIDE THE GUARD TO EXTERNAL OF MOTOR HOUSING | 3752 | Brian Gray | 2016-04-29 | Electrical | Med Duty | ERECT | Complete | 2016-05-06 | 2016-05-08
6833 | Agru 1 | AGRU 2 - Top Deck | Build mobile access deck at AGRU2 for acess to fin fan high point vents. (See attached model shot) Has to be able to traverse under each loop, to allow access to the top of each spool. | 3753 | Wayne McCarthy | 2016-04-29 | Mechanical | Med Duty | ERECT | Complete | 2016-04-30 | 2016-05-05
6834 | RBDE | RBDE / RBDQ | Dismantle the Downer scaffold on the nth side of RBDE rack to allow CPB to dig V drain | 3754 | Mike Hemming | 2016-04-29 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-10 | 2016-05-14
6835 | RBDE | RBDE / Pipe rack | Dismantle the base of the stair access A033 (CK) on the nth side of RBDE/RBDQrack to allow CPB to dig V drain | 3755 | Mike Hemming | 2016-04-29 | Mechanical | Med Duty | Dismantle | Not Started | 2016-05-10
6837 | Train 3 | TR3 3V 1510 | Erect access scaffold for vessel entry | 3760 | Mark orr | 2016-04-29 | Chevron | Med Duty | ERECT | complete | 2016-04-08 | 2016-04-29
6837 | Train 3 | TR3 3V 1510 | Dismantle | 3760 | Mark orr | 2016-04-29 | Chevron | Med Duty | ERECT | Complete | 2016-04-08 | 2016-05-17
6838 | Train 3 | TR3 3V 1510 | Dismantle Access Scaffold for vessel entry | 3761 | Mark orr | 2016-04-29 | Chevron | Med Duty | ERECT | Complete | 2016-04-08 | 2016-05-03
6839 | GAA1 | GAA1 pump A - inlet | Erect Scaffold to access buttwelds at pump A inlet | 3762 | Shane Shillabeer | 2016-04-30 | Mechanical | Med Duty | ERECT | Complete | 2016-04-05 | 2016-05-10
6840 | GAA1 | GAA1 pump B- inlet | Erect Scaffold to access buttwelds at pump B inlet | 3763 | Shane Shillabeer | 2016-04-30 | Mechanical | Med Duty | ERECT | Complete | 2016-04-05 | 2016-05-05
6840 | GAA1 | GAA1 pump B- inlet | Modify scaffold | 3763 | Shane Shillabeer | 2016-04-30 | Mechanical | Med Duty | MODIFY | Complete | 2016-04-05 | 2016-05-18
6841 | GAA1 | GAA1 pump C - inlet | Erect Scaffold to access buttwelds at pump C inlet | 3764 | Shane Shillabeer | 2016-04-30 | Mechanical | Med Duty | ERECT | Complete | 2016-04-05 | 2016-05-15
6842 | GAA1 | GAA1 pump A- inlet | Erect Scaffold to access buttwelds on raiser at pump A inlet | 3765 | Shane Shillabeer | 2016-04-30 | Mechanical | Med Duty | ERECT | Complete | 2016-04-05 | 2016-05-11
6843 | GAA1 | GAA1 pump B - inlet | Erect Scaffold to access buttwelds on raiser at pump B inlet | 3766 | Shane Shillabeer | 2016-04-30 | Mechanical | Med Duty | ERECT | complete | 2016-04-05 | 2016-05-05
6844 | GAA1 | GAA1 pump C - inlet | Erect Scaffold to access buttwelds on raiser at pump C inlet | 3767 | Shane Shillabeer | 2016-04-30 | Mechanical | Med Duty | ERECT | Complete | 2016-04-05 | 2016-05-03
6845 | Agru 2 | Agru 2 | remove AGRU 2 rigging and SMP loft from the south end - ground level. client has requested the strip as commissioning will fence up area within 2 weeks. | 3768 | David Goodes | 2016-04-30 | Electrical | Med Duty | ERECT | Complete | 2016-04-05 | 2016-05-02
6846 | ABAA | ABAA | Handrail extension in AGRU2 on vessel 2V-1101 as per attached | 4074 | Geoff Haren | 2016-04-30 | Mechanical | Med Duty | Erect | Not Started | 2016-05-03
6847 | ABAA | ABAA | Build Hard barricade to facilitate gridmesh removal (See attached model shot) | 4075 | Wayne McCarthy | 2016-04-30 | Mechanical | Med Duty | ERECT | Complete | 2016-05-01 | 2016-05-05
6848 | ABAC | ABAC | Hop up is required for Catalyst loading on the T2 AGRU MRU Vessel: 2C-1105Flange: UC1Hop up is required to reach the Dump nozzle on the front of the vessel.See Andrew Ledingham for walkaround of moduleIndependent BirdcageSee attached photo's/model shots | 4076 | Andrew Ledingham | 2016-05-01 | Sulzer | Med Duty | ERECT | Complete | 2016-05-10 | 2016-05-05
6849 | ABAC | ABAC | Hop up is required for Catalyst loading on the T2 AGRU MRU Vessel: 2C-1105Flange: M2Hop up is required to access manway on the side of the vessel.See Andrew Ledingham for walkaround of moduleIndependent Birdcage See attached photo's/model shots | 4077 | Andrew Ledingham | 2016-05-01 | Sulzer | Med Duty | ERECT | Complete | 2016-05-10 | 2016-05-08
6849 |  | 2C-1105 | Dismantle Scaffold at bottom of man weay on 2C-1105 | 4675 | Graham Galloway | 2016-05-26 | Mechanical | Med Duty | Dismantle | Complete | 2016-05-26 | 2016-05-26
6850 | ABAC | ABAC | Hop up is required for Catalyst loading on the T2 AGRU MRU Vessel Vessel: 2C-1105 Flange: N1 & M1Scaff is required for the top elbow/pig pen/hopper hop up. This all ties in as oneScaffold.SeeAndrew Ledingham for walkaround of module IndependentBirdcageSee attached photo's/model shots | 4078 | Andrew Ledingham | 2016-05-01 | Sulzer | Med Duty | ERECT | Complete | 2016-05-10 | 2016-05-16
6851 | Jetty | L1 JETTY | TAKEOVER TAGS | 3771 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-02
6852 | Jetty | L3 NORTH END | TAKEOVER TAGS | 3772 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-02
6853 | Jetty | L3 SOUTH | TAKEOVER TAGS | 3773 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-02
6854 | Jetty | L3/L4 TRUSS BRIDGE | TAKEOVER TAGS | 3774 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-02
6855 | Jetty | L4 | TAKEOVER TAGS | 3775 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-02
6856 | Jetty | L3 SOUTH | TAKEOVER TAGS | 3776 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-04-02
6857 | Jetty | L3 | TAKEOVER TAGS | 3777 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-02
6858 | Jetty | L3 | TAKEOVER TAGS | 3778 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-02
6859 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3779 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-02
6860 | Jetty | L5 ACCESS TO BOTTOM | TAKEOVER TAGS 126 | 3780 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-02
6860 | Jetty | L5 | Dismantle 1st access from walkway | 4524 | Chris Hampson | 2016-05-24 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-24 | 2016-05-24
6860 | L5/6 | L5 jetty | Dismantle 1nd access from walkway to L5 caison | 4524 | Chris Hampson | 2016-05-24 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-24 | 2016-05-24
6861 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3781 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-02
6861 | Jetty | L5 | Dismantle 2nd access from walkway | 4523 | Chris Hampson | 2016-05-24 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-24 | 2016-05-24
6861 | L5/6 | L5 jetty | Dismantle 2nd access from walkway to L5 caison | 4523 | Chris Hampson | 2016-05-24 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-24 | 2016-05-24
6862 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3782 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-02
6863 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3783 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-02
6863 | Jetty | L5 | Dismantle 3rd access | 4521 | Chris Hampson | 2016-05-24 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-24 | 2016-05-24
6863 | L5/6 | L5 jetty | Dismantle 3rd access from walkway to L5 caison | 4521 | Chris Hampson | 2016-05-24 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-24 | 2016-05-24
6864 | MOF | L5 STH END TRUSS | TAKEOVER TAGS 7 | 3784 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-02
6865 | MOF | L5 STH END TRUSS | TAKEOVER TAGS 4 | 3785 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-02
6866 | MOF | L5 EAST/END TRUSS | TAKEOVER TAGS 3 | 3786 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-02
6867 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3787 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-02
6868 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3788 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-02
6869 | Jetty | L6 NORTH/SOUTH | TAKEOVER TAGS | 3789 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-02
6870 | Jetty | L5 EAST/BOTTOM | TAKEOVER TAGS 964 | 3790 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-02
6871 | Jetty | L5 EAST BOTTOM | TAKEOVER TAGS | 3791 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-02
6872 | Jetty | L5 NORTHSIDE WALKWAY | TAKEOVER TAGS | 3792 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-04-02
6873 | Jetty | L5 TOP DECK FIRE WATER | TAKEOVER TAGS | 3793 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-02
6874 | Jetty | L5 MAIN SCAFFOLD (DROPPY) | TAKEOVER TAGS | 3794 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-02
6875 | Jetty | L5 SOUTH/SIDE | TAKEOVER TAGS | 3795 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-02
6876 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3796 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-02
6877 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 13 | 3797 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-05
6878 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 1016 | 3798 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-05
6879 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3799 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-03
6880 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3800 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-05
6881 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3801 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-03
6882 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 1014 | 3802 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-05
6883 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS I2391 | 3803 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6884 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 338 | 3804 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6885 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 85 | 3805 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6886 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 165 | 3806 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6887 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 597 | 3807 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6888 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 597 | 3808 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6889 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 12 | 3809 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6890 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 118 | 3810 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6891 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 422 | 3811 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6892 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 618 | 3812 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6893 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 619 | 3813 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6894 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 619 | 3814 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6895 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 501 | 3815 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6896 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 119 | 3816 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6897 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 628 | 3817 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6898 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 163 | 3818 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6899 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 1012 | 3819 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6900 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 783 | 3820 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6901 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 73 | 3821 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6902 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 330 | 3822 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6903 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 331 | 3823 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6904 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 332 | 3824 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6905 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3825 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6906 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 1056 | 3826 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6907 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 975 | 3827 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6908 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 620 | 3828 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6909 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 976 | 3829 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6909 | Jetty | L9 | Dismantle 2 access walkway to L9 Cassion | 4518 | Chris Hampson | 2016-05-24 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-24 | 2016-05-24
6909 | L9/10 | L9/L10 | Dismantle 2nd access from walkway to L9 caison | 4518 | Chris Hampson | 2016-05-24 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-24 | 2016-05-24
6910 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 1042 | 3830 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6911 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 117 | 3831 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6912 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 1000 | 3832 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6913 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 1079 | 3833 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6914 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3834 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6915 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3835 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6916 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3836 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6917 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 1182 | 3837 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6918 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 625 | 3838 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6918 | Jetty | L11 | Dismantle 6918 | 4516 | Chris Hampson | 2016-05-24 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-24 | 2016-05-24
6919 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 985 | 3839 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6920 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3840 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6921 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 627 | 3841 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6922 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 626 | 3842 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6923 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 895 | 3843 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6924 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3844 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6925 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3845 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6926 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 81 | 3846 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6927 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 127 | 3847 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6928 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 313 | 3848 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6929 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 205 | 3849 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6930 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 147 | 3850 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6930 | Jetty | M1 | Dismantle 6930 | 4525 | Chris Hampson | 2016-05-24 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-24 | 2016-05-24
6930 | M1 | M1/2 | Dismantle up & over access on M1/M2 Caisson | 4525 | Chris Hampson | 2016-05-24 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-24 | 2016-05-24
6931 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3851 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6932 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 772 | 3852 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6933 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 487 | 3853 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6934 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 185 | 3854 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6935 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 1196 | 3855 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6936 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 80 | 3856 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6937 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3857 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6938 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3858 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6939 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 607 | 3859 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | complete | 2016-04-30 | 2016-05-05
6939 | Jetty | M5 | Dismantle 6936 walkway M5 caission | 4515 | Chris Hampson | 2016-05-24 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-24 | 2016-05-24
6939 | L11 | Jetty | Dismantle access from alkway ro L11 caisson | 4516 | Chris Hampson | 2016-05-24 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-24 | 2016-05-24
6940 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 942 | 3860 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-05
6941 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 699 | 3861 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-05
6942 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3862 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-05
6943 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3863 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-05
6944 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3864 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-05
6945 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 1169 | 3865 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-05
6946 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3866 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-05
6947 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3867 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-05
6948 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 1174 | 3868 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-05
6949 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 1168 | 3869 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-05
6950 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3870 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-05
6951 | L13 | JETTY - L13 | TAKEOVER TAGS 551 | 3871 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-05
6951 | L13 | JETTY - L13 | Dismantle 6951 | 3871 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-04-30 | 2016-05-10
6952 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3872 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
6953 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3873 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
6954 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3874 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
6955 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3875 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
6956 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3876 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
6957 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3877 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
6958 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3878 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
6959 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3879 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
6960 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3880 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
6961 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3881 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
6962 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3882 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
6963 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3883 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
6964 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3884 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
6965 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3885 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
6966 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3886 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-05
6967 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 972 | 3887 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-05
6967 | Jetty | L9 | Dismantle 6967 | 4519 | Chris Hampson | 2016-05-24 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-24 | 2016-05-24
6967 | L9/10 | L9 Jetty | Dismantle access from walkway to L9 caison | 4519 | Chris Hampson | 2016-05-24 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-24 | 2016-05-24
6968 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 207 | 3888 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-05
6969 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3889 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-05
6970 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 1175 | 3890 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-05
6971 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS I1709 | 3891 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-06
6972 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS I1540 | 3892 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-06
6973 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS I1549 | 3893 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-06
6974 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS I1802 | 3894 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-06
6975 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS I955 | 3895 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-06
6976 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 928 | 3896 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-06
6977 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 414 | 3897 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-06
6978 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 15 | 3898 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-06
6978 | Jetty | L7 | Dismantle 6978 L7 | 4520 | Chris Hampson | 2016-05-24 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-24 | 2016-05-24
6978 | L7 | L7 | Dismantle access from walkway to L7 caison | 4520 | Chris Hampson | 2016-05-24 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-24 | 2016-05-24
6979 | SITEWIDE - TBA | AREA 3 - HERTEL COMPOUND | TAKEOVER TAGS | 3899 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-07
6980 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS I2676 | 3900 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-07
6981 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS I0947 | 3901 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-07
6982 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 2647 | 3902 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-07
6983 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 36 | 3903 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-08
6984 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 111 | 3904 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-08
6985 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 1170 | 3905 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-08
6986 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 860 | 3906 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-08
6987 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3907 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-08
6988 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 235 | 3908 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-08
6988 | LPW | Jetty | Dismantle Scaffol 6988 | 4404 | Mike Brown | 2016-05-17 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-18 | 2016-05-18
6989 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3909 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-08
6990 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3910 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-08
6991 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3911 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-08
6992 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 904 | 3912 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-11
6993 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 549 | 3913 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-11
6994 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 986 | 3914 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-11
6995 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3915 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-11
6996 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3916 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-11
6997 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3917 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-11
6998 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3918 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-11
6999 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3919 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-11
7000 | Area 2 | DAB | TAKEOVER TAGS Intrim 016 | 3920 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-12
7001 | MOF | SCAB | TAKEOVER TAGS I 2509 | 3921 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-12
7002 | MOF | Loop 6 | TAKEOVER TAGS N/A | 3922 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-12
7003 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3923 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-04-30
7004 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3924 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-12
7005 | RBDS | Train 3 - RBDS | TAKEOVER TAGS A2211 | 3925 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-12
7006 | Jetty | Jetty | TAKEOVER TAGS 950 | 3926 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-14
7007 | Jetty | Jetty | TAKEOVER TAGS 139 | 3927 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-14
7008 | Jetty | Jetty | TAKEOVER TAGS 356 | 3928 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-14
7009 | Jetty | MD1W | TAKEOVER TAGS 319 | 3929 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-14
7010 | Jetty | MD1W | TAKEOVER TAGS 432 | 3930 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-14
7011 | Jetty | BD1E | TAKEOVER TAGS NA | 3931 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-14
7012 | Jetty | BD2E | TAKEOVER TAGS 616 | 3932 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-14
7013 | Jetty | BD2E | TAKEOVER TAGS 141 | 3933 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-14
7014 | MD4E | jetty | Modify TAKEOVER TAGS 154 | 3934 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | MODIFY | Complete | 2016-04-30 | 2016-05-16
7014 | MD4E | jetty | TAKEOVER TAGS 154 | 3934 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-16
7015 | MD4W | Jetty | Modify TAKEOVER TAGS 153 | 3935 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | MODIFY | Complete | 2016-04-30 | 2016-05-16
7015 | MD4W | Jetty | TAKEOVER TAGS 153 | 3935 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-16
7016 | MD5W | Jetty | Modify TAKEOVER TAGS 396 | 3936 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | MODIFY | Complete | 2016-04-30 | 2016-05-16
7016 | MD5W | Jetty | TAKEOVER TAGS 396 | 3936 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-16
7017 | MD6W | Jetty | Modify TAKEOVER TAGS 156 | 3937 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | MODIFY | Complete | 2016-04-30 | 2016-05-16
7017 | MD6W | Jetty | TAKEOVER TAGS 156 | 3937 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-16
7018 | MD6W | Jetty | Modify TAKEOVER TAGS 789 | 3938 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | MODIFY | Complete | 2016-04-30 | 2016-05-16
7018 | MD6W | Jetty | TAKEOVER TAGS 789 | 3938 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-16
7019 | MD5E | Jetty | odify TAKEOVER TAGS na | 3939 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | MODIFY | Complete | 2016-04-30 | 2016-05-16
7019 | MD5E | Jetty | TAKEOVER TAGS na | 3939 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-16
7020 | MD4E | Jetty | Modify TAKEOVER TAGS 187 | 3940 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Modify | Complete | 2016-04-30 | 2016-05-16
7020 | MD4E | Jetty | TAKEOVER TAGS 187 | 3940 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-16
7021 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3941 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-10
7022 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3942 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-10
7023 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3943 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7024 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3944 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7025 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3945 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7026 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3946 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7027 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3947 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7028 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3948 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7029 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3949 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7030 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3950 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7031 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3951 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7032 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3952 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7033 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3953 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7034 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3954 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7035 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3955 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7036 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3956 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7037 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3957 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7038 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3958 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7039 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3959 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7040 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3960 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7041 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3961 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7042 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3962 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7043 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3963 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7044 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3964 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7045 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3965 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7046 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3966 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7047 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3967 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7048 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3968 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7049 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3969 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7050 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3970 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7051 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3971 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7052 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3972 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7053 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3973 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7054 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3974 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7055 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3975 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7056 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3976 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7057 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3977 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7058 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3978 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7059 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3979 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7060 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3980 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7061 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3981 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7062 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3982 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7063 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3983 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7064 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3984 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7065 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3985 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7066 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3986 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7067 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3987 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7068 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3988 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7069 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3989 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7070 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3990 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7071 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3991 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7072 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3992 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7073 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3993 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7074 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3994 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7075 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3995 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7076 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3996 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7077 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3997 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7078 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3998 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7079 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 3999 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7080 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4000 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7081 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4001 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7082 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4002 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7083 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4003 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7084 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4004 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7085 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4005 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7086 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4006 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7087 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4007 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7088 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4008 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7089 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4009 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7090 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4010 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7091 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4011 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7092 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4012 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7093 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4013 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7094 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4014 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7095 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4015 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7096 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4016 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7097 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4017 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7098 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4018 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7099 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4019 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7100 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4020 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7101 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4021 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7102 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4022 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7103 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4023 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7104 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4024 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7105 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4025 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7106 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4026 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7107 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4027 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7108 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4028 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7109 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4029 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7110 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4030 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7111 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4031 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7112 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4032 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7113 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4033 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7114 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4034 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7115 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4035 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7116 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4036 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7117 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4037 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7118 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4038 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7119 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4039 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7120 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4040 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7121 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4041 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7122 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4042 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7123 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4043 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7124 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4044 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7125 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4045 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7126 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4046 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7127 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4047 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7128 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4048 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7129 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4049 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7130 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4050 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7131 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4051 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7132 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4052 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7133 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4053 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7134 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4054 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7135 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4055 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7136 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4056 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7137 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4057 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7138 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4058 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7139 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4059 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7140 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4060 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7141 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4061 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7142 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4062 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7143 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4063 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7144 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4064 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7145 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4065 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7146 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4066 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7147 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4067 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7148 | TBAA | level 3 | Modify Scaffold takover to be able to access safely | 4068 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | MODIFY | Complete | 2016-04-30 | 2016-05-15
7148 | TBAA | level 3 | TAKEOVER TAGS No tag - TBAA | 4068 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Complete | 2016-04-30 | 2016-05-15
7149 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4069 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7150 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4070 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7151 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4071 | Murray Wetere | 2016-04-30 | Scaffolding | Med Duty | Takeover | Not Started | 2016-04-30
7152 | GACA | GACA | Dismantle TAGS G1199 | 4079 | Kevin Hegarty | 2016-05-01 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-06 | 2016-05-12
7152 | GACA | GACA | TAKEOVER TAGS G1199 | 4079 | Kevin Hegarty | 2016-05-01 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-12
7153 | DOMGAS | DOMGAS | Scaffold to work on spring can on Domgas module for CSU Model attached. | 4080 | Bob Brevker | 2016-05-02 | Chevron | Med Duty | ERECT | Cancelled | 2016-05-02
7154 | TAFA | TAFA | TAKEOVER TAGS | 4081 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Cancelled | 2016-05-06
7155 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4082 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-03
7156 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4083 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-03
7156 | TRAIN 1 | TRAIN 1, TAJC TOP LEVEL | Dismantle 8 x mobile scaffolds on Train 1, TAJC Finfans Top Level. Scaffold numbers: 6688, 6690, 6716, 6689, 6721, 6694, 7157, 7156. | 4136b | Craig Coombe | 2016-05-05 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-12 | 2016-05-05
7157 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4084 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-03
7157 | TRAIN 1 | TRAIN 1, TAJC TOP LEVEL | Dismantle 8 x mobile scaffolds on Train 1, TAJC Finfans Top Level. Scaffold numbers: 6688, 6690, 6716, 6689, 6721, 6694, 7157, 7156. | 4136c | Craig Coombe | 2016-05-05 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-12 | 2016-05-05
7158 | TACA | Level 4 train 1 - TACA | Mobile scaffold. TAKEOVER. Scaff TAG# | 4085 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-04
7158 | TACA | Level 4 train 1 - TACA | Dismatle 7158 | 4085 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-06 | 2016-05-10
7159 | TACA | Train | TAKEOVER TAGS | 4086 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-06
7159 | TACA | Train | Dismantle TAKEOVER TAGS | 4086 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-06 | 2016-05-21
7160 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS 1086 | 4087 | Michael Stephens | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-11
7160 |  |  | Not use yet | 4087 | Cecil Ngaheu |  | Scaffolding | Med Duty
7161 | UAEA | under finfans | TAKEOVER TAGS A2262 | 4088 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-07
7161 | UAEA | under finfans | Modify TAGS A2262 | 4088 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-06 | 2016-05-19
7162 | RBFA | INLET | MODIFY TAKEOVER TAGS I-2990 | 4089 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-06 | 2016-05-15
7162 | UAEA | UAEA | MODIFY TAKEOVER TAGS A-2263 | 4089 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-06 | 2016-05-18
7162 | RBFA | INLET | TAKEOVER TAGS I-2990 | 4089 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-18
7162 | UAEA | UAEA | TAKEOVER TAGS A-2263 | 4089 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-18
7163 | sah1 | SAH1 - Condensate Tanks | Modify TAKEOVER TAGS i3082 | 4090 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-06 | 2016-05-15
7163 | sah1 | SAH1 - Condensate Tanks | TAKEOVER TAGS i3082 | 4090 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-15
7164 | MAJ | MAJ | Mod TAKEOVER TAGS 1045 | 4091 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-06 | 2016-05-15
7164 | MAJ | MAJ | TAKEOVER TAGS 1045 | 4091 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-15
7165 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS - Interim TAG no: 4212 | 4092 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-09
7166 | MAJ | jetty | TAKEOVER TAGS 1052 | 4093 | Murray Wetere | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-14
7166 | BD3E | jetty | TAKEOVER TAGS 125 | 4093 | Murray Wetere | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-14
7167 | DAAA | DAAA | Modify TAKEOVER TAGS mas 2456 | 4094 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-06 | 2016-05-14
7167 | maj | maj | Modify TAKEOVER TAGS 923 | 4094 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-06 | 2016-05-14
7167 | DAAA | DAAA | TAKEOVER TAGS mas 2456 | 4094 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-14
7167 | maj | maj | TAKEOVER TAGS 923 | 4094 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-14
7168 | MAJ | MAJ | MODIFY TAKEOVER TAGS 896 | 4095 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-06 | 2016-05-14
7168 | MAJ | MAJ | TAKEOVER TAGS 896 | 4095 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-14
7168 | UAEA | UAEA | MODIFY TAKEOVER TAGS No 4 | 4095 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-06 | 2016-05-19
7168 | UAEA | UAEA | TAKEOVER TAGS No.4 | 4095 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-19
7169 | TACA | MAJ | MODIFY TAKEOVER TAGS B2642 | 4096 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-06 | 2016-05-14
7169 | MAJ | MAJ | MODIFY TAKEOVER TAGS 900 | 4096 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-06 | 2016-05-14
7169 | TACA | MAJ | TAKEOVER TAGS B2642 | 4096 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-14
7169 | MAJ | MAJ | TAKEOVER TAGS 900 | 4096 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-14
7169 | TACA | TR1 1st Level TACA | Dismantle scaffold 7169 on TACA 4th Level | 4506 | Denny Shewell | 2016-05-22 | Chevron | Med Duty | DISMANTLE | Not Started | 2016-05-28
7170 | MAJ | MAJ | TAKEOVER TAGS 901 | 4097 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-14
7170 | MAJ | MAJ | Modify TAKEOVER TAGS 901 | 4097 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-06 | 2016-05-18
7171 | SITEWIDE - TBA | Sitewide | Modify | 4098 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-06 | 2016-05-11
7171 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4098 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-11
7172 | maj | maj | TAKEOVER TAGS 891 | 4099 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-06 | 2016-05-18
7172 | maj | maj | TAKEOVER TAGS 891 | 4099 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-18
7173 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4100 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-12
7173 | DAAA | Domgas | Dismantle | 4380 | Trevor Pike | 2016-05-16 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-16 | 2016-05-15
7174 |  | Demin Shed | Modify TAKEOVER TAGS No 7 | 4101 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-06 | 2016-05-18
7174 | MAJ | MAJ | Modify TAKEOVER TAGS 710 | 4101 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-06 | 2016-05-18
7174 |  | Demin Shed | TAKEOVER TAGS No 7 | 4101 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-18
7174 | MAJ | MAJ | TAKEOVER TAGS 710 | 4101 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-18
7175 | UAG1 | UAG1 | Modify TAKEOVER TAGS 41946 | 4102 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-06 | 2016-05-18
7175 | MAJ | MAJ | Modify TAKEOVER TAGS 868 - 656 - 862 | 4102 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-06 | 2016-05-18
7175 | UAG1 | UAG1 | TAKEOVER TAGS 41946 | 4102 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-18
7175 | MAJ | MAJ | TAKEOVER TAGS 868 - 656 - 862 | 4102 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-18
7176 | MAJ | MAJ | Modify TAKEOVER TAGS 709 | 4103 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-06 | 2016-05-18
7176 | MAJ | MAJ | TAKEOVER TAGS 709 | 4103 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-18
7176 | UAGA | UAGA | Modify TAKEOVER TAGS 709 | 4103 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-06 | 2016-05-19
7176 | UAGA | UAGA | TAKEOVER TAGS 709 | 4103 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-19
7177 | UAGA | UAGA | Modify TAKEOVER TAGS MAS A2214 | 4104 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-06 | 2016-05-18
7177 | TAJA | Train level 1 | Modify TAKEOVER TAGS MAS 4711 | 4104 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-06 | 2016-05-18
7177 | UAGA | UAGA | TAKEOVER TAGS MAS A2214 | 4104 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-18
7177 | TAJA | Train level 1 | TAKEOVER TAGS MAS 4711 | 4104 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-18
7178 | MAJ | MAJ | Modify TAKEOVER TAGS 718 | 4105 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-06 | 2016-05-18
7178 | MAJ | MAJ | TAKEOVER TAGS 718 | 4105 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-18
7179 | MAJ | MAJ | Modify TAKEOVER TAGS B2642 | 4106 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-06 | 2016-05-21
7179 | MAJ | MAJ | TAKEOVER TAGS B2642 | 4106 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-21
7180 | MAJ | MAJ | ModifyTAKEOVER TAGS 1203 | 4107 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-06 | 2016-05-18
7180 | MAJ | MAJ | TAKEOVER TAGS 1203 | 4107 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-18
7181 | GADA | Top Level | Modify TAKEOVER TAGS MAS A-2292 | 4108 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-06 | 2016-05-18
7181 | GADA | Top Level | TAKEOVER TAGS MAS A-2292 | 4108 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-18
7182 | GADA | Level 2 | Modify TAKEOVER TAGS MAS 2472 | 4109 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-06 | 2016-05-18
7182 | GADA | Level 2 | TAKEOVER TAGS MAS 2472 | 4109 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-18
7182 | GADA | Gada - Inlet | Dismantle 7182 / A1872 | 4408 | Mark orr | 2016-05-19 | Scaffolding | Med Duty | ERECT | Complete | 2016-05-19
7183 | TBAA | TBAA level 3 | Modify Takeover access | 4110 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-06 | 2016-05-15
7183 | TBAA | TBAA level 3 | TAKEOVER TAGS TBAA Train 2 Lvl 3 | 4110 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-15
7183 | TBAA | TBAA level 3 | Dismantle Lifting Frames TBAA level 3 | 4476 | Cecil Ngaheu | 2016-05-21 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-28 | 2016-05-21
7184 | TBAA | TBAA level 2 | Modify TAKEOVER TAGS | 4111 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-06 | 2016-05-23
7184 | TBAA | TBAA level 2 | TAKEOVER TAGS | 4111 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-23
7184 | TBAA | TBAA level 3 | Dismantle Lifting Frames TBAA level 3 | 4477 | Cecil Ngaheu | 2016-05-21 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-28 | 2016-05-23
7185 | TBAA | TBAA level 2 | Modify Takeover access | 4113 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-06 | 2016-05-15
7185 | TBAA | TBAA level 2 | TAKEOVER TAGS TBAA Train 2 Lvl 3 213PSV004A | 4113 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-15
7185 | TBAA | TBAA level 3 | Dismantle Lifting Frames TBAA level 3 | 4478 | Cecil Ngaheu | 2016-05-21 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-28 | 2016-05-21
7185 | TBBA | TR 2 TBBA | Dismantle 7185 | 4478 | Brett Taane | 2016-05-21 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-28 | 2016-05-22
7186 | TBAA | TBAA level 3 | Modify Takeover access | 4114 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-06 | 2016-05-15
7186 | TBAA | TBAA level 3 | TAKEOVER TAGS TBAA Train 2 Lvl 3 | 4114 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-15
7186 | TBAA | TBAA level 3 | Dismantle Lifting Frames TBAA level 3 | 4479 | Cecil Ngaheu | 2016-05-21 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-28 | 2016-05-21
7186 | TBBA | TR 2 TBBA | Dismantle 7186 | 4479 | Brett Taane | 2016-05-21 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-28 | 2016-05-22
7187 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4115 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-06 | 2016-05-03
7187 | SITEWIDE - TBA | Sitewide | Mod TAKEOVER TAGS - Interim TAG no: 4212 | 4315 | Cecil Ngaheu | 2016-05-02 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-06 | 2016-05-15
7188 | AGRU 2 | RL40 | Strip out scaffold (CKJV SCAFFOLD) which is preventing us from installing RV ladder and handrails. | 4120 | David Goodes | 2016-05-03 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-04 | 2016-05-12
7189 | ABAG | ABAG | Build scaffold at south end of RV platform to allow for handrail and walkway modifications. Arrange a walk down with supervisor prior to build as there are small details that need to be allowed for. | 4121 | David Goodes | 2016-05-03 | Mechanical | Med Duty | Dismantle | Not Started | 2016-05-04
7190 | M1 | RWJ/M1 JETTY | Dismantle existing access to spool deck from pedestrian path. Construct lower scaff deck below pedestrian path at M1 to allow installation of handrail. Construct alternate access/egree to spool deck. | 4122 | Adam Keown | 2016-05-03 | Mechanical | Med Duty | Dismantle | Not Started | 2016-05-09
7191 | BIBBY | BIBBY/AMT CRUSADER | Erect lifting frame and handrails for removal of AMT crusader Pump motor and grid mesh. | 4123 | Mike Hemming | 2016-05-04 | Mechanical | Med Duty | ERECT | Complete | 2016-05-15 | 2016-05-15
7192 | INLET | INLET LAYDOWN AREA | APTS are receiving a 10ft PSV testing container. It is due to land on theisland on the 05/05/2016. It will be unsure when it gets places in the Inlet area. What we require is some scaffold erected to provide shade and shelving on the outside of the container around three sides. | 4124 | Tim Whiffin | 2016-05-04 | APTS | Med Duty | ERECT | Complete | TBA | 2016-05-27
7193 | BD2W | LPW/BD2W | Dismantle cable tray waterfall access | 4125 | Martin Riegert | 2016-05-04 | Scaffolding | Med Duty | Dismantle | Not Started | 2016-05-11
7194 | Jetty | L5/L6 | Dismantle scaffold preventing access to valve platform. | 4126 | Martin Riegert | 2016-05-04 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-11 | 2016-05-06
7195 | LPW | L9/L10 | Dismantle scaffolding preventing access to valve platform. | 4127 | Martin Riegert | 2016-05-04 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-11 | 2016-05-25
7196 | LPW | LPW | Dismantle structural chartek access. Tag no: 468 LPW | 4128 | Martin Riegert | 2016-05-04 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-11 | 2016-05-25
7197 | LPW | LPW | Dismantle structural chartek access. Tag no: 1072 LPW | 4129 | Martin Riegert | 2016-05-04 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-11 | 2016-05-25
7198 | LPW | LPW | Dismantle E&I cable tray dance floor | 4130 | Martin Riegert | 2016-05-04 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-11 | 2016-05-15
7199 | LPW | LPW | Dismantle all redundant handrails | 4131 | Martin Riegert | 2016-05-04 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-11 | 2016-05-25
7200 | LPW | LPW | Dismantle level 1 LNG line cladding access | 4132 | Martin Riegert | 2016-05-04 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-11 | 2016-05-25
7201 | M2 | M2 | Dismantle spool deck under LNG line elbows | 4133 | Martin Riegert | 2016-05-04 | Scaffolding | Med Duty | Dismantle | Not Started | 2016-05-11
7202 | M4 | M4 | Dismantle spool deck under LNG line elbows. Tag no: 207 M4 | 4134 | Martin Riegert | 2016-05-04 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-11 | 2016-05-22
7203 | SAH1 | SAH1 - Condensate Tanks | Require existing scaffold to be stripped so Electrical team can install cable ladder where this scaffold has been erected. This scaffold has been erected on the Eastern Wall, outside of the condy tanks main bund wall. | 4135 | Gavin Hughes | 2016-05-04 | Electrical | Med Duty | Dismantle | Not Started | 2016-04-10
7205 | TRAIN 1 | TRAIN 1, TACA VESSEL 1533, LEVEL 3 | Erect scaffold inside vessel 1533 Tag# 4444 Module TACA | 4137 | Trevor Pike | 2016-05-05 | Mechanical | Med Duty | SHUTDOWN-ERECT | Complete | 2016-05-05 | 2016-05-05
7205 | TRAIN 1 | TRAIN 1, TACA VESSEL 1533, LEVEL 3 | Dismantle scaffold inside vessel 1533 Tag# 4444 Module TACA | 4137 | Trevor Pike | 2016-05-05 | Mechanical | Med Duty | SHUTDOWN-DISMANTLE | Complete | 2016-05-05 | 2016-05-09
7206 | ABAA | V21101 - ABAA | Dismantle scaffold that is blocking CKJV's work in Agru 2. | 4138 | Alistair Nicholas | 2016-05-05 | Scaffolding | Med Duty | Dismantle | Not Started | 2016-05-12
7207 | LPW | JETTY L7/L8 | Erect scaffold humpy over storage cabinet (52078/7) @ L7/L8 to fully enclose hot works. | 4139 | Adam Keown | 2016-05-05 | Mechanical | Med Duty | ERECT | Complete | 2016-05-12 | 2016-05-25
7208 | MOF | M1 - MOF | Partial dismantle of layher underhung (N/W CNR M1 - Sea escape platform area) to allow install of structural ladder. | 4140 | Blur | 2016-05-05 | APS | Med Duty | DISMANTLE | Complete | 2016-05-05 | 2016-05-07
7209 | ENERMECH YARD | ENERMECH YARD | Strip scaffold for 40T valve in the enermech testing facility | 4141 | Rick Muston | 2016-05-05 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-12 | 2016-05-15
7210 | INLET | INLET, GAGA, Ground Level | Provide access for installing cable tray frame. | 4142 | Mark Farley | 2016-05-05 | Mechanical | Med Duty | ERECT | Complete | 2016-05-07 | 2016-05-10
7211 | INLET | INLET, JADA, Ground Level | Provide access for installing cable tray frame. | 4143 | Mark Farley | 2016-05-05 | Mechanical | Med Duty | ERECT | Complete | 2016-05-07 | 2016-05-10
7212 | INLET | GAC 1/WEST | Please remove temporary stair access. | 4144 | Paul Cummins | 2016-05-05 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-12 | 2016-05-12
7213 | INLET | INLET, GAGA, 1st Level | Modifications required to allow better access for pipe welds x 3 locations. | 4145 | Mark Farley | 2016-05-05 | Mechanical | Med Duty | MODIFY | Cancelled | 2016-05-07
7214 | GAC1 | GAC 1 | Provide access to modify/weld ladder hoops x 2 locations | 4146 | Mark Farley | 2016-05-05 | Mechanical | Med Duty | ERECT | Not Started | 2016-05-07
7215 | GAGA | GAGA, 1st Lvl | Build scaffold to allow for encaptulation | 4147 | Mark Farley | 2016-05-05 | Mechanical | Med Duty | ERECT | Not Started | 2016-05-12
7216 | GAGA | GAGA, 1st Lvl | Build scaffold to allow for encaptulation | 4148 | Mark Farley | 2016-05-05 | Mechanical | Med Duty | ERECT | Complete | 2016-05-12 | 2016-05-21
7217 | TACA | TACA Train 1 | Erect Hand Rail on the top level west side of Train 1 TACA to support Hertel. | 4150 | Luke Geiger | 2016-05-06 |  | Med Duty | ERECT | Complete | 2016-05-06 | 2016-05-09
7218 | TRAIN 2 | TBAA, Sth grid mesh level 1 | TBAA HM-2062 Lower and modify scaffold deck to access flanges and pipe work for insulation boxes. Note: Deck to be lowered 900mm and have third handrail to allow trade work off safe step. | 4151 | James Halliday | 2016-05-06 | Hertel | Med Duty | MODIFY | Complete | 2016-05-10 | 2016-05-08
7219 | TRAIN 2 | TBAA, Sth grid mesh level 1 | TBAA HM-2063 Lower and modify scaffold deck to access flanges and pipe work for insulation boxes. Note: Deck to be lowered 900mm and have third handrail to allow trade work off safe step. | 4152 | James Halliday | 2016-05-06 | Hertel | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-08
7220 | RBCA | RBCA | RBCA HM-2064 Tag 6427 Extend scaffold NTH 1500mm to allow for the insulatoin of PPE. | 4153 | Troy Brand | 2016-05-06 | Hertel | Med Duty | MODIFY | Cancelled | 2016-05-15
7221 | SAYN | SAYN | SAYN HM-2056 Structural steel needs paint and Chartek lift will need to be lowered there is no access or tag for this scaffold so no reference number can be given. | 4154 | Troy Brand | 2016-05-06 | Hertel | Med Duty | MODIFY | Cancelled | 2016-05-09
7222 | RBCA | RBCA EST | RBCA HM-2057 Est Tag 1855 Move back boards and tube to allow room to install PPE box. | 4155 | Troy Brand | 2016-05-06 | Hertel | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-18
7223 | RBCA | RBCA EST | RBCA HM-2058 Est west of pipe Tag 1558 Move back boards and tube to allow room to install PPE box. | 4156 | Troy Brand | 2016-05-06 | Hertel | Med Duty | MODIFY | Complete | 2016-05-12 | 2016-05-18
7224 | RBCA | RBCA | RBCA HM-2059 Tag 1993 Move back boards and tube to allow room to install PPE box. | 4157 | Troy Brand | 2016-05-06 | Hertel | Med Duty | ERECT | Complete | 2016-05-13 | 2016-05-18
7225 | RBCA | RBCA | RBCA HM -2060 Erect scaffold to allow for the installation of valve PPE box. | 4158 | Troy Brand | 2016-05-06 | Hertel | Med Duty | ERECT | Complete | 2016-05-13 | 2016-05-18
7226 | RBCA | ref to dnc 4159 | RBCA HM -2064 Erect scaffold Nth 1500mm to allow for the insulation of PPE. | 4159 | Troy Brand | 2016-05-06 | Hertel | Med Duty | MODIFY | Complete | 2016-05-15 | 2016-05-18
7727 | GACA | GAGA | Scaffold request for 10H00-06. Scaffolding required for the installation of support brackets. Scaffold as per attached drawing. | 4160 | Ian Pritchard | 2016-05-06 | Electrical | Med Duty | ERECT | complete | 2016-05-16 | 2016-05-23
7728 | BD1W | BD1W | Dismantle drop scaffold for rope edge protection, including Handrails and scaffold above gridmesh level. Remove all materials. | 4161 | Martin Riegert | 2016-05-06 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-06 | 2016-05-15
7729 | BD2W | BD2W | Dismantle Handrails and scaffold above gridmesh level. Remove all materials. | 4162 | Martin Riegert | 2016-05-06 | Scaffolding | Med Duty | Dismantle | Not Started | ASAP
7730 | LPW | LPW/BD2W | Dismantle cable tray waterfall access | 4163 | Martin Riegert | 2016-05-06 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-06 | 2016-05-25
7731 | BD3W | BD3W | Dismantle Handrails and scaffold above gridmesh level. Remove all materials. | 4164 | Martin Riegert | 2016-05-06 | Scaffolding | Med Duty | Dismantle | Not Started | ASAP
7732 | BD4W | BD4W | Dismantle scaffold for rope edge protection, including Handrails and scaffold above girdmesh level. Remove all materials. | 4165 | Martin Riegert | 2016-05-06 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-06 | 2016-05-15
7733 | CT4W | CT4W | Dismantle southern junction box scaffold (on CT4W walkway) | 4166 | Martin Riegert | 2016-05-06 | Scaffolding | Med Duty | Dismantle | Not Started | ASAP
7734 | CT4W | CT4W | Dismantle northern junction box scaffold (on CT4W walkway) | 4167 | Martin Riegert | 2016-05-06 | Scaffolding | Med Duty | Dismantle | Not Started | ASAP
7735 | MD1 | MD1 | Dismantle sea escape platform drop scaffold | 4168 | Martin Riegert | 2016-05-06 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-06 | 2016-05-21
7735 | MD1 | MD1 | Erect sea escape platform drop scaffold | 4168 | Martin Riegert | 2016-05-06 | Scaffolding | Med Duty | ERECT | Complete | 2016-05-19 | 2016-05-19
7736 | MD2 | MD2 | Dismantle Handrails and scaffold above gridmesh level. Remove all materials. | 4169 | Martin Riegert | 2016-05-06 | Scaffolding | Med Duty | Dismantle | Not Started | ASAP
7737 | MD2 | MD2 | Dismantle sea escape platform drop scaffold | 4170 | Martin Riegert | 2016-05-06 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-06 | 2016-05-21
7738 | MD3 | MD3 | Dismantle Handrails and scaffold above gridmesh level. Remove all materials. | 4171 | Martin Riegert | 2016-05-06 | Scaffolding | Med Duty | Dismantle | Not Started | ASAP
7739 | MD3 | MD3 | Dismantle sea escape platform drop scaffold | 4172 | Martin Riegert | 2016-05-06 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-06 | 2016-05-21
7739 | MD3 | MD3 | Erect sea escape platform drop scaffold | 4172 | Martin Riegert | 2016-05-06 | Scaffolding | Med Duty | ERECT | Complete | 2016-05-19 | 2016-05-19
7740 | MD4W | MD4W | Dismantle Handrails and scaffold above gridmesh level. Remove all materials. | 4173 | Martin Riegert | 2016-05-06 | Scaffolding | Med Duty | Dismantle | Not Started | ASAP
7741 | MD5W | MD5W | Dismantle Handrails and scaffold above gridmesh level. Remove all materials. | 4174 | Martin Riegert | 2016-05-06 | Scaffolding | Med Duty | Dismantle | Not Started | ASAP
7742 | MD6W | MD6W | Dismantle Handrails and scaffold above gridmesh level. Remove all materials. | 4175 | Martin Riegert | 2016-05-06 | Scaffolding | Med Duty | Dismantle | Not Started | ASAP
7743 | GACA | GACA | Require scaffolds to access light fittings. LF - DB8382-E01-05W-03 (See attached drawing G1-TD-E-0901-LED0116) LF - DB8382-E01-05W-01 (See attached drawing G1-TD-E-0901-LED0116) LF - DB8382-E01-05W-03 (See attached drawing G1-TD-E-0901-LED0124) LF - DB8382-E01-05W-04 (See attached drawing G1-TD-E-0901-LED0123) LF - DB8382-E01-05W-06 (See attached drawing G1-TD-E-0901-LED0124). Also see attached highlighted photographs. | 4176 | Bruce Stephenson | 2016-05-06 | Electrical | Med Duty | ERECT | complete | 2016-05-08 | 2016-05-24
7744 | TBF1 | TRAIN 2, TBF1 | Dismantle scaffolding inside vessel | 4177 | Jason Princen | 2016-05-06 | Mechanical | Med Duty | Dismantle | Not Started | 2016-05-13
7745 | TBF1 | TRAIN 2, TBF1 | Dismantle scaffolding inside vessel | 4178 | Jason Princen | 2016-05-06 | Mechanical | Med Duty | Dismantle | Not Started | 2016-05-13
7746 | GACA | 09D00-10 GACA | Dismantle scaffold as per attached drawings | 4179 | Ian Pritchard | 2016-05-06 | Electrical | Med Duty | DISMANTLE | Complete | 2016-05-16 | 2016-05-24
7746 | GACA | 09D00-10 GACA | Modify scaffold as per attached drawings | 4179 | Ian Pritchard | 2016-05-06 | Electrical | Med Duty | MODIFY | Complete | 2016-05-16 | 2016-05-24
7747 | SAH1 | INSIDE TANK 1 BUND (GROUND LEVEL) | 2 Mobile scaffold frames to be built for hot works, needs to be able to be lifted by a crane. Leave 2 ends open so able to go over pipework. Wheels to be attached. | 4180 | Daniel Edwards | 2016-05-06 | Mechanical | Med Duty | ERECT | Not Started | 2016-05-08
7748 | SAH1 | OUTSIDE NORTH WALL TANK 1 (GROUND LEVEL) | 2 Mobile scaffold frames to be built for hot works, needs to be able to be lifted by a crane. Leave 2 ends open so able to go over pipework. Wheels to be attached. | 4181 | Daniel Edwards | 2016-05-06 | Mechanical | Med Duty | ERECT | Complete | 2016-05-08 | 2016-05-15
7749 | DAAA | DAAA 3rd Level | Reinstate access to S/E cnr DAAA Domgas for Red Spade removal #351 | 4182 | Jeff Menzie | 2016-05-06 | Mechanical | Med Duty | MODIFY | Not Started | ASAP
7750 | Abutment Office Area | Abutment Office Area | Dismantle bridge scaffold next to generator #6730 | 4183 | Martin Riegert | 2016-05-06 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-06 | 2016-05-24
7751 | Abutment Office Area | Abutment Office Area | Dismantle tube and clip access to air conditioner between old white crib rooms. #6734 | 4184 | Martin Riegert | 2016-05-06 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-06 | 2016-05-24
7752 | Abutment Office Area | Abutment Office Area | Dismantle modular accss to old meeting room #6737 | 4185 | Martin Riegert | 2016-05-06 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-06 | 2016-05-24
7754 | Abutment Office Area | Abutment Office Area | Dismantle pre-start humpy next to Hertel crib room #6735 | 4187 | Martin Riegert | 2016-05-06 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-06 | 2016-05-24
7755 | Abutment Office Area | Abutment Office Area | Dismantle redundant handrails around abutment office/crib room area (including QA office aircon support) | 4188 | Martin Riegert | 2016-05-06 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-06 | 2016-05-24
7756 | LPW | JETTY L8 | Erect scaffold on existing walkway to allow for full hot works encapsualation. Under pipe rack SCKL @ L8 Jetty | 4189 | Adam Keown | 2016-05-06 | Mechanical | Med Duty | ERECT | Complete | 2016-05-11 | 2016-05-25
7757 | SAH1 | INSIDE TANK 2 BUND (GROUND LEVEL) | 2 Mobile scaffold frames to be built for hot works, needs to be able to be lifted by a crane. Leave 2 ends open so able to go over pipework. Wheels to be attached. | 4190 | Daniel Edwards | 2016-05-06 | Mechanical | Med Duty | ERECT | Not Started | 2016-05-13
7758 | TRAIN 1 | TRAIN 1, TACA, LEVEL 3 | Dismantle scaffold on Train 1 TACA, level vessel 1531 Scaff Tag No: 6598 | 4191a | Trevor Pike | 2016-05-06 |  | Med Duty | DISMANTLE | Complete | 2016-05-06 | 2016-05-09
7758 | TRAIN 1 | TRAIN 1, TACA, LEVEL 3 | Dismantle scaffold on Train 1 TACA, level vessel 1531 Scaff Tag No: 6597 | 4191b | Trevor Pike | 2016-05-06 |  | Med Duty | DISMANTLE | Complete | 2016-05-06 | 2016-05-09
7758 | TRAIN 1 | TRAIN 1, TACA, LEVEL 3 | Dismantle scaffold on Train 1 TACA, level vessel 1530 Scaff Tag No: 6596 | 4191c | Trevor Pike | 2016-05-06 |  | Med Duty | DISMANTLE | Complete | 2016-05-06 | 2016-05-09
7758 | TRAIN 1 | TRAIN 1, TACA, LEVEL 3 | Dismantle scaffold on Train 1 TACA, level vessel 1530 Scaff Tag No: 6595 | 4191d | Trevor Pike | 2016-05-06 |  | Med Duty | DISMANTLE | Complete | 2016-05-06 | 2016-05-09
7759 | TRAIN 1 | TACA | Dismantle of scaffold in V1-1530 TACA Train 1 | 4192 | Wilfred Nahona | 2016-05-07 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-14 | 2016-05-09
7760 | TACA | TRAIN 1 TACA Level 3 | Build 3x scaffolds to access actutator valve on Train 1 Level 3 | 4193 | Trevor Pike | 2016-05-07 | Chevron | Med Duty | ERECT | Complete | 2016-05-07 | 2016-05-18
7760 | TACA | TRAIN 1 TACA Level 3 | Dismantle 7760 | 4371 | Trevor Pike | 2016-05-17 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-17 | 2016-05-16
7761 | TRAIN 1 | TRAIN 1 TACA Level 3 | Build 3x scaffolds to access actutator valve on Train 1 Level 3 | 4194 | Trevor Pike | 2016-05-07 | Chevron | Med Duty | ERECT | Complete | 2016-05-07 | 2016-05-08
7761 | TRAIN 1 | TRAIN 1 TACA Level 3 | Build 3x scaffolds to access actutator valve on Train 1 Level 3 | 4194 | Trevor Pike | 2016-05-07 | Chevron | Med Duty | ERECT | Complete | 2016-05-07 | 2016-05-17
7761 | TACA | TRAIN 1 TACA Level 3 | Dismantle 7761 | 4372 | Trevor Pike | 2016-05-17 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-17 | 2016-05-16
7762 | TRAIN 1 | TRAIN 1 TACA Level 3 | Build 3x scaffolds to access actutator valve on Train 1 Level 3 | 4195 | Trevor Pike | 2016-05-07 | Chevron | Med Duty | ERECT | Complete | 2016-05-07 | 2016-05-08
7762 | TRAIN 1 | TRAIN 1 TACA Level 3 | Build 3x scaffolds to access actutator valve on Train 1 Level 3 | 4195 | Trevor Pike | 2016-05-07 | Chevron | Med Duty | ERECT | Complete | 2016-05-07 | 2016-05-17
7762 | TACA | TRAIN 1 TACA Level 3 | Dismantle 7762 | 4373 | Trevor Pike | 2016-05-17 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-17 | 2016-05-16
7763 | LPW | LPW | Erect scaffold to allow Hertel access to lifting lugs for Chartek works. (Add onto scaffold 6525) | 4196 | Alistair Nicholas | 2016-05-07 | Scaffolding | Med Duty | ERECT | Complete | 2016-05-07 | 2016-05-25
7764 | LPW | LPW | Erect scaffold to allow Hertel access to lifting lugs for Chartek works. (Add onto scaffold 6526) | 4197 | Alistair Nicholas | 2016-05-07 | Scaffolding | Med Duty | ERECT | Complete | 2016-05-07 | 2016-05-25
7765 | DOMGAS | DOMGAS North End | Please setup scaffold tubing for encapsulation x 2 locations | 4198 | Mark Farley | 2016-05-07 | Mechanical | Med Duty | ERECT | Complete | 2016-05-14 | 2016-05-09
7766 | DOMGAS | DOMGAS North End | Modification works to scaffold to enable the removal of 2 blinds and rotation. Installation of Tee Piece spool. | 4199 | Mark Farley | 2016-05-07 | Mechanical | Med Duty | MODIFY | Complete | 2016-05-14 | 2016-05-14
7767 | Jetty | JH23 | Re-erect stair access to toilet block on jetty. | 4200 | Alistair Nicholas | 2016-05-07 | Scaffolding | Med Duty | ERECT | Complete | 2016-05-09 | 2016-05-09
7768 | TBJF | TRAIN 2 TBJF | 1. Ladder bars and tubes to support the spools dropping from pipe rack. 2. Hope over at temp bund. 3. Access and deck to frak tank and ISO container. All in same area. | 4201 | Todd Lyons | 2016-05-07 | Mechanical | Med Duty | ERECT | Not Started | 2016-05-10
7769 | TRAIN 1 | TAJA | Erect mobile scaffold on the west side/top level of the Fin Fans | 4202 | Steven Linton | 2016-05-09 | KJV | Med Duty | ERECT | Complete | 2016-05-09 | 2016-05-09
7770 | TRAIN 1 | TAJA | Erect mobile scaffold on the east side/top level of the Fin Fans | 4203 | Steven Linton | 2016-05-09 | KJV | Med Duty | ERECT | Complete | 2016-05-09 | 2016-05-09
7771 | TRAIN 2 | TBJA South Train 2 | Need to remove drop zone for gen wheel for chem clean set up.Scaff Tag No: GW725 | 4209 | Todd Lyons | 2016-05-09 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-09 | 2016-05-13
7772 | TRAIN 2 | TBJA South Train 2 | Need to remove drop zone for gen wheel for chem clean set up. Scaff Tag No: GW761 | 4210 | Todd Lyons | 2016-05-09 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-09 | 2016-05-13
7773 | TBAA | TBAA | TBAA HM-2088 Erect scaffold deck to access pipe work for insulation. Note: 225mm clearance required for insulation off all pipe work. | 4213 | Felise Emelio | 2016-05-11 | Hertel | Med Duty | ERECT | Cancelled | 2016-05-07
7774 | TBG1 | TBG1 Module (A) | Require a scaffold built to access a hathc on the fin fans to complete works inside the confined space. Scaffold boards also need to be installed as a work platform. | 4214 | Jason Princen | 2016-05-11 | Mechanical | Med Duty | ERECT | Not Started | 2016-04-10
7775 | INLET | Crib rooms | Modify TAKEOVER TAGS H231 | 4227 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-19
7775 | INLET | Crib rooms | TAKEOVER TAGS H231 | 4227 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-05-11 | 2016-05-19
7776 | INLET | Crib rooms | Modify TAKEOVER TAGS H230 | 4228 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-19
7776 | INLET | Crib rooms | TAKEOVER TAGS H230 | 4228 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-05-11 | 2016-05-19
7777 | INLET | Crib rooms | Modify TAKEOVER TAGS H1632 | 4229 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-19
7777 | INLET | Crib rooms | TAKEOVER TAGS H1632 | 4229 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-05-11 | 2016-05-19
7778 | INLET | Crib rooms | Modify TAKEOVER TAGS H1604 | 4230 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-19
7778 | INLET | Crib rooms | TAKEOVER TAGS | 4230 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-05-11 | 2016-05-19
7779 | INLET | Crib rooms | Modify TAKEOVER TAGS H1575 | 4231 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-19
7779 | INLET | Crib rooms | TAKEOVER TAGS H1575 | 4231 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-19
7780 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4232 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-11
7781 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4233 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-11
7782 | INLET | Crib rooms | TAKEOVER TAGS H733 | 4234 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-21
7782 | INLET | Crib rooms | TAKEOVER TAGS H733 | 4234 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-05-11 | 2016-05-21
7783 | Inlet | Crib rooms | oodify TAKEOVER TAGS H732 | 4235 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-21
7783 | Inlet | Crib rooms | TAKEOVER TAGS H732 | 4235 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-05-11 | 2016-05-21
7784 | Inlet | Stores | Modify TAKEOVER TAGS H716 | 4236 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-19
7784 | Inlet | Stores | TAKEOVER TAGS H716 | 4236 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-05-11 | 2016-05-19
7785 | Abutment Office Area | Abutment Office Area | Dismantle tube and clip stairs to old QA office #6732 | 4186 | Martin Riegert | 2016-05-06 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-06 | 2016-05-24
7785 | Inlet | Bus stop | Modify TAKEOVER TAGS H1974 | 4237 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-19
7785 | Inlet | Bus stop | TAKEOVER TAGS H1974 | 4237 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-05-11 | 2016-05-19
7786 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4238 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-11
7787 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4239 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-11
7788 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4240 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-11
7789 | INLET | Inlet | Modify TAKEOVER TAGS H1552 | 4241 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-21
7789 | INLET | Inlet | TAKEOVER TAGS H1552 | 4241 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-05-11 | 2016-05-21
7790 | INLET | inlet | Modify TAKEOVER TAGS H483 - H1723 | 4242 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-21
7790 | INLET | inlet | TAKEOVER TAGS H483 - H1723 | 4242 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-05-11 | 2016-05-21
7791 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4243 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-11
7792 | GAA1 | GAA1 | Modify TAKEOVER TAGS no tag no. | 4244 | Jamie Macmimi | 2016-05-22 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-22
7792 | GAA1 | GAA1 | TAKEOVER TAGS no tag no. | 4244 | Jamie Macmimi | 2016-05-22 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-05-11 | 2016-05-22
7793 | RBCA | RBCA | TAKEOVER TAGS no tag no. | 4245 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-22
7793 | RBCA | RBCA | TAKEOVER TAGS no tag no. | 4245 | Jamie Macmimi | 2016-05-22 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-05-11 | 2016-05-22
7794 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4246 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-11
7795 | RBCA | Inlet | TAKEOVER TAGS no tag | 4247 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-20
7795 | RBCA | Inlet | TAKEOVER TAGS no tag | 4247 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-05-11 | 2016-05-20
7796 | RBCA | Inlet | TAKEOVER TAGS C 1962 | 4248 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-20
7796 | RBCA | Inlet | TAKEOVER TAGS C 1962 | 4248 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-05-11 | 2016-05-20
7797 | INLET | Pig reciever | Modify TAKEOVER TAGS H1739 | 4249 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-18
7797 | INLET | Pig reciever | TAKEOVER TAGS H1739 | 4249 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-18
7798 | RBCA | Inlet RBCA / RBCN | Modify TAGS G 598 & C 1619 | 4250 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-20
7798 | RBCA | Inlet RBCA / RBCN | TAKEOVER TAGS G 598 & C 1619 | 4250 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-20
7798 | RBCA | Inlet RBCA / RBCN | Modify TAKEOVER TAGS G 598 & C 1619 | 4250 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-22
7799 | RBAG | Inlet | TAKEOVER TAGS H887 | 4251 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-18
7799 | RBAG | Inlet | TAKEOVER TAGS H887 | 4251 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-18
7800 | RBAG | Inlet | ModifyTAKEOVER TAGS H846 | 4252 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-18
7800 | RBAG | Inlet | TAKEOVER TAGS H846 | 4252 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-18
7801 | CAAA | Agru 1 - level | TAKEOVER TAGS Mas D864 | 4253 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-20
7801 | CAAA | Agru 1 - level | TAKEOVER TAGS Mas D864 | 4253 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-20
7802 | CAAA | Agru 1 | Modify TAKEOVER TAGS Mas 523 | 4254 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-20
7802 | CAAA | Agru 1 | TAKEOVER TAGS 523 | 4254 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-20
7803 | CAAA | Agru 1 | Modfy TAKEOVER TAGS D170 | 4255 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-20
7803 | CAAA | Agru 1 | TAKEOVER TAGS D170 | 4255 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-20
7804 | CAAA | Agru 1 | Modfy TAKEOVER TAGS | 4256 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-20
7804 | CAAA | Agru 1 | TAKEOVER TAGS | 4256 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-20
7805 | CAAA | Agru 1 | Modofy TAKEOVER TAGS | 4257 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-20
7805 | CAAA | Agru 1 | TAKEOVER TAGS | 4257 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-20
7806 | CAAA | Agru 1 | TAKEOVER TAGS D947 | 4258 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-20
7807 | CAAA | Agru 1 | TAKEOVER TAGS 7807 | 4259 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-20
7807 | CAAA | Agru 1 | TAKEOVER TAGS 7807 | 4259 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-20
7808 | CAAA | Agru 1 - Level 1 | Modify TAKEOVER TAGS D 265 | 4260 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-21
7808 | CAAA | Agru 1 - Level 1 | TAKEOVER TAGS D 265 | 4260 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-21
7809 | CAAA | Agru 1 - Level 1 | Modify TAKEOVER TAGS D 949 | 4261 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-21
7809 | CAAA | Agru 1 - Level 1 | TAKEOVER TAGS D949 | 4261 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-21
7810 | CAAA | Agru 1 - Level 1 | Modify TAKEOVER TAGS D 726 | 4262 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-21
7810 | CAAA | Agru 1 - Level 1 | TAKEOVER TAGS D 726 | 4262 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-21
7811 | CAAA | Agru 1 - Level 1 | Modify TAKEOVER TAGS 167 | 4263 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-21
7811 | CAAA | Agru 1 - Level 1 | TAKEOVER TAGS 167 | 4263 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-21
7812 | CAAA | Agru 1 - Level 1 | Modify TAKEOVER TAGS D203 | 4264 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-21
7812 | CAAA | Agru 1 - Level 1 | TAKEOVER TAGS D203 | 4264 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-21
7813 | CAAA | Agru 1 - Level 1 | Modify TAKEOVER TAGS D181 | 4265 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-21
7813 | CAAA | Agru 1 - Level 1 | TAKEOVER TAGS D181 | 4265 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-21
7814 | CAAA | Agru 1 - Level 1 | Modify TAKEOVER TAGS D 204 | 4266 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-21
7814 | CAAA | Agru 1 - Level 1 | TAKEOVER TAGS D 204 | 4266 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-21
7815 | CAAA | Agru 1 - Level 1 | Modify TAKEOVER TAGS Mas 710 | 4267 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-21
7815 | CAAA | Agru 1 - Level 1 | TAKEOVER TAGS Mas 710 | 4267 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-21
7816 | CAAA | Agru 1 - Level 1 | Modify TAKEOVER | 4268 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-21
7816 | CAAA | Agru 1 - Level 1 | TAKEOVER TAGS | 4268 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-21
7817 | CAAA | Agru 1 - Level 1 | Modify TAKEOVER TAGS D 942 | 4269 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-21
7817 | CAAA | Agru 1 - Level 1 | TAKEOVER Tag D 942 | 4269 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-05-11 | 2016-05-21
7818 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4270 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | Takeover | Not Started | 2016-05-11
7819 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4271 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | Takeover | Not Started | 2016-05-11
7820 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4272 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | Takeover | Not Started | 2016-05-11
7821 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4273 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | Takeover | Not Started | 2016-05-11
7822 | CAAA | Agru 1 - Level 1 | Modify TAKEOVER TAGS Mas nth / east crn | 4274 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-21
7822 | CAAA | Agru 1 - Level 1 | TAKEOVER TAGS Mas nth / east crn | 4274 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-21
7823 | JACA | Inlet | Modify TAKEOVER TAGS G972 | 4275 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-24
7823 | JACA | Inlet | TAKEOVER TAGS G972 | 4275 | Jamie Macmimi | 2016-05-11 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-24
7824 | Jetty | Jetty | TAKEOVER TAGS No tag - LPW Layher reinstate and extension.xlsx | 4276 | Martin Riegert | 2016-05-11 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-18
7824 | Jetty | Jetty | ModifyTAKEOVER TAGS No tag - LPW Layher reinstate and extension.xlsx | 4276 | Martin Riegert | 2016-05-11 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-19
7825 | GAA1 | Injection Pumps - GAA1 | Erect Scaffold to access butt welds on riser at A outlet | 4283 | Shane Shillabeer | 2016-05-13 | Mechanical | Med Duty | ERECT | complete | 2016-05-16 | 2016-05-23
7826 | L13 | L13-14 jetty Area 1 | Modify Scaffold around L13-14 to allow bolier maker to access guide flanges | 4284 | Adam Keown | 2016-05-13 | Mechanical | Med Duty | MODIFY | Complete | 2016-05-20 | 2016-05-21
7827 | SAH1 | SAH1 Condensate Tanks | Erect scaffold Access to weld in brackets | 4288 | Gavin Hughes | 2016-05-13 | Mechanical | Med Duty | ERECT | Not Started | 2016-05-20
7828 | SAH1 | SAH, outside northern wall | Set up scaffold tube framing for encapsulation for pipe welding on theeastern 2 pipe going throught the wal into condensate tanks 3 & 4. | 4289 | Mark Farley | 2016-05-13 | Mechanical | Med Duty | ERECT | Not Started | 2016-05-20
7829 | SAH1 | SAH1 Condensate Tanks | Erect scaffold Access under stair case to weld in brackets | 4290 | Gavin Hughes | 2016-05-13 | Mechanical | Med Duty | ERECT | Complete | 2016-05-20 | 2016-05-16
7830 | SAH1 | SAH1 Condensate Tanks - DNC near by 6828 | Require a scaffold built on West Wall, dimentions as 4000mm long x 2000mm Wide with a working deck @ 1800mm from grade. If possible, tie into existing scaffold. Take into consideration, the route of cable ladders (x2) that are required to be installed at a later date. This scaffold is for welding activities & Electrical scope. Refer to below model shot. Please make contact with Gavin to walk the job to ensure scaffold is fit for both SMP & I&E, prior to build. DNC near by 6828 | 4291 | Gavin Hughes | 2016-05-13 | Mechanical | Med Duty | ERECT | Complete | 2016-05-20 | 2016-05-18
7831 | SAH1 | SAH1 Condensate Tanks | Erect scaffold to get to all welding parts in attached picture | 4292 | Gavin Hughes | 2016-05-13 | Mechanical | Med Duty | ERECT | Complete | 2016-05-20 | 2016-05-16
7832 | TBJF | TBJF Train 2 | 1. Ladder bars and tubes to support the spools dropping from pipe rack | 4293 | Todd Lyons | 2016-05-13 | Mechanical | Med Duty | ERECT | Complete | 2016-05-20 | 2016-05-16
7833 | TBJF | TBJF Train 2 | 2.Hope over at temp bund | 4294 | Todd Lyons | 2016-05-13 | Mechanical | Med Duty | ERECT | Not Started | 2016-05-20
7834 | TBJF | TBJF Train 2 | 3.Access and deck to frak tank and ISO container | 4295 | Todd Lyons | 2016-05-13 | Mechanical | Med Duty | ERECT | Complete | 2016-05-20 | 2016-05-18
7835 | TBAB | TBAB Train 2 | Build one scaffold access and platforms to access tanks for temp | 4296 | Todd Lyons | 2016-05-13 | Mechanical | Med Duty | ERECT | Not Started | 2016-05-20
7836 | TBAB | TBAB Train 2 | Build one scaffold access and platforms to access tanks for temp | 4297 | Todd Lyons | 2016-05-13 | Mechanical | Mechanical | ERECT | Complete | 2016-05-20 | 2016-05-13
7837 | GAC1 | Inlet GAC1 | please build scaffold around south east corner of the GAC1 module this is a welding job and will require encaptulation there is an existing scaffold in the immediate area that may require modification please contact Jono or myself to be walked through the job. | 4298 | Paul Cummins | 2016-05-13 | Mechanical | Med Duty | ERECT | Complete | 2016-05-20 | 2016-05-18
7838 | DAAA | Domgas | ModifyCHEVRON TAKEOVER TAGS A-1504 | 4318 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-16
7838 | DAAA | Domgas | CHEVRON TAKEOVER TAGS A-1504 | 4318 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-16
7839 | DAAA | Domgas | ModifyCHEVRON TAKEOVER TAGS A-2502 | 4319 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-16
7839 | DAAA | Domgas | CHEVRON TAKEOVER TAGS A-2502 | 4319 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-16
7840 | DAAA | Domgas | ModifyCHEVRON TAKEOVER TAGS A-2299 | 4320 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-16
7840 | DAAA | Domgas | CHEVRON TAKEOVER TAGS A-2299 | 4320 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-16
7840 | DAAA | Domgas | Dismantle as per request by Trevor Pike | 4499 | Trevor Pike | 2016-05-22 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-28 | 2016-05-23
7841 | DAAA | Domgas | ModifyCHEVRON TAKEOVER TAGS A-2298 | 4321 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-16
7841 | DAAA | Domgas | CHEVRON TAKEOVER TAGS A-2298 | 4321 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-16
7842 | DAAA | Domgas | ModifyCHEVRON TAKEOVER TAGS A1334 | 4322 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-16
7842 | DAAA | Domgas | CHEVRON TAKEOVER TAGS A1334 | 4322 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-16
7843 | DAAA | Domgas | Modify CHEVRON TAKEOVER TAGS A1335 | 4323 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-16
7843 | DAAA | Domgas | CHEVRON TAKEOVER TAGS A1335 | 4323 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-16
7844 | DAAA | Domgas | modify CHEVRON TAKEOVER TAGS MAS A2455 | 4324 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-16
7844 | DAAA | Domgas | CHEVRON TAKEOVER TAGS MAS A2455 | 4324 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-16
7845 | DAAA | Domgas | CHEVRON TAKEOVER TAGS A 1337 | 4325 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-16
7845 | DAAA | Domgas | CHEVRON TAKEOVER TAGS A 1337 | 4325 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-16
7845 | DAAA | Domgas | Dismantle as per request by Trevor Pike (maybe 1125??) | 4500 | Trevor Pike | 2016-05-22 | Chevron | Med Duty | Dismantle | Complete | 2016-05-28 | 2016-05-27
7846 | DAAA | Domgas | Modify CHEVRON TAKEOVER TAGS A 2064 | 4326 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-15
7846 | DAAA | Domgas | CHEVRON TAKEOVER TAGS A 2064 | 4326 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-15
7846 | DAAA | Domgas | Dismantle | 4382 | Trevor Pike | 2016-05-16 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-16 | 2016-05-17
7847 | DAAA | DAAA | Modify CHEVRON TAKEOVER TAGS A1934 | 4327 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-16
7847 | DAAA | DAAA | CHEVRON TAKEOVER TAGS A1934 | 4327 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-16
7848 | DAAA | Domgas | Takeover A2496 | 4387 | Trevor Pike | 2016-05-16 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-16 | 2016-05-16
7848 | DAAA | Domgas | Dismantle | 4387 | Trevor Pike | 2016-05-16 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-16 | 2016-05-17
7849 | DAAA | Domgas | CHEVRON TAKEOVER TAGS | 4329 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-16
7849 | DAAA | Domgas | Dismantle | 4388 | Trevor Pike | 2016-05-16 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-16 | 2016-05-17
7850 | DAAA | Domgas | Modify CHEVRON TAKEOVER TAGS A2310 | 4330 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-16
7850 | DAAA | Domgas | CHEVRON TAKEOVER TAGS A2310 | 4330 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-16
7850 | DAAA | Domgas | Dismantle | 4386 | Trevor Pike | 2016-05-16 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-16 | 2016-05-17
7851 | DAAA | Domgas | CHEVRON TAKEOVER TAGS A2310 | 4331 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-11 | 2016-05-16
7851 | DAAA | Domgas | CHEVRON TAKEOVER TAGS A2310 | 4331 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-16
7851 | DAAA | Domgas | CHEVRON TAKEOVER TAGS A2310 | 4331 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-16
7851 | DAAA | Domgas | Dismantle A2475 | 4385 | Trevor Pike | 2016-05-16 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-16 | 2016-05-24
7852 | DAAA | Domgas | Modify CHEVRON TAKEOVER TAGS MAS A-2449 | 4332 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-16
7852 | DAAA | Domgas | CHEVRON TAKEOVER TAGS MAS A-2449 | 4332 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-16
7852 | DAAA | Domgas | Dismantle | 4389 | Trevor Pike | 2016-05-16 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-16 | 2016-05-24
7853 | DAAA | Domgas | Modify CHEVRON TAKEOVER TAGS MAS A2450 | 4333 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-16
7853 | DAAA | Domgas | CHEVRON TAKEOVER TAGS MAS A2450 | 4333 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-16
7853 | DAAA | Domgas | Dismantle | 4390 | Trevor Pike | 2016-05-16 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-16 | 2016-05-22
7854 | DAAA | DAAA Level 1 s/e crn lagging access | modify CHEVRON TAKEOVER TAGS A-2493 | 4334 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-15
7854 | DAAA | DAAA Level 1 s/e crn lagging access | CHEVRON TAKEOVER TAGS A-2493 | 4334 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-15
7855 | DAAA | DAAA | modify CHEVRON TAKEOVER TAGS A2491 | 4335 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-16
7855 | DAAA | DAAA | CHEVRON TAKEOVER TAGS A2491 | 4335 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-16
7855 | DAAA | Domgas level 1 s/w | Dismantle 7855 DAAA | 4481 | Trevor Pike | 2016-05-21 | Chevron | Med Duty | MODIFY | Complete | 2016-05-28 | 2016-05-23
7856 | DAAA | Domgas ground level n/e crn | Modify CHEVRON TAKEOVER TAGS A 1672 | 4336 | Trevor Pike | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-15
7856 | DAAA | Domgas ground level n/e crn | CHEVRON TAKEOVER TAGS A 1672 | 4336 | Trevor Pike | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-15
7856 | DAAA | Domgas | Dismantle | 4381 | Trevor Pike | 2016-05-16 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-16 | 2016-05-16
7857 | SITEWIDE - TBA | Sitewide | CHEVRON TAKEOVER TAGS A 2471 | 4337 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-15
7857 | DAAA | Domgas | Dismantle | 4383 | Trevor Pike | 2016-05-16 | Chevron | Med Duty | DISMANTLE | Complete | 2016-05-16 | 2016-05-16
7859 | DAAA | DAAA | modify CHEVRON TAKEOVER TAGS A-1613 | 4339 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-16
7859 | DAAA | DAAA | CHEVRON TAKEOVER TAGS A-1613 | 4339 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-16
7860 | DAAA | DAAA | modify CHEVRON TAKEOVER TAGS A-2176 | 4340 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-16
7860 | DAAA | DAAA | CHEVRON TAKEOVER TAGS A-2176 | 4340 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-16
7861 | DAAA | DAAA | modify CHEVRON TAKEOVER TAGS A-1594 | 4341 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-16
7861 | DAAA | DAAA | CHEVRON TAKEOVER TAGS A-1594 | 4341 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-16
7862 | SITEWIDE - TBA | Sitewide | Modify CHEVRON TAKEOVER TAGS | 4342 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-18
7862 | SITEWIDE - TBA | Sitewide | CHEVRON TAKEOVER TAGS | 4342 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-18
7863 | GAEA | GAEA Level 1 hydro carbon line 2R10159 | Modify to access takeover - TAGS MAS 2509 | 4343 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-17
7863 | GAEA | GAEA Level 1 hydro carbon line 2R10159 | CHEVRON TAKEOVER TAGS MAS 2509 | 4343 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-17
7864 | GAEA | GAEA Level 1 center | Modify to access takeover - TAGS MAS A-2511 | 4344 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-17
7864 | GAEA | GAEA Level 1 center | CHEVRON TAKEOVER TAGS MAS A-2511 | 4344 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-17
7865 | GAEA | GAEA Level 1 center | Modify to access takeover - TAGS MAS A-2511 | 4345 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-17
7865 | GAEA | GAEA Level 1 center | CHEVRON TAKEOVER TAGS MAS A-2511 | 4345 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-17
7866 | GAEA | GAEA Level 2 S/E corner humpy center | Modify to access takeover - TAGS MAS A-1871 | 4346 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-17
7866 | GAEA | GAEA Level 2 S/E corner humpy center | CHEVRON TAKEOVER TAGS A-1871 | 4346 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-17
7867 | GAEA | GAEA Level 2 S/E corner arge humpy landing | Modify to access takeover - TAGS MAS A-2481 | 4347 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-17
7867 | GAEA | GAEA Level 2 S/E corner arge humpy landing | CHEVRON TAKEOVER TAGS MAS A-2481 | 4347 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-17
7868 | GAEA | GAEA Level 2 S/E corner Staires | Modify to access takeover - TAGS MAS A-2023 | 4348 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-17
7868 | GAEA | GAEA Level 2 S/E corner Staires | CHEVRON TAKEOVER TAGS MAS A-2023 | 4348 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-17
7869 | GAEA | GAEA Level 2 S/E corner Staires | Modify to access takeover - TAGS MAS A-1532 | 4349 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-17
7869 | GAEA | GAEA Level 2 S/E corner Staires | CHEVRON TAKEOVER TAGS MAS A-1532 | 4349 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-17
7869 | GAEA | GAEA | Please modify the scaffold platform as per photographs to enable access to install temp.pipe spooling I had a walk down with Jarrod concerning this scope however I have missed submitting | 4667 | Lennie Haira | 2016-05-26 | CSU | Med Duty | DISMANTLE | Complete | 2016-05-26 | 2016-05-26
7870 | GAEA | GAEA Level 2 S/E corner Staires | Modify to access takeover - TAGS MAS A-1405 | 4350 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-17
7870 | GAEA | GAEA Level 2 S/E corner Staires | CHEVRON TAKEOVER TAGS MAS A-1405 | 4350 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-17
7871 | GAEA | GAEA Level 2 N/E corner Stairs | Modify to access takeover - TAGS MAS A-2397 | 4351 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-17
7871 | GAEA | GAEA Level 2 N/E corner Stairs | CHEVRON TAKEOVER TAGS MAS A-2397 | 4351 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-17
7872 | GAEA | Level 1 far north handrail | Modify TAKEOVER TAGS MAS A-1540 | 4352 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-17
7872 | GAEA | Level 1 far north handrail | CHEVRON TAKEOVER TAGS MAS A-1540 | 4352 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-17
7873 | GAEA | off A 281 | ModifyTAKEOVER TAGS MAS A-A1903 | 4353 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-17
7873 | GAEA | off A 281 | CHEVRON TAKEOVER TAGS MAS A-A1903 | 4353 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-17
7874 | GAEA | Level 1 far north handrail | Modify TAKEOVER TAGS MAS A281 | 4354 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-17
7874 | GAEA | Level 1 far north handrail | CHEVRON TAKEOVER TAGS MAS A281 | 4354 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-17
7875 | GAEA | LEVEL 1 N/W | Modify TAKEOVER TAGS MAS A-2398 | 4355 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-17
7875 | GAEA | LEVEL 1 N/W | CHEVRON TAKEOVER TAGS MAS A-2398 | 4355 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-17
7876 | Gaea | Level 2 | Modify TAKEOVER TAGS A-2327 | 4356 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-18
7876 | Gaea | Level 2 | CHEVRON TAKEOVER TAGS A-2327 | 4356 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-18
7877 | GADA | level 2 N/E | Modify TAKEOVER TAGS 2504 | 4357 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-18
7877 | GADA | level 2 N/E | CHEVRON TAKEOVER TAGS 2504 | 4357 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-18
7878 | GADA | Level 1 S/E up laadder minor land | Modify TAKEOVER TAGS MAS A-2503 | 4358 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-18
7878 | GADA | Level 1 S/E up laadder minor land | CHEVRON TAKEOVER TAGS MAS A-2503 | 4358 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-18
7879 | GADA | Level 2 South end | Modify TAKEOVER TAGS MAS 1522 | 4359 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-18
7879 | GADA | Level 2 South end | CHEVRON TAKEOVER TAGS MAS 1522 | 4359 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-18
7880 | GADA | Level 2 North | Modify TAKEOVER TAGS 802 | 4360 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-18
7880 | GADA | Level 2 North | CHEVRON TAKEOVER TAGS 802 | 4360 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-18
7881 | GADA | S/E level 2 messanie | Modify takeover access TAGS 739 | 4361 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-18
7881 | GADA | S/E level 2 messanie | CHEVRON TAKEOVER TAGS 739 | 4361 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-18
7882 | GADA | S/E level 2 messanie | Modify Takeover access TAGS 872 A2472 | 4362 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-11 | 2016-05-18
7882 | GADA | S/E level 2 messanie | CHEVRON TAKEOVER TAGS 872 / A2472 | 4362 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Complete | 2016-05-11 | 2016-05-18
7882 | GADA | Gada - Inlet | Dismantle 7882 / A2472 | 4409 | Mark orr | 2016-05-19 | Scaffolding | Med Duty | ERECT | Complete | 2016-05-19
7883 | TBBA | TBBA | Scaffold access to high point Vents, Potentially 5 builds maybe less with a Mobile. Needed for temp flush set up to drain points. | 4369 | Todd Lyons | 2016-05-15 | CSU | Med Duty | ERECT | Not Started | 2016-05-17
7884 | TBBA | TBBA | Scaffold access to high point Vents, Potentially 5 builds maybe less with a Mobile. Needed for temp flush set up to drain points. | 4368 | Todd Lyons | 2016-05-15 | CSU | Med Duty | ERECT | Not Started | 2016-05-17
7885 | TBBA | TBBA | Scaffold access to high point Vents, Potentially 5 builds maybe less with a Mobile. Needed for temp flush set up to drain points. | 4367 | Todd Lyons | 2016-05-15 | CSU | Med Duty | ERECT | Not Started | 2016-05-17
7886 | TBBA | TBBA | Scaffold access to high point Vents, Potentially 5 builds maybe less with a Mobile. Needed for temp flush set up to drain points. | 4366 | Todd Lyons | 2016-05-15 | CSU | Med Duty | ERECT | Not Started | 2016-05-17
7887 | TBBA | TBBA | Scaffold access to high point Vents, Potentially 5 builds maybe less with a Mobile. Needed for temp flush set up to drain points. | 4365 | Todd Lyons | 2016-05-15 | CSU | Med Duty | ERECT | Not Started | 2016-05-17
7888 | SAH1 | SAH1 North west corner Condensate tank 3 | Dismantel Scaffold in north west corner condensate Tank 3 | 4410 | Glenn Beckett | 2016-05-19 | Mechanical | Med Duty | Dismantle | Not Started | 2016-05-19
7889 | Area 4 | Stores at area 4 | Scaffold require for shelf inside CSU punchlist container(SBIU 200158 4 22G1)for storage , ( A request has already been put in when it was in the Inlet yard) .A Scaffold is required for shelter and a bench at the front and side of the area 4 CSU punchlist store containers . See attached location and photos. | 4394 | Mattew Pollard | 2016-05-18 | Mechanical | Med Duty | ERECT | Not Started | 2016-05-20
7889 | SAH1 | SAH1 North west corner Condensate tank 3 | Dismantel Scaffold in north west corner condensate Tank 3 | 4411 | Glenn Beckett | 2016-05-19 | Mechanical | Med Duty | Dismantle | Not Started | 2016-05-19
7890 | Area 4 | Stores at area 4 | Scaffold require for shelf inside CSU punchlist container(SBIU 200158 4 22G1)for storage , ( A request has already been put in when it was in the Inlet yard) .A Scaffold is required for shelter and a bench at the front and side of the area 4 CSU punchlist store containers . See attached location and photos. | 4395 | Mattew Pollard | 2016-05-18 | Mechanical | Med Duty | ERECT | Not Started | 2016-05-20
7891 | Area 4 | Stores at area 4 | Scaffold require for shelf inside CSU punchlist container(SBIU 200158 4 22G1)for storage , ( A request has already been put in when it was in the Inlet yard) .A Scaffold is required for shelter and a bench at the front and side of the area 4 CSU punchlist store containers . See attached location and photos. | 4396 | Mattew Pollard | 2016-05-18 | Mechanical | Med Duty | ERECT | Not Started | 2016-05-20
7892 | Area 4 | Stores at area 4 | Scaffold require for shelf inside CSU punchlist container(SBIU 200158 4 22G1)for storage , ( A request has already been put in when it was in the Inlet yard) .A Scaffold is required for shelter and a bench at the front and side of the area 4 CSU punchlist store containers . See attached location and photos. | 4397 | Mattew Pollard | 2016-05-18 | Mechanical | Med Duty | ERECT | Not Started | 2016-05-20
7893 | GACA | GACA, Elevation 31 (5 platforms | Require scaffolds to access light fittings LF-DB8382-E01-05W-03 (See attached drawing G1-TD-E-0901-LED0116) | 4398 | Bruce Stephenson | 2016-05-18 | Electrical | Med Duty | ERECT | Complete | 2016-05-20 | 2016-05-21
7894 | GACA | GACA, Elevation 31 (5 platforms | Require scaffolds to access light fittings LF-DB8382-E01-05W-01 (See attached drawing G1-TD-E-0901-LED0116) | 4399 | Bruce Stephenson | 2016-05-18 | Electrical | Med Duty | ERECT | Complete | 2016-05-20 | 2016-05-21
7895 | GACA | GACA, Elevation 31 (5 platforms | Require scaffolds to access light fittings LF-DB8382-E01-05B-03 (See attached drawing G1-TD-E-0901-LED0124) | 4400 | Bruce Stephenson | 2016-05-18 | Electrical | Med Duty | ERECT | Complete | 2016-05-20 | 2016-05-21
7896 | GACA | GACA, Elevation 31 (5 platforms | Require scaffolds to access light fittings LF-DB8382-E01-05B-04 (See attached drawing G1-TD-E-0901-LED0123) | 4401 | Bruce Stephenson | 2016-05-18 | Electrical | Med Duty | ERECT | Complete | 2016-05-20 | 2016-05-21
7897 | GACA | GACA, Elevation 31 (5 platforms | Require scaffolds to access light fittings LF-DB8382-E01-05B-06 (See attached drawing G1-TD-E-0901-LED0124) | 4402 | Bruce Stephenson | 2016-05-18 | Electrical | Med Duty | ERECT | Complete | 2016-05-20 | 2016-05-20
7898 | GAC1 | GAC1 | Modify scaffold NW side of GAC1 Tank to access field weld on ground level | 4403 | Mark Orr | 2016-05-18 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-20 | 2016-05-18
7898 | GAC1 | GAC1 | Erect scaffold NW side of GAC1 Tank to access field weld on ground level | 4403 | Mark Orr | 2016-05-18 | Scaffolding | Med Duty | ERECT | Complete | 2016-05-20 | 2016-05-18
7898 | GAC1 | GAC1 | Dismantle scaffold NW side of GAC1 Tank to access field weld on ground level | 4403 | Mark Orr | 2016-05-21 | Scaffolding | Med Duty | DISMANTLE | Complete | 2016-05-20 | 2016-05-21
7899 | RBDE | RBDE | RBDE-RBDQ HM-2129 need to access line PRBDE00-0P-10178.70/B1 for insulation/cladding scopes will need SCAFFOLD TAKE OVER Tag A33. | 4412 | Felise Emelio | 2016-05-19 | Hertel | Med Duty | MODIFY | Not Started | 2016-05-24
7899 | RBDE | RBDE | RBDE-RBDQ HM-2129 need to access line PRBDE00-0P-10178.70/B1 for insulation/cladding scopes will need SCAFFOLD TAKE OVER Tag A33. | 4412 | Felise Emelio | 2016-05-19 | Hertel | Med Duty | Takeover | Not Started | 2016-05-24
7900 | GAHk | GAHk / RBAN | Need scaffold built at the south east corner of GAHK & RBAN inlet area. This is the one that CKJV had built & needed Gate & tag done. | 4416 | Rick Muston | 2016-05-20 | Mechanical | Med Duty | ERECT | Complete | 2016-05-25 | 2016-05-19
7901 | GAGA | GAGA | New scaffold build to access for installation of Studs & tensioning of Nuts. This will need to be done after the elbows have been lifted into position by riggers | 4417 | Rick Muston | 2016-05-20 | Mechanical | Med Duty | ERECT | Complete | 2016-05-25 | 2016-05-21
7902 | RBAN | RBAN | New scaffold build at the south east corner of RBAN pipe rack inlet area. This is to do closure welding on 6" pipe see attached picture. | 4418 | Rick Muston | 2016-05-20 | Mechanical | Med Duty | ERECT | Complete | 2016-05-25 | 2016-05-21
7903 | GAHK | GAHK | Need scaffold built at the south east corner of GAHK & RBAN inlet area. This is the one that CKJV had built & needed Gate & tag done. | 4419 | Rick Muston | 2016-05-20 | Mechanical | Med Duty | ERECT | complete | 2016-05-25 | 2016-05-24
7904 | GAGA | GAGA | Build new muilti deck and drop deck scaffold to allow welding of cable ladder bracket and installation of cable ladder and tubing refer to pic TON: 791.5 | 4421 | Andrew Ferres | 2016-05-19 | Scaffolding | Med Duty | ERECT | Complete | 2016-05-19 | 2016-05-22
7905 | DAAA | DAAA | Require a Scaffold to Access Flow Element 024FE006 for Possible removal of Element.This is for Chevron CSU TeamTank FRANK ARIAS CSU CONTACT- TETRA # 840522 Tel +61 8 9159 9772 | 4422 | Trevor Pike | 2016-05-19 | Chevron | Med Duty | ERECT | complete | 2016-05-19 | 2016-05-23
7906 | SAHA | SAHA | Need hard barricade to be erected on the northern end of condensate tank 1 to utilise as fall protection when removing grid mesh. The way that the hydro needs to be completed has changed therefore this was un expected. OPS AREA | 4429 | Daniel Edwards | 2016-05-20 | Mechanical | Med Duty | ERECT | Not started | 2016-05-25
7907 | SADA | SADA | Please see attached email to strip out scaffold fencing along rd at SADA module this has come as directive from client Can you ask your Downer scaffold contact to schedule the removal of this scaffold barricade… we need it removed by Monday-Tuesday next week. Paul BartlettCSU Commissioning Gorgon Project Kellogg Joint Venture Gorgon | 4432 | Todd Lyons | 2016-05-20 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-25 | 2016-05-24
7908 | UAGA | Northern end of module UAG | Need 3 scaffold humpies erected on the northern end of UAGA & an additional mobile humpy erected to allow for encapsulation of hot works that need to be carried out | 4463 | Daniel Edwards | 2016-05-21 | Mechanical | Med Duty | ERECT | Complete | 2016-05-22 | 2016-05-22
7909 | UAGA | Northern end of module UAG | Need 3 scaffold humpies erected on the northern end of UAGA & an additional mobile humpy erected to allow for encapsulation of hot works that need to be carried out | 4464 | Daniel Edwards | 2016-05-21 | Mechanical | Med Duty | ERECT | Complete | 2016-05-22 | 2016-05-22
7910 | UAGA | Northern end of module UAG | Need 3 scaffold humpies erected on the northern end of UAGA & an additional mobile humpy erected to allow for encapsulation of hot works that need to be carried out | 4465 | Daniel Edwards | 2016-05-21 | Mechanical | Med Duty | ERECT | Complete | 2016-05-22 | 2016-05-22
7911 | GAEA | GAEA | Build a rated lifting scaffold around valve number 210HV20778 in GAEA, this valve is damaged and need replacing. Could the scaffold be rated to at 300kgs NB Craig will bring down model shot | 4466 | Lennie Haira | 2016-05-21 | CSU | Med Duty | ERECT | Complete | 2016-05-22 | 2016-05-22
7911 | GAEA | GAEA | Dismantle a rated lifting scaffold around valve number 210HV20778 in GAEA, this valve is damaged and need replacing. Could the scaffold be rated to at 300kgs | 4467 | Lennie Haira | 2016-05-21 | CSU | Med Duty | DISMANTLE | Complete | 2016-05-22 | 2016-05-25
7912 | UAG1 | UAG1 | 1 OF 2. SCAFFOLD TO BE ERECTED TO SUPPORT PIPING FROM COMPRESSOR OUTLET TO EXISTING PIPING | 4469 | Daniel Edwards | 2016-05-21 | Mechanical | Med Duty | ERECT | Complete | 2016-05-28 | 2016-05-22
7913 | UAG1 | UAG1 | 2 OF 2. SCAFFOLD TO BE ERECTED TO SUPPORT PIPING FROM COMPRESSOR OUTLET TO EXISTING PIPING | 4470 | Daniel Edwards | 2016-05-21 | Mechanical | Med Duty | ERECT | Complete | 2016-05-28 | 2016-05-22
7914 | UAG1 | UAG1 | 1 OF 5. SCAFFOLD TO BE ERECTED TO SUPPORT PIPING FROM COMPRESSOR OUTLET TO EXISTING PIPING NORTH EAST END | 4471 | Daniel Edwards | 2016-05-21 | Mechanical | Med Duty | ERECT | Complete | 2016-05-28 | 2016-05-24
7915 | UAG1 | UAG1 | 2 OF 5. SCAFFOLD TO BE ERECTED TO SUPPORT PIPING FROM COMPRESSOR OUTLET TO EXISTING PIPING NORTH EAST END | 4472 | Daniel Edwards | 2016-05-21 | Mechanical | Med Duty | ERECT | Complete | 2016-05-28 | 2016-05-24
7916 | UAG1 | UAG1 | 3 OF 5. SCAFFOLD TO BE ERECTED TO SUPPORT PIPING FROM COMPRESSOR OUTLET TO EXISTING PIPING NORTH EAST END | 4473 | Daniel Edwards | 2016-05-21 | Mechanical | Med Duty | ERECT | Complete | 2016-05-28 | 2016-05-24
7917 | UAG1 | UAG1 | 4 OF 5. SCAFFOLD TO BE ERECTED TO SUPPORT PIPING FROM COMPRESSOR OUTLET TO EXISTING PIPING NORTH EAST END | 4474 | Daniel Edwards | 2016-05-21 | Mechanical | Med Duty | ERECT | Complete | 2016-05-28 | 2016-05-24
7918 | UAG1 | UAG1 | 5 OF 5. SCAFFOLD TO BE ERECTED TO SUPPORT PIPING FROM COMPRESSOR OUTLET TO EXISTING PIPING NORTH EAST END | 4475 | Daniel Edwards | 2016-05-21 | Mechanical | Med Duty | ERECT | Complete | 2016-05-28 | 2016-05-24
7919 | SITEWIDE - TBA | Sitewide | Takeover Scaffold | 4433 | Chistopher Reachy | 2016-05-19 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-19
7920 | SITEWIDE - TBA | Sitewide | Takeover Scaffold | 4434 | Chistopher Reachy | 2016-05-19 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-19
7921 | SITEWIDE - TBA | Sitewide | Takeover Scaffold | 4435 | Chistopher Reachy | 2016-05-19 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-19
7922 | SITEWIDE - TBA | Sitewide | Takeover Scaffold | 4436 | Chistopher Reachy | 2016-05-19 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-19
7923 | SITEWIDE - TBA | Sitewide | Takeover Scaffold | 4437 | Chistopher Reachy | 2016-05-19 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-19
7924 | SITEWIDE - TBA | Sitewide | Takeover Scaffold | 4438 | Chistopher Reachy | 2016-05-19 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-19
7925 | SITEWIDE - TBA | Sitewide | Takeover Scaffold | 4439 | Chistopher Reachy | 2016-05-19 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-19
7926 | SITEWIDE - TBA | Sitewide | Takeover Scaffold | 4440 | Chistopher Reachy | 2016-05-19 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-19
7927 | SITEWIDE - TBA | Sitewide | Takeover Scaffold | 4441 | Chistopher Reachy | 2016-05-19 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-19
7928 | SITEWIDE - TBA | Sitewide | Takeover Scaffold | 4442 | Chistopher Reachy | 2016-05-19 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-19
7929 | SITEWIDE - TBA | Sitewide | Takeover Scaffold | 4443 | Chistopher Reachy | 2016-05-19 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-19
7930 | SITEWIDE - TBA | Sitewide | Takeover Scaffold | 4444 | Chistopher Reachy | 2016-05-19 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-19
7931 | TBCA | TBCA level 3 - east | Modify Takeover Scaffold MAS 2222 | 4445 | Chistopher Reachy | 2016-05-19 | Scaffolding | Med Duty | MODIFY | Complete | 2016-05-19 | 2016-05-23
7931 | TBCA | TBCA level 3 - east | Takeover Scaffold MAS 2222 | 4445 | Chistopher Reachy | 2016-05-19 | Scaffolding | Med Duty | TAKEOVER | Complete | 2016-05-19 | 2016-05-23
7932 | SITEWIDE - TBA | Sitewide | Takeover Scaffold | 4446 | Chistopher Reachy | 2016-05-19 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-19
7933 | SITEWIDE - TBA | Sitewide | Takeover Scaffold | 4447 | Chistopher Reachy | 2016-05-19 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-19
7934 | SITEWIDE - TBA | Sitewide | Takeover Scaffold | 4448 | Chistopher Reachy | 2016-05-19 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-19
7935 | SITEWIDE - TBA | Sitewide | Takeover Scaffold | 4449 | Chistopher Reachy | 2016-05-19 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-19
7936 | TBBA | TR 2 TBBA | Dismantle 7183 | 4476 | Brett Taane | 2016-05-21 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-28 | 2016-05-22
7937 | TBBA | TR 2 TBBA | Dismantle 7184 | 4477 | Brett Taane | 2016-05-21 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-28 | 2016-05-22
7938 | SITEWIDE - TBA | Sitewide | Takeover Scaffold | 4450 | Chistopher Reachy | 2016-05-19 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-19
7939 | SITEWIDE - TBA | Sitewide | Takeover Scaffold | 4451 | Chistopher Reachy | 2016-05-19 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-19
7940 | SITEWIDE - TBA | Sitewide | Takeover Scaffold | 4452 | Chistopher Reachy | 2016-05-19 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-19
7941 | SITEWIDE - TBA | Sitewide | Takeover Scaffold | 4453 | Chistopher Reachy | 2016-05-19 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-19
7942 | SITEWIDE - TBA | Sitewide | Takeover Scaffold | 4454 | Chistopher Reachy | 2016-05-19 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-19
7943 | SITEWIDE - TBA | Sitewide | Takeover Scaffold | 4455 | Chistopher Reachy | 2016-05-19 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-19
7944 | SITEWIDE - TBA | Sitewide | Takeover Scaffold | 4456 | Chistopher Reachy | 2016-05-19 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-19
7945 | SITEWIDE - TBA | Sitewide | Takeover Scaffold | 4457 | Chistopher Reachy | 2016-05-19 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-19
7946 | SITEWIDE - TBA | Sitewide | Takeover Scaffold | 4458 | Chistopher Reachy | 2016-05-19 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-19
7947 | SITEWIDE - TBA | Sitewide | Takeover Scaffold | 4459 | Chistopher Reachy | 2016-05-19 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-19
7948 | SITEWIDE - TBA | Sitewide | Takeover Scaffold | 4460 | Chistopher Reachy | 2016-05-19 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-19
7948 | RBDE | RBDE / Pipe rack | Takeover 1731 RBDE | 4462 | Trevor Pike | 2016-05-21 | Chevron | Med Duty | Takeover | Complete | 2016-05-28 | 2016-05-21
7948 | RBDE | RBDE / Pipe rack | Dismantle 1731 - dnc 7948 RBDE | 4462 | Trevor Pike | 2016-05-21 | Chevron | Med Duty | Dismantle | Not Started | 2016-05-28
7949 | SITEWIDE - TBA | Sitewide | Takeover Scaffold | 4461 | Chistopher Reachy | 2016-05-19 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-19
7949 | JAA1 | JAA1 | JAA1 HM-2137 downers laydown yard need to erect scaffold to support straps for temporary roof/encapsulation for PFP works. As shown to Kevin Hegarty. SCAFFOLD/ STRAPS | 4480 | Felise Emelio | 2016-05-21 | Hertel | Med Duty | ERECT | Not Started | 2016-05-28
7950 | SITEWIDE - TBA | Sitewide | Takeover Scaffold | 4462 | Chistopher Reachy | 2016-05-19 | Scaffolding | Med Duty | TAKEOVER | Not Started | 2016-05-19
7951 | GAGA | GAGA level 3 | Erect scaffold to access but welds and pipe supports on line GACA-0A-09974.02 Level three west end of GAGA | 4486 | Charlie Bryce | 2016-05-22 | Mechanical | Med Duty | ERECT | complete | 2016-05-28 | 2016-05-22
7952 | GACA | GACA Levvel 3 west | Erect scaffold to access pipe support and guides on line GACA-0A-09974.02 west end level 3 | 4487 | Charlie Bryce | 2016-05-22 | Mechanical | Med Duty | ERECT | complete | 2016-05-28 | 2016-05-23
7953 | GACA | GACA Levvel 3 north / west | Erect scaffold to access butt welds and support on the north west corner of GACA level 3 on line 100-0A-09974.02 | 4488 | Charlie Bryce | 2016-05-22 | Mechanical | Med Duty | ERECT | Complete | 2016-05-28 | 2016-05-24
7954 | GAC1 | GAC1 | Build scaffolding shelving in stores container at GAC1 | 4490 | Charlie Bryce | 2016-05-22 | Mechanical | Med Duty | ERECT | complete | 2016-05-28 | 2016-05-24
7955 | GACA | GACA Levvel 3 west | Erect scaffold to access pipe welds on line GAC1-100-0D-09217-01 | 4491 | Charlie Bryce | 2016-05-22 | Mechanical | Med Duty | ERECT | complete | 2016-05-28 | 2016-05-24
7956 | GACA | GACA Levvel 3 north / west | Erect scaffold to access butt welds and pipe supports on line GACA-100-0A-09974-02 west end level 3 GACA | 4492 | Charlie Bryce | 2016-05-22 | Mechanical | Med Duty | ERECT | Complete | 2016-05-28 | 2016-05-24
7957 | GACA | GACA top level | Erect scaffold to access pipe support on level 3 north west corner GACA line number 100-0A-09974.02 | 4493 | Charlie Bryce | 2016-05-22 | Mechanical | Med Duty | ERECT | complete | 2016-05-28 | 2016-05-24
7958 | GACA | GACA top level | Erect scaffold to access butt welds and pipe supports level 3 west end GACA 100- 0A-09971.02 | 4494 | Charlie Bryce | 2016-05-22 | Mechanical | Med Duty | ERECT | complete | 2016-05-28 | 2016-05-22
7959 | GACA | GACA top level | Erect scaffold to access line stops and guides west end level 3 GACA | 4495 | Charlie Bryce | 2016-05-22 | Mechanical | Med Duty | ERECT | Complete | 2016-05-28 | 2016-05-23
7960 | GAC1 | GAC1 | Erect scaffold to allow for removal of pipe guides on line | 4496 | Charlie Bryce | 2016-05-22 | Mechanical | Med Duty | ERECT | complete | 2016-05-28 | 2016-05-24
7961 | GAC1 | GAC1 | Erect scaffold on vessel 0V-0931 in GAC1 | 4497 | Charlie Bryce | 2016-05-22 | Mechanical | Med Duty | ERECT | complete | 2016-05-28 | 2016-05-23
7962 | GACA | GACA top level | Erect scaffold on vessel 0V-0930 in GAC1 | 4498 | Charlie Bryce | 2016-05-22 | Mechanical | Med Duty | ERECT | complete | 2016-05-28 | 2016-05-23
7963 | DAAA | Domhas - sub station | Scaffolding frame required for the removal of electrical panels at sub station 83:69 | 4501 | Jared Ngaheu | 2016-05-22 | Scaffolding | Med Duty | ERECT | Not Started | 2016-05-28
7967 | INLET | Inlet Workshop | Build hop-up scaffold to allow welding on 750NB elbow to flange connection Located in the inlet workshop, heights and sizes to be discussed with SMP and welding supervision | 4507 | David Goodes | 2016-05-23 | Mechanical | Med Duty | ERECT | Complete | 2016-05-28 | 2016-05-24
7967 | INLET | Inlet Workshop | Dismantle hop-up scaffold to allow welding on 750NB elbow to flange connection Located in the inlet workshop, heights and sizes to be discussed with SMP and welding supervision | 4539 | David Goodes | 2016-05-26 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-28 | 2016-05-26
7968 | Jetty | JH45 | Erect handrail & gate on JH45 for penetration/protection | 4512 | Chris Hampson | 2016-05-24 | Mechanical | Med Duty | ERECT | Complete | 2016-05-24 | 2016-05-24
7969 | Jetty | Jetty | Dismantle hanging scaffold around see escape platform | 4513 | Chris Hampson | 2016-05-24 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-24 | 2016-05-24
7970 | Jetty | Jetty | Dismantle access tower around CCTV tower | 4517 | Chris Hampson | 2016-05-24 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-24 | 2016-05-24
7971 | Jetty | M1 | Takover up & over access on M1 caisson (M101 intrim) | 4526 | Chris Hampson | 2016-05-24 | Mechanical | Med Duty | DISMANTLE | Complete | 2016-05-24 | 2016-05-24
7971 | Jetty | M1 | Modify up & over access on M1 caisson (M101 intrim) | 4526 | Chris Hampson | 2016-05-24 | Mechanical | Med Duty | Modify | Complete | 2016-05-24 | 2016-05-24
7973 | MOF | MOF | Erect hard barricades to remover gridmesh | 4530 | John Young | 2016-05-25 | Mechanical | Med Duty | Erect | Not Started | 2016-05-25
7974 | DAAA | DAAA | require a scaffold urgently in DAAA for isolation purposes. This is so we can rectify a leaking airline as directed by the system owner and the Chevron punch list hit team | 4532 | Michael Finch | 2016-05-25 | Mechanical | Med Duty | ERECT | Not Started | 2016-05-25
7975 | RBCB | Inlet | RBCB HM-2118 need to provide access to pipe PRBCA00-0B-62036.01/B1 to install Insulation protection. Deck 600 below pipe. As shown to Kayne. | 4406 | Felise Emelio | 2016-05-19 | Hertel | Med Duty | ERECT | Not Started | 2016-05-24
7976 | RBCB | Inlet | RBCB HM-2117 north need to provide access on both sides of pipe 0B-62006.01 east & west to allow for Insulation protection. As shown to Kayne | 4407 | Felise Emelio | 2016-05-22 | Hertel | Med Duty | ERECT | Not Started | 2016-05-24 | 2016-05-22
7977 | AGRU 3 | Area 3 | Area 3 HM-2126 Hertel stores need to provide tubes to repair shade cloth for shelter. Contact Scaffold Coordinator on arrival for specs. | 4405 | Felise Emelio | 2016-05-19 | Hertel | Med Duty | ERECT | Not Started | 2016-05-24
7978 | GACA | GACA | Scaffold to access butt welds and pipe supports on line GACA-0A09974-02 eastern tank 0T-0915A level 2 GACA | 4533 | Charlie Bryce | 2016-05-25 | Mechanical | Med Duty | ERECT | In Progress | 2016-05-25
7979 | GACA | GACA | Scaffold to access cable ladder supports GAC1 as per model shot attached | 4534 | Charlie Bryce | 2016-05-25 | Mechanical | Med Duty | ERECT | Not Started | 2016-05-25
7980 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4540 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
7981 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4541 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
7982 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4542 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
7983 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4543 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
7984 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4544 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
7985 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4545 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
7986 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4546 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
7987 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4547 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
7988 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4548 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
7989 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4549 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
7990 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4550 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
7991 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4551 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
7992 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4552 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
7993 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4553 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
7994 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4554 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
7995 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4555 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
7996 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4556 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
7997 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4557 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
7998 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4558 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
7999 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4559 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8000 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4560 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8001 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4561 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8002 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4562 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8003 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4563 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8004 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4564 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8005 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4565 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8006 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4566 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8007 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4567 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8008 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4568 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8009 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4569 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8010 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4570 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8011 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4571 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8012 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4572 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8013 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4573 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8014 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4574 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8015 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4575 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8016 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4576 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8017 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4577 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8018 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4578 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8019 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4579 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8020 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4580 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8021 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4581 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8022 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4582 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8023 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4583 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8024 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4584 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8025 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4585 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8026 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4586 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8027 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4587 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8028 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4588 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8029 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4589 | Chris Reach | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8030 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4590 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8031 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4591 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8032 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4592 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8033 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4593 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8034 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4594 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8035 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4595 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8036 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4596 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8037 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4597 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8038 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4598 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8039 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4599 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8040 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4600 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8041 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4601 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8042 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4602 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8043 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4603 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8044 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4604 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8045 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4605 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8046 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4606 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8047 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4607 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8048 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4608 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8049 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4609 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8050 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4610 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8051 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4611 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8052 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4612 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8053 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4613 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8054 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4614 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8055 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4615 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8056 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4616 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8057 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4617 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8058 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4618 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8059 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4619 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8060 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4620 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8061 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4621 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8062 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4622 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8063 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4623 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8064 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4624 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8065 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4625 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8066 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4626 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8067 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4627 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8068 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4628 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8069 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4629 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8070 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4630 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8071 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4631 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8072 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4632 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8073 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4633 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8074 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4634 | Michel Stephens | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8075 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4635 | Murray Wetere | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8076 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4636 | Murray Wetere | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8077 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4637 | Murray Wetere | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8078 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4638 | Murray Wetere | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8079 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4639 | Murray Wetere | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8080 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4640 | Murray Wetere | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8081 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4641 | Murray Wetere | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8082 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4642 | Murray Wetere | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8083 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4643 | Murray Wetere | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8084 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4644 | Murray Wetere | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8085 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4645 | Murray Wetere | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8086 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4646 | Murray Wetere | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8087 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4647 | Murray Wetere | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8088 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4648 | Murray Wetere | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8089 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4649 | Murray Wetere | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8090 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4650 | Murray Wetere | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8091 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4651 | Murray Wetere | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8092 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4652 | Murray Wetere | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8093 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4653 | Murray Wetere | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8094 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4654 | Murray Wetere | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8095 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4655 | Murray Wetere | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8096 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4656 | Murray Wetere | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8097 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4657 | Murray Wetere | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8098 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4658 | Murray Wetere | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8099 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4659 | Murray Wetere | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8100 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4660 | Murray Wetere | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8101 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4661 | Murray Wetere | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8102 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4662 | Murray Wetere | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8103 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4663 | Murray Wetere | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8104 | SITEWIDE - TBA | Sitewide | TAKEOVER TAGS | 4664 | Murray Wetere | 2016-05-26 | inspectors | Med Duty | TAKEOVER | Not Started | 2016-05-26
8105 | Area 12 | TR3 Shakedown Yard | Build scaffold on internals on FAN A of MR Fans for TR3 located in the Shakedown Yard. | 4665 | Wayne Hall | 2016-05-26 | Mechanical | Med Duty | Erect | Not Started | 2016-05-26
8106 | Area 12 | TR3 Shakedown Yard | Build scaffold on internals on FAN B of MR Fans for TR3 located in the Shakedown Yard. | 4666 | Wayne Hall | 2016-05-26 | Mechanical | Med Duty | Erect | Not Started | 2016-05-26
Pending | SITEWIDE - TBA | Sitewide | CHEVRON TAKEOVER TAGS | 4328 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Not Started | 2016-05-11
Pending | SITEWIDE - TBA | Sitewide | CHEVRON TAKEOVER TAGS | 4338 | Mark orr | 2016-05-15 | Scaffolding | Med Duty | Takeover | Not Started | 2016-05-11
Pending | GAHG | GAHG | build scaff to access pipe shoe for welding | 4503 | Richard Jensen | 2016-05-22 | Mechanical | Med Duty | ERECT | In Progress | 2016-05-28
Pending | RBAM | RBAM | build sccaff to access flange bolt up and welding of guides on top of wall | 4504 | Richard Jensen | 2016-05-22 | Mechanical | Med Duty | ERECT | In Progress | 2016-05-28
Pending | GAHK | GAHK | build scaff to access support to weld guides | 4505 | Richard Jensen | 2016-05-22 | Mechanical | Med Duty | ERECT | In Progress | 2016-05-28
Pending | ACAA | Agru 3 RL33 | Build Scaffold dor access and welding on 750 NB pipe - CW35 CW35 and CW28 scaffold need to have de-attachable handrails to allow for spools | 4511 | David Goodes | 2016-05-24 | Mechanical | Med Duty | ERECT | Not Started | 2016-05-30
Pending | GAEA | GAEA | Inspect & Tag Scaffold decks on the West side of GAEA00-2E-1081/E1 , E2, E3 & E4 Fin Fan Coolers.Erect Hard Barricading & Foot protection to allow Painters to access Lower Nozzles on the East side of GAEA00-2E-1081/E1 , E2, E3 & E4 Fin Fan Coolers. Area Reviewed with Jared Ngaheu & Trevor Pike | 4536 | Trevor Pike | 2016-05-25 | Chevron | Med Duty | MODIFY | Not Started | 2016-06-01
Pending | GADA | GADA - Compressor Floor | A1872 - Dismantle | 4537 | Trevor Pike | 2016-05-25 | Chevron | Med Duty | Dismantle | Not Started | 2016-06-01
Pending | GADA | GADA - Compressor Floor | A2472 - Dismantle | 4538 | Trevor Pike | 2016-05-25 | Chevron | Med Duty | Dismantle | Not Started | 2016-06-01
Pending | GAA1 | GAA1 | Erect new scaffold Access to GAA1 0P-100003.01 | 4668 | Shane Shillabeer | 2016-05-26 | Mechanical | Med Duty | Erect | Not Started | 2016-05-28
Pending | SAYU | Jetty | SAYU HM-2143 Need to provide access to complete PFP works keep a min of 225mm clearance from PFP works allow for encapsulation. | 4669 | Felise Emelio | 2016-05-26 | Hertel | Med Duty | MODIFY | Not Started | 2016-06-01
Pending | SAYV | Jetty | SAYV HM-2144 Need to provide access to complete PFP works keep a min of 225mm clearance from PFP works. Remove timber planks and drop down to next lift. | 4670 | Felise Emelio | 2016-05-26 | Hertel | Med Duty | MODIFY | Not Started | 2016-06-01
Pending | SADA | SADA | SADA HM-2145 Need to provide access to complete PFP works keep a min of 225mm clearance from PFP works. Deck @ 1.8 from ground. | 4671 | Felise Emelio | 2016-05-26 | Hertel | Med Duty | Erect | Not Started | 2016-06-02
Pending | SADA | SADA | SADA HM-2145 Need to provide access to complete PFP works keep a min of 225mm clearance from PFP works. Deck @ 1.8 from ground. | 4672 | Felise Emelio | 2016-05-26 | Hertel | Med Duty | Erect | Not Started | 2016-06-02
Pending | GACA | Inlet GACA | Erect scaffold mid & top rail for grid mesh removal | 4677 | Steven Cameron | 2016-05-26 | Mechanical | Med Duty | Erect | Not Started | 2016-06-03
Pending | GACA | Inlet GACA | Erect scaffold mid & top rail for grid mesh removal | 4676 | Steven Cameron | 2016-05-27 | Mechanical | Med Duty | Erect | Not Started | 2016-06-03

## Customer
Downer Group Imports
Import: Customer
Name | Number | Accounting ID | Is Active | Email | Web Site | Business Phone | Fax Phone
APS |  |  | TRUE
APTS |  |  | TRUE
Blast/Painting |  |  | TRUE
Chevron |  |  | TRUE
CKJV |  |  | TRUE
Common User |  |  | TRUE
CSU |  |  | TRUE
E&I |  |  | TRUE
Electrical |  |  | TRUE
Hertel |  |  | TRUE
HSE |  |  | TRUE
Inspection |  |  | TRUE
inspectors |  |  | TRUE
KJV |  |  | TRUE
Mechanical |  |  | TRUE
Oceaneering NDT |  |  | TRUE
Painting/Electrical |  |  | TRUE
Pre-comm |  |  | TRUE
Rigging |  |  | TRUE
Scaffolding |  |  | TRUE
Scaffolding/Rigging/Crane |  |  | TRUE
Shutdown |  |  | TRUE
Sulzer |  |  | TRUE
Lucinate |  |  | TRUE

## Customer Contact
Downer Group Imports
Import: Customer Contact
Customer Name | First | Last | Title | Email | Phone | Fax | Cell | Notes | IsActive | User Name | Password
Trade | Blur | -- | [6 empty] | TRUE | Blur | password
APS | Tim | Whiffin | [6 empty] | TRUE | tim.whiffin | password
APTS | Felise | Emelio | [6 empty] | TRUE | felise.emelio | password
Blast/Painting | Adam | Stark | [6 empty] | TRUE | adam.stark | password
Chevron | Barry | Baker | [6 empty] | TRUE | barry.baker | password
Chevron | Bob | Brevker | [6 empty] | TRUE | bob.brevker | password
Chevron | Boyd | Edwards | [6 empty] | TRUE | boyd.edwards | password
Chevron | Colin | Maguire | [6 empty] | TRUE | colin.maguire | password
Chevron | Craig | Coombe | [6 empty] | TRUE | craig.coombe | password
Chevron | Dario | Archer | [6 empty] | TRUE | dario.archer | password
Chevron | Denny | Shewell | [6 empty] | TRUE | denny.shewell | password
Chevron | George | Fomin | [6 empty] | TRUE | george.fomin | password
Chevron | John | Watson | [6 empty] | TRUE | john.watson | password
Chevron | Mark | Orr | [6 empty] | TRUE | mark.orr | password
Chevron | Mike | Hemming | [6 empty] | TRUE | mike.hemming | password
Chevron | Steve | Denham | [6 empty] | TRUE | steve.denham | password
Chevron | Steve | Linton | [6 empty] | TRUE | steve.linton | password
Chevron | Steve | walker | [6 empty] | TRUE | steve.walker | password
Chevron | Sukahyur | Fahmy | [6 empty] | TRUE | sukahyur.fahmy | password
Chevron | Trevor | Pike | [6 empty] | TRUE | trevor.pike | password
Chevron | Vim | Vyadury | [6 empty] | TRUE | vim.vyadury | password
Chevron | Michael | Hemmings | [6 empty] | TRUE | michael.hemmings | password
CKJV | Brad | Scheers | [6 empty] | TRUE | brad.scheers | password
Common User | Craig | Fishlock | [6 empty] | TRUE | craig.fishlock | password
Common User | Matty | Hodges | [6 empty] | TRUE | matty.hodges | password
Common User | Nathan | Gleean | [6 empty] | TRUE | nathan.gleean | password
Common User | Lennie | Haira | [6 empty] | TRUE | lennie.haira | password
CSU | Todd | Lyons | [6 empty] | TRUE | todd.lyons | password
CSU | Andrew | Georgiou | [6 empty] | TRUE | andrew.georgiou | password
E&I | Adam | Keown | [6 empty] | TRUE | adam.keown | password
Electrical | Andrew | Ferres | [6 empty] | TRUE | andrew.ferres | password
Electrical | Andrew | Georgiou | [6 empty] | TRUE | andrew.georgiou | password
Electrical | Brian | Gray | [6 empty] | TRUE | brian.gray | password
Electrical | Bruce | Stephenson | [6 empty] | TRUE | bruce.stephenson | password
Electrical | David | Goodes | [6 empty] | TRUE | david.goodes | password
Electrical | Gavin | Hughes | [6 empty] | TRUE | gavin.hughes | password
Electrical | Geoff | Haren | [6 empty] | TRUE | geoff.haren | password
Electrical | George | Fomin | [6 empty] | TRUE | george.fomin | password
Electrical | Grant | Percy | [6 empty] | TRUE | grant.percy | password
Electrical | Gunther | Grossinger | [6 empty] | TRUE | gunther.grossinger | password
Electrical | Ian | Pritchard | [6 empty] | TRUE | ian.pritchard | password
Electrical | Jason | Hopkins | [6 empty] | TRUE | jason.hopkins | password
Electrical | Jeffery | Spry | [6 empty] | TRUE | jeffery.spry | password
Electrical | John | Pouroula | [6 empty] | TRUE | john.pouroula | password
Electrical | Mathew | Poole | [6 empty] | TRUE | mathew.poole | password
Electrical | Mick | Finch | [6 empty] | TRUE | mick.finch | password
Electrical | Mike | Knott | [6 empty] | TRUE | mike.knott | password
Electrical | Paul | Slocombe | [6 empty] | TRUE | paul.slocombe | password
Electrical | Felise | Emelio | [6 empty] | TRUE | felise.emelio | password
Hertel | James | Halliday | [6 empty] | TRUE | james.halliday | password
Hertel | John | Young | [6 empty] | TRUE | john.young | password
Hertel | Mark | Orr | [6 empty] | TRUE | mark.orr | password
Hertel | Troy | Brand | [6 empty] | TRUE | troy.brand | password
Hertel | Jim | McWhitner | [6 empty] | TRUE | jim.mcwhitner | password
HSE | Richard | Jensen | [6 empty] | TRUE | richard.jensen | password
Inspection | Chris | Reach | [6 empty] | TRUE | chris.reach | password
inspectors | Michel | Stephens | [6 empty] | TRUE | michel.stephens | password
inspectors | Murray | Wetere | [6 empty] | TRUE | murray.wetere | password
inspectors | Cristian | Niculescu | [6 empty] | TRUE | cristian.niculescu | password
KJV | George | Fomin | [6 empty] | TRUE | george.fomin | password
KJV | Mike | Hemming | [6 empty] | TRUE | mike.hemming | password
KJV | Steven | Linton | [6 empty] | TRUE | steven.linton | password
KJV | Adam | Keown | [6 empty] | TRUE | adam.keown | password

## Job Site
Downer Group Imports |  |  |  | Lucinate
Import: Job Site
Parent Location | Name | Customer Name | Number | Accounting ID | Is Active | Description | Track Scaffolds | Track Activities | Job List Label 1 | Job Text Label 1 | IsBillable
Gorgon | A-True | Lucinate |  |  | TRUE | Just a plain job | FALSE | FALSE | na | na | FALSE
Gorgon | [Empty String] | Scaffolding |  |  | TRUE | RBAK-RBAL Tug pen 2C-1105 Shipping steel ground level S/E CNR Ground N/E CNR MAJ2 Painters Container Abutment Centre over cable tray on beams Demin Shed | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | [Question Mark] | Chevron |  |  | TRUE | 3V1510 Dustcover | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | A | Scaffolding |  |  | TRUE | 86A - Dismantle 120A - Dismantle Jetty | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | AAA3 | Hertel |  |  | TRUE | AAA3 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | AAAA | Mechanical |  |  | TRUE | AGRU 1 AAAA AGRU 1 - AAAA - Ground Floor AGRU 1 - AAAA - Level 1 AGRU 1 - AAAA - Level 3 Agru 1 AAAA 1057AAAA AGRU 2 SOUTH END RL27000 AGRU 1 AAAA south level 3 - AAAA AAAA level 1 central AAA3 HM-1949 south/east tag 1071 AAA3 HM-1950 south/east tag 107 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | AAAB | scaffolding |  |  | TRUE | AAAB AAAB Central west side AAAB | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | AAAC | Hertel |  |  | TRUE | AAAC AGRU1 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | AAAE | Scaffolding |  |  | TRUE | TOP LEVEL AAAE | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | AAAF | Mechanical |  |  | TRUE | AREA 17 AAAF AGRU 1, - AAAF | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | AAAH | Mechanical |  |  | TRUE | AGRU 1, AAAH AAAH | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | ABAA | Scaffolding |  |  | TRUE | ABAA west side Level 1 AGRU 2, - ABAA AGRU 2, ABAH - ABAA ABAA west side Level 1 ABAA level 1 ABAA-ABAB CO2 Agru 2 Stores AGRU 2 ABAA OLD TAG 1165 -Agru 2 Lvl 1 S/E Area AGRU 2, ABAA AGRU 2, - ABAA ABAA AGRU2 ABAA AGRU 2 1ST Level S/E AGRU2 ABAA - RL 27 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | ABAB | scaffolding |  |  | TRUE | ABAB | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | ABAC | Sulzer |  |  | TRUE | AGRU 2, ABAC ABAC | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | ABAD | Hertel |  |  | TRUE | ABAD level 3 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | ABAE | Mechanical |  |  | TRUE | ABAE top level AGRU 2 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | ABAF | Mechanical |  |  | TRUE | AGRU 2, ABAF ABAF | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | ABAG | Mechanical |  |  | TRUE | ABAG | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | ABAH | Mechanical |  |  | TRUE | AGRU 2, ABAH AGRU 2, - ABAH AGRU 2, ABAH Ground level south/east corner ABAH level 1 west tag 5851 ABAH | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | Abutment Office Area | Scaffolding |  |  | TRUE | Abutment Office Area | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | ACAA | scaffolding |  |  | TRUE | south level 3 - ACAA Agru 3 RL33 ACAA | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | ACAD | Hertel |  |  | TRUE | ACAD | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | ACAG | Mechanical |  |  | TRUE | AGRU 3 underside of RV platform - ACAG | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | ACAH | Mechanical |  |  | TRUE | ACAH - AGRU 3 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | Agru 1 | Mechanical |  |  | TRUE | Agru 1 AAAD AAAA AGRU 1 AGRU 1 - CAAA AGRU 2 - Top Deck | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | Agru 2 | Scaffolding |  |  | TRUE | Agru MRU Tank Next to Murcury Sample Panel AGRU 2 AGRU 2 Ground floor AGRU 2 RL27 AGRU 2 RL33 Agru MRU Tank Agru 2 - MRU Tank ABAB AGRU 2 TAG D1410 AGRU2 AGRU 2, ABAG AGRU 2 filter platform stair access ABAA AGRU 2 Aru 2 RL 33 AGRU 2 South West AGRU 2 - C | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | Agru 3 | Sulzer |  |  | TRUE | Agru 3, GROUND LEVEL Agru 3 Level 1 Area 3 AGRU3, ACAA AGRU 3, ACAG AGRU 3, ACAC AGRU 3, ACAA Agru 3 Ground Level AGRU 3 - CCAA AGRU 3 AGRU 3, RL33 Agru 3 RL ACA3 RL44 Agru 3, GROUND LEVEL Agru 3, 20.7RL Agru 3, MRU stairway, 33RL Agru 3, RV platform, 45 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | Area 10 | Scaffolding |  |  | TRUE | AREA 10 yard Area 18 Oliver Yard container EST mech Work Shop container cyclone prep - Area10 mech Work Shop container cyclone prep - Area11 Court Yard Humpy Zrigging store Boiler workshop Area 10 saffold yar hump | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | Area 12 | Mechanical |  |  | TRUE | TR3 Shakedown Yard | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | Area 18 | Mechanical |  |  | TRUE | Inlet - Injection Pumps | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | Area 19 | Mechanical |  |  | TRUE | Laser Label Room - Oliver CBI laydown Yard CBI yard Oliver Yard | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | Area 2 | Scaffolding |  |  | TRUE | DAB | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | Area 20 | Mechanical |  |  | TRUE | 1199 - Baker Hughes Area L20 (near inlet area) H1960 - Baker Hughes Area L20 (near inlet area) | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | Area 4 | Scaffolding |  |  | TRUE | Stores at area 4 crib 6 access crib 5 acess sulza stairs elect tray frame smmokers hut-crib 9 Office Permit | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | AREA 8 | Scaffolding |  |  | TRUE | SAP - Area 8 AREA 8 / SAP WATER ON WALKWAY BETWEEN PONDS Sap 1 Area 8 LNG Tank 2 UTILITIES LNG TANK 2 LOWER DECK EAST SIDE | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | B8331 | Hertel |  |  | TRUE | B8331 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | BD`S | Electrical |  |  | TRUE | BDW & MDW | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | BD1W | Scaffolding |  |  | TRUE | BD1W | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | BD2W | Scaffolding |  |  | TRUE | BD2W Jetty LPW/BD2W BD2W | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | BD3E | Scaffolding |  |  | TRUE | jetty | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | BD3W | Scaffolding |  |  | TRUE | BD3W | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | BD4W | Scaffolding |  |  | TRUE | BD4W | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | BIBBY | Mechanical |  |  | TRUE | BIBBY/AMT CRUSADER | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | CAAA | Scaffolding |  |  | TRUE | Agru 1 - level Agru 1 Agru 1 - Level 1 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | CBAA | Mechanical |  |  | TRUE | AGRU 2 CO² Compressors Level 1 CBAA CBAA Agru 3 CBAA AGRU 2 - CBAA | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | CCAA | scaffolding |  |  | TRUE | 1st Level of CCAA east side of module Agru 3 CCAA CCAA | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | Condensate Tanks | Scaffolding |  |  | TRUE | Condensate Container 1 Condensate Container 2 Condensate Container 3 Condensate Tanks North west corner tank 3 condensate ground level Condensate Tanks Condensate Tanks 3 & 4 SR3138-Bund wall Northern end of Condensate Tank Condensate Tanks Condy tank 2 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | CT4W | Scaffolding |  |  | TRUE | CT4W | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | DAAA | Sulzer |  |  | TRUE | Domgas sth end of dom gas / level 2 DAAA DAAA level 1 DAAA 2 level south Domgas level 1 s/w DAAA DAAA - CKJV affold A2099 Area 14 - DAAA 1066 DAAA DAAA 1147 DAAA DAAA South East Corner DAAA AREA 14 - DAAA RV platform south east corner of central DAAA ARE | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | DAAF | Electrical |  |  | TRUE | DAAF - Tag 210 DAAF - Tag 1066 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | DABA | Chevron |  |  | TRUE | DABA | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | DOMGAS | scaffolding |  |  | TRUE | DAAA Ground level South side of B8372 (Substation) and HV transformer Domgas DAAA DOMGAS DAAA Ground level South side of B8372 (Substation) and HV transformer DOMGAS North End North end DOMGAS Ground level East side DOMGAS Ground level Ground level East | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | EAA1 | Hertel |  |  | TRUE | EAA1 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | EAAB | Hertel |  |  | TRUE | EAAB | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | EAAC | Hertel |  |  | TRUE | EAAC | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | EAAD | Hertel |  |  | TRUE | EAAD | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | ENERMECH YARD | Mechanical |  |  | TRUE | ENERMECH YARD | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | FUELGAS | Mechanical |  |  | TRUE | UACA TOP LEVEL OF RV PLATFORM FUELGAS | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | GAA1 | Scaffolding |  |  | TRUE | GAA1 GAA1 - RBAQ GAA1 INLET Inlet North GAA1 GAA1, MEG Injection Pumps Meg Injection Pumps GAA1 GAA1 GAA1 2nd Level GAA1 - Takeover H1005 GAA1 inlet Inlet injection Pumps Injection Pumps GAA1 Injetion Pumps GAA1 pump A - inlet GAA1 pump B- inlet GAA1 pum | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | GAA3 | Hertel |  |  | TRUE | GAA3 HM-165 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | GAA4 | Mechanical |  |  | TRUE | GAA4 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | GAAC | Rigging |  |  | TRUE | GAAC AREA 18 GAAC Level 1 / GAAF & GAAC GAAC | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | GAAF | Mechanical |  |  | TRUE | GAAF GAAF East side CSU GAAF - Inlet Area HIPPS pipe spools GAAF | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | GABE | Mechanical |  |  | TRUE | GABE | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | GAC1 | Scaffolding |  |  | TRUE | GAC1 Inlet South GAC1 GAC 1 Inlet GAC1 GAC1 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | GACA | Scaffolding/Rigging/Crane |  |  | TRUE | NE Crn Elev 31 GACA GAGA GACA 09D00-10 GACA GACA, Elevation 31 (5 platforms GACA South Inlet - GACA GACA 1st level NE cnr GACA Levvel 3 west GACA Levvel 3 north / west GACA top level GACA Inlet GACA GACA Sitewide INLET- GACA LVL 2 INLET- GACA GACA, Eastsi | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | GADA | Scaffolding |  |  | TRUE | GADA - Compressor Floor GADA GADA 1080 Vessel 739 GADA 1080 Vessel 957 GADA SR3371 - First level north east corner GADA Lube Oil Skid GADA Top Level Level 2 Gada - Inlet level 2 N/E Level 1 S/E up laadder minor land Level 2 South end Level 2 North S/E l | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | GAE1 | Hertel |  |  | TRUE | GAE1 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | Gaea | Scaffolding |  |  | TRUE | GAEA Top Level Westside of GAEA First Level Nth - East crn GAEA Lube oil Skid Level 1 North West GAEA Level 1 West Center GAEA 3RD LEVEL - MOBILE GAEA Level 1 hydro carbon line 2R10159 GAEA Level 1 center GAEA Level 2 S/E corner humpy center GAEA Level 2 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | GAGA | Scaffolding |  |  | TRUE | GAGA West side- Takeover G1143 GAGA GAGA west ground need GAGA GAGA - Inlet Inlet top floor GAGA GAGA west ground need Top Level GAGA GAGA top level GAGA LVL 2, NORTH EAST CORNER OF MODULE Level 2 GAGA 1st Level - GAGA 2nd Level - GAGA GAGA 2 level GAGA L | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | GAGA - Level 1 | scaffolding |  |  | TRUE | GAGA - Level 1 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | GAGA - Level 2 | scaffolding |  |  | TRUE | GAGA - Level 2 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | GAGA Level 2 | scaffolding |  |  | TRUE | GAGA Level 2 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | GAGB | Hertel |  |  | TRUE | GAGB WST | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | GAH1 | Mechanical |  |  | TRUE | GAH1 HM-164 GAH1 Meg tank 0941 Inlet GAH1 Meg Pump DN350Line GAH1 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | GAH3 | Scaffolding/Rigging/Crane |  |  | TRUE | GAH3 1st Level | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | GAH4 | Mechanical |  |  | TRUE | GAh4 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | GAHG | Mechanical |  |  | TRUE | GAHG | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | GAHJ | scaffolding |  |  | TRUE | GAHJ | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | GAHJ - Level 1 | scaffolding |  |  | TRUE | GAHJ - Level 1 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | GAHJ - Level 2 | scaffolding |  |  | TRUE | GAHJ - Level 2 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | GAHJ - Level 3 | scaffolding |  |  | TRUE | GAHJ - Level 3 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | GAHK | scaffolding |  |  | TRUE | GAHK upper deck GAHK GAHK MEG Transfer Pumps GAHk / RBAN GAHK | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | GAHK | Mechanical |  |  | TRUE | GAHK | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | GAHK South | scaffolding |  |  | TRUE | GAHK South | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | GAHL | Mechanical |  |  | TRUE | GAHL North End GAHL - North end GAHL GAHL HM-1993 1st grid mesh level south end GAHL - Inlet Area | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | GAHL | Blast/Painting |  |  | TRUE | GAHL | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | GAHL Lvl 1 | scaffolding |  |  | TRUE | GAHL Lvl 1 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | Gorgon Slug Catcher | Mechanical |  |  | TRUE | Gorgon Slug Catcher | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | GTG3 | Mechanical |  |  | TRUE | GTG3 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | GTGS | Mechanical |  |  | TRUE | GT3 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | GUA | Mechanical |  |  | TRUE | GUA GUA - MAJ2 / Tank OT-6401 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | INLET | Scaffolding |  |  | TRUE | GAA1 RBAE GAA5 GAA3 Inlet Inlet GACA Inlet Inlet - GAAC Inlet - GAA1 Inlet - RBAH RBAQ PRODUCTION PUMP North Inlet - RBAQ Tool store inlet GAA1 Injection Pumps Inlet north laydown yard GAH1 RBAL Inlet, GAGA top level INLET, RBAD, Top Level GAGA INLET, GA | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | INLET GAGA | Mechanical |  |  | TRUE | INLET GAGA | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | JAA1 | Hertel |  |  | TRUE | JAA1 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | JABH | Chevron |  |  | TRUE | JABH | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | JAC1 | Mechanical |  |  | TRUE | JAC1 JAC1 - tanks no:OV-0970 and OV-0971 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | JAC1 West | Hertel |  |  | TRUE | JAC1 West | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | JACA | Scaffolding |  |  | TRUE | ACA-JAC1 HM-162 JACA HM-163 JACA HM-1724 JACA 2ND LEVEL JACA Area 18 JACA JACA Inlet | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | JACA Ground | scaffolding |  |  | TRUE | JACA Ground | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | JACA Lvl 3 | scaffolding |  |  | TRUE | JACA Lvl 3 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | jada | Scaffolding |  |  | TRUE | JADA JADA GROUND | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | JADA - Level 2 | scaffolding |  |  | TRUE | JADA - Level 2 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | JADB | Scaffolding/Rigging/Crane |  |  | TRUE | JADB-RBAC GROUND LVL | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | Jetty | Scaffolding |  |  | TRUE | JETTY HEAD JETTY MOP JETTY L9-L10 L5-L6 L9-L10 TUG PEN GANGWAYS T5 t7 L5/L6 jetty passing bay LPW L5 L5 L9 L11 M1 M5 L7 JH45 Jetty Jetty MD4W BD4W BD3W LPW LEVEL 1 LPW LPW TOP LEVEL Jetty L6 Jetty - L13 Jetty - LPW-Road side JAA1 Jetty - MD4W Jetty - | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | Jetty AREA 2 | Pre-comm |  |  | TRUE | JETTY AREA 2 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | JH23 | Mechanical |  |  | TRUE | JETTY head 23 JH23 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | JH4 | scaffolding |  |  | TRUE | JH4 - Jetty | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | L10 | Electrical |  |  | TRUE | L9 - Tag no 972 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | L11 | Mechanical |  |  | TRUE | Jetty | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | L11/12 | Electrical |  |  | TRUE | Jetty L11/L12 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | L13 | Scaffolding |  |  | TRUE | L13 L13-14 jetty Area 1 JETTY - L13 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | L13/14 | Electrical |  |  | TRUE | Jetty L13/L14 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | L5/6 | Mechanical |  |  | TRUE | L5 Tag Number 964 SR3679 - Jetty L5/L6 L5 jetty | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | L7 | Mechanical |  |  | TRUE | L7 Tag number 338 L7 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | L7/8 | Electrical |  |  | TRUE | Jetty L7/L8 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | L9/10 | Mechanical |  |  | TRUE | L9/L10 L9 Jetty | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | LNG Tank 1 | Scaffolding |  |  | TRUE | LNG Tank 1VAAA | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | LNG TANK AREA | Chevron |  |  | TRUE | LNG TANK AREA | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | LP9-LP10 | Hertel |  |  | TRUE | LP9-LP10 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | LPE | Scaffolding |  |  | TRUE | LPE | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | LPW | Scaffolding |  |  | TRUE | Jetty - LPW Jetty LPW Gang way LPW Dolphins MD1,2,3,4,5,6E and BD1,2,3,4E LWP South Side at MDW1, NMDW2, MDW3 LWP North side. MD4W,MD5W. LPW LPW-SAYE LPW-SAYN LPW Jetty JETTY L7/L8 JETTY L8 LPW LPW "S" bend LNG line PW-SAYN L9/L10 LPW/BD2W | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | M1 | Mechanical |  |  | TRUE | Abutment to M1 M1/2 RWJ/M1 JETTY | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | M2 | Scaffolding |  |  | TRUE | M2 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | M4 | Scaffolding |  |  | TRUE | M4 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | MAG | Mechanical |  |  | TRUE | Jetty - MAG | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | MAJ | Scaffolding |  |  | TRUE | MAJ jetty | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | MAJ2 | Scaffolding |  |  | TRUE | South East Tank 2 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | MAM | Scaffolding |  |  | TRUE | Shakedown Yard sub station | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | MD1 | Scaffolding |  |  | TRUE | MD1 - MD5 MD1 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | MD2 | Scaffolding |  |  | TRUE | MD2 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | MD3 | Scaffolding |  |  | TRUE | MD3 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | MD4E | Scaffolding |  |  | TRUE | jetty | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | MD4W | Scaffolding |  |  | TRUE | Jetty MD4W | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | MD5E | Scaffolding |  |  | TRUE | Jetty | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | MD5W | Scaffolding |  |  | TRUE | Capstan MD5W Jetty MD5W | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | MD6W | Scaffolding |  |  | TRUE | Jetty MD6W | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | MEG | Mechanical |  |  | TRUE | JACA Meg Pump DN350Line Meg MEG Injection | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | MOF | Scaffolding |  |  | TRUE | M1 - MOF MOF, SCABL MOF, SCCN MOF, SCBG MOF, SCCW, LOOP 7 MOF, SCBK, SCBY MOF, SCBC, SCBZ MOF, SCBX MOF, SCBJ MOF, SCJB MOF, SCCZ, SCBG MOF, SCBF MOF, SCBE MOF, SCBD MOF, SCBC, SCCU MOF, SCBC MOF, SCBA MOF, SCAR MOF, SCAQ MOF, SCCQ MOF, SCAN MOF, SCAL MOF | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | MOP | Electrical |  |  | TRUE | MOP – M1 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | MRU | Mechanical |  |  | TRUE | Top of MRU DOMGAS | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | Oliver | Scaffolding |  |  | TRUE | OLIVER YARD Oliver container shelves stores right side containers / humpy access left of stores container access stores bench / shade protetion Generator Cover sataight hard barricade smokers humpy Mobile Humpy | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | POF | Scaffolding |  |  | TRUE | POF POF CRIB 4 STAIR ACCESS POF CRIB 3 STAIR ACCESS POF CRIB 2 STAIR ACCESS POF CRIB 1 STAIR ACCESS | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | PR COMP | Scaffolding/Rigging/Crane |  |  | TRUE | PR COMP PR COMPRESSOR | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBAA | Scaffolding |  |  | TRUE | RBAA INLET RBAA - RBAC | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBAB | Scaffolding |  |  | TRUE | RBAB INLET RBAB stair access RBAB - Tag H1535 RBAB RBAB - TAG 1095 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBAC | Scaffolding/Rigging/Crane |  |  | TRUE | RBAC RBAC - Tag ID #G1462 RCAC RBAC RBAC/GACB GROUND LVL | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBAC-RBAE | Hertel |  |  | TRUE | RBAC-RBAE | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBAD | Mechanical |  |  | TRUE | RBAD INET - RBAD1081 Inlet West end RBAD RBAD | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBAE | Scaffolding |  |  | TRUE | RBAE-RBAC up ladder RBAE-RBAP RBAE RBAE - Scaff tag: H1958 RBAE-RBAC RBAE Inlet Inlet Site Wide | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBAF | Scaffolding |  |  | TRUE | RBAF | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBAG | Scaffolding |  |  | TRUE | RBAG H1950 Inlet | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBAH | scaffolding |  |  | TRUE | RBAH RBAH South RBAH West RBAH LVL 1 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBAJ | Scaffolding |  |  | TRUE | RBAJ nother / South piperack | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBAK | scaffolding |  |  | TRUE | RBAK | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBAL | Scaffolding |  |  | TRUE | RBAL RBAL - Inlet | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBAL/GAHL | scaffolding |  |  | TRUE | RBAL/GAHL | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBAL-RBAK | Scaffolding |  |  | TRUE | RBAL-RBAK RBAL Inlet | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBAM | Mechanical |  |  | TRUE | RBAM | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBAN | scaffolding |  |  | TRUE | RBAN | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBAP | Chevron |  |  | TRUE | RBAP | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBAQ | scaffolding |  |  | TRUE | RBAQ north RBAQ RBAQ inlet RBAQ | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBAQ North | scaffolding |  |  | TRUE | RBAQ North | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBCA | Scaffolding |  |  | TRUE | RBCA RBCA EST ref to dnc 4159 RBCA Inlet Inlet RBCA / RBCN | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBCB | Hertel |  |  | TRUE | RBCB Inlet Inlet | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBCC | Chevron |  |  | TRUE | RBCC | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBCD | Chevron |  |  | TRUE | RBCD | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBCE | Hertel |  |  | TRUE | RBCE | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBCF | Hertel |  |  | TRUE | RBCF | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBDD | Hertel |  |  | TRUE | RBDD | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBDE | Mechanical |  |  | TRUE | RBDE RBDE / RBDQ RBDE / Pipe rack | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBDH | Electrical |  |  | TRUE | RBDH, PIPERACK | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBDM | Chevron |  |  | TRUE | RBDM RBDM are 14 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBDS | Scaffolding |  |  | TRUE | Train 3 - RBDS | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBFA | Scaffolding |  |  | TRUE | INLET | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBFB | Scaffolding |  |  | TRUE | RBFB west of lng 2 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBFC | Mechanical |  |  | TRUE | AREA 9 RBFC | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | RBFD | Mechanical |  |  | TRUE | AREA 9 RBFD | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SADA | Scaffolding |  |  | TRUE | SADA fin fan level 4 west end SADA SAGA tag 2549 SADA - 3rd Level SADA - Top level SADA East Side, Near Road SADA SADA east sdie SADA level 3 East face Level 2 S/W crn Site Wide SADA lagging accesss level SADA lagging accesss level 1 SADA | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SADA TOP LVL | scaffolding |  |  | TRUE | SADA TOP LVL | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SAF1 | Scaffolding |  |  | TRUE | SAF1 UAEB South East Tank 2 / BEHIND BOG FLARES SAF1 BEHIND BOG FLARES | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SAGA | Chevron |  |  | TRUE | SAGA | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SAGB | Scaffolding |  |  | TRUE | SAGB SAGB top level | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SAH | Scaffolding |  |  | TRUE | N/W corner condensate tank 3 North wall inside condi tanks SAH1 Condi tanks east wall SAH1 SAH Utilities LNG tank ground level Utilities LNG tank 1 top Centre Utilities LNG tank 1 top eastern landing Utilities LNG tank 1 lower level eastern face | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | sah1 | Scaffolding |  |  | TRUE | SAH1 SAH1 - Condy tank area SAH1 - Condensate Tanks SAH1 Condensate tank skid 6157 - SAH1 adjacent condensate pumps outside north bund wall SAH1 adjacent condensate pumps outside north bund wall Condi tanks east wall SAH1 Condensate Tanks 6676-A SAH1 adja | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SAHA | Scaffolding |  |  | TRUE | Condensate Tanks SAHA NW Corner Condensate Tanks SAHA Northern Wall Condensate Tanks SAHA between T3/T4 Condensate Tanks SAHA Condy tanks Site Wide | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SANA | Mechanical |  |  | TRUE | SANA Pumps | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SAP | Scaffolding |  |  | TRUE | SAGB Mercury management facility SAP Condensate Tanks Stores Condensate Takns Tank 4 Condensate tanks East side platform between con tank 3 and 4 Platform 32, Eastern wall, Tank 4 Condensate Area RBFD / E North RBFC / FD North RBFB / C North RBFB Area | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SARA | Scaffolding |  |  | TRUE | SARA Mercury Management Facility building 782 at the interim mercury management facility, adjacent to area 10. SARA Mercury Management East SARA Mercury Management South SARA Mercury Management West SARA SARA on Skid | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SASA | KJV |  |  | TRUE | SASA | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SASC | Scaffolding |  |  | TRUE | SASC | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SASD | Scaffolding |  |  | TRUE | SASD | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SASG | Scaffolding |  |  | TRUE | SASG by sada toilets to access lagging for hertel | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SASL | Hertel |  |  | TRUE | SASL | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SASN | Scaffolding |  |  | TRUE | SASN | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SATB | Hertel |  |  | TRUE | SATB | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SATE | Scaffolding |  |  | TRUE | SAT | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SATU | Mechanical |  |  | TRUE | SATU Pig launcher | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SAYC | E&I |  |  | TRUE | SAY C | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SAYL | Hertel |  |  | TRUE | SAYL | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SAYM | Hertel |  |  | TRUE | LPW-SAYM | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SAYN | Hertel |  |  | TRUE | SAYL-SAYN SAYN | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SAYU | Hertel |  |  | TRUE | Jetty | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SAYV | Hertel |  |  | TRUE | LPW-SAYV Jetty | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SCAC | Scaffolding |  |  | TRUE | SCAC | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SCAD | Scaffolding |  |  | TRUE | SCAD | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SCAH | Scaffolding |  |  | TRUE | SCAH | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SCAJ | Scaffolding |  |  | TRUE | SCAJ | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SCCD | Scaffolding |  |  | TRUE | SCCD | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SCCE | Scaffolding |  |  | TRUE | SCCE | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SCCF | Scaffolding |  |  | TRUE | SCCF | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SCCG | Scaffolding |  |  | TRUE | SCCG Sitewide | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SCCH | Scaffolding |  |  | TRUE | SCCH MOF | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SCCI | Scaffolding |  |  | TRUE | MOF | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SCCK | Scaffolding |  |  | TRUE | SCCK | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SCCO | Scaffolding |  |  | TRUE | SCCO / SCCF | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SCJC | Hertel |  |  | TRUE | SCJC | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | SITEWIDE - TBA | Scaffolding |  |  | TRUE | Sitewide Site Wide Train2 Sitewide AREA 3 - HERTEL COMPOUND | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | T12 | Mechanical |  |  | TRUE | T12 T13 T14 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | T5 | Electrical |  |  | TRUE | T5 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | T6 | Mechanical |  |  | TRUE | T6 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | T7 | Mechanical |  |  | TRUE | Jetty T7 T7 jetty | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | TAAA | Chevron |  |  | TRUE | TAAA TAAA east side | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | TAC1 | Chevron |  |  | TRUE | TAC1 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | TACA | 0 |  |  | TRUE | TACA - Train 1 top level Train 1 Turbine TACA TACA TACA Train 1 Shutdown Train 1 Ground Level - TACA TACA Ground level Train 1 Level 3 - TACA Train 1 TOP Level - TACA Train 1 Level 1 - TACA TR1 1st Level TACA Train 1 TACA TRAIN 1 TACA Level 3 TACA Train 1 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | TACA LVL 3 | scaffolding |  |  | TRUE | TACA LVL 3 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | TACA LVL 4 | scaffolding |  |  | TRUE | TACA LVL 4 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | TACA Top Level | scaffolding |  |  | TRUE | TACA Top Level | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | TADA | Mechanical |  |  | TRUE | TADA TADA Level 4 TRAIN 1 - TADA Train 1 TADA | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | TAF1 | Scaffolding |  |  | TRUE | TAF1 TAF1 - Ground level North | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | TAFA | Scaffolding |  |  | TRUE | Train 1 Turbine TAFA TAFA TAFA PR Compressor TAFA Ground level TAFA TAFA Compresso | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | TAG1 | Hertel |  |  | TRUE | TAG1 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | TAHA | Scaffolding |  |  | TRUE | Train 1 TAHA TAHA train 1 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | TAJA | Scaffolding |  |  | TRUE | TAJA Level 2 TAJA Level 3 level 2 TAJA TAJA Train level 1 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | TAJB | Scaffolding |  |  | TRUE | AREA 17 TAJB TRAIN 1 - TAJB Stair tower ground Level TAJB West face ground Level TAJB | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | TAJD | Scaffolding |  |  | TRUE | train 1 TAJD Train 1 - TAJD AREA 17 TAJD TAJD - fin fans | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | TANK 3 | Mechanical |  |  | TRUE | North West Corner Tank 3 - Condensate Ground Level South Western wall Tank 3 Access Platform | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | TBAA | Scaffolding |  |  | TRUE | TBAA 2V-1201 TBAA TBBA TRAIN 2 RE-BOILERS TBAA Train 2 TRAIN 2 Re-Boilers TBBA -2E-1602 TRAIN 2 Re-Boilers TBBA -2E-1603 TRAIN 2 Re-Boilers TBBA -2E-1601 Train 2 TBAA TBAA Train 2 4th level TBAA Train 2 2 level North Side level 1 Level 1 Hydro 2P13001 Va | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | TBAA | Hertel |  |  | TRUE | TBAA | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | TBAB | Mechanical |  |  | TRUE | TBAB Train 2 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | TBBA | Scaffolding |  |  | TRUE | TBBA TBBA TRAIN 2 RE-BOILERS TBBA South TBBA TRAIN 2 RE-BOILERS TRAIN 2 Re-Boilers TBBA -2E-1604 TRAIN 2 Re-Boilers TBBA -2E-1601 TBBA TBAA VESSEL 2V-1201 TRAIN 2 TR 2 TBBA Level 1 south Site Wide Train2 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | TBCA | Scaffolding |  |  | TRUE | TBCA Train 3 TBCA level 3 - east | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | TBF1 | Mechanical |  |  | TRUE | TRAIN 2, TBF1 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | TBG1 | Mechanical |  |  | TRUE | TBG1 Module (A) | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | TBJD | Mechanical |  |  | TRUE | TBJD - Ground Level Nth Train2 - TBJD module, 1st fl, temp water pumps | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | TBJF | Mechanical |  |  | TRUE | TBJF Tain 2 take over E2338 TRAIN 2 TBJF TBJF Train 2 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | Top of ladder - UAMA Heater | scaffolding |  |  | TRUE | Top of ladder - UAMA Heater | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | TRAIN 1 | 0 |  |  | TRUE | TACA Overhead Crane repair Scaffold A Train 1 Overhead Crane repair Scaffold B manway M50 on 1E-1531 manway M55 on 1E-1531 manway M59 on 1E-1531 Train 1, TACA, Level 3 TR1 Fin Fan Level TRAIN 1 TACA Level 3 TACA TAJA TADA MR FANS T1 TACA TRAIN 1, TACA VES | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | Train 1 Fin Fan Modules | scaffolding |  |  | TRUE | Train 1 Fin Fan Modules | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | TRAIN 2 | Mechanical |  |  | TRUE | TR1 Fin Fan Level TBAA TBAA, Sth grid mesh level 1 SCM1 TRAIN 2- TBF1 Module (A) TRAIN 2- TBF1 Module (B) TRAIN 2- TBG1 Module (A) TRAIN 2- TBG1 Module (B) TBJA South Train 2 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | TRAIN 2 TBAA | Chevron |  |  | TRUE | TRAIN 2 TBAA | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | Train 3 | Scaffolding |  |  | TRUE | TR3 3V1510 Dustcover TR3 3V 1510 TRAIN 3- TCF1 Module (A) TRAIN 3- TCF1 Module (B) TRAIN 3- TCG1 Module (A) TRAIN 3- TCG1 Module (B) 3V150 Train 3 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | UACA | scaffolding |  |  | TRUE | UACA UACA Area 14 UACA Area 14 top level (Under) sth end UACA UACA East/West Piperack - 721 UACA NW corner UACA S/W UACA S/W 1st Lvl UACA UACA Fin Fan Lvl UACA Est FUEL GAS Sth/West crn UACA sth -west crn UACA East/West Piperack - 721 AREA 14 UACA UACA Mo | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | UACB | scaffolding |  |  | TRUE | UACB UACB 2nd Level West side UACB Ground Level 1st Level UACB Top of MRU UACB 2nd Level UACB West side of module | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | UAEA | Scaffolding |  |  | TRUE | UAEA AREA 14 UAEA under finfans UAEA | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | UAG1 | Scaffolding |  |  | TRUE | UAG1 | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | UAGA | Scaffolding |  |  | TRUE | Northern end of module UAG UAGA | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | UAMA | scaffolding |  |  | TRUE | UAMA | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | UAMA GATE | scaffolding |  |  | TRUE | UAMA GATE | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | UAMA Mobile | scaffolding |  |  | TRUE | UAMA Mobile | TRUE | TRUE | Load Limit | Request Number | FALSE
Gorgon | UTILITY WEST | Electrical |  |  | TRUE | DAA | TRUE | TRUE | Load Limit | Request Number | FALSE

## Job Site List Values
Downer Group Imports
Import: Job Site List Value
Job Site Name | List | Value
AAAA | Activity List 1 | Med Duty
AGRU 2 | Activity List 1 | Med Duty
GAEA | Activity List 1 | Med Duty
Jetty | Activity List 1 | Med Duty
MOP | Activity List 1 | Med Duty
UACB | Activity List 1 | Med Duty
UAEA | Activity List 1 | Med Duty
MOF | Activity List 1 | Med Duty
AAAA | Scaffold Tag Activity Type | DISMANTLE
AAAA | Scaffold Tag Activity Type | ERECT
AAAA | Scaffold Tag Activity Type | MODIFY
AAAA | Scaffold Tag Activity Type | TAKEOVER
AGRU 2 | Scaffold Tag Activity Type | DISMANTLE
AGRU 2 | Scaffold Tag Activity Type | ERECT
AGRU 2 | Scaffold Tag Activity Type | MODIFY
AGRU 2 | Scaffold Tag Activity Type | TAKEOVER
GAEA | Scaffold Tag Activity Type | DISMANTLE
GAEA | Scaffold Tag Activity Type | ERECT
GAEA | Scaffold Tag Activity Type | MODIFY
GAEA | Scaffold Tag Activity Type | TAKEOVER
Jetty | Scaffold Tag Activity Type | DISMANTLE
Jetty | Scaffold Tag Activity Type | ERECT
Jetty | Scaffold Tag Activity Type | MODIFY
Jetty | Scaffold Tag Activity Type | Takeover
MOP | Scaffold Tag Activity Type | ERECT
UACB | Scaffold Tag Activity Type | DISMANTLE
UACB | Scaffold Tag Activity Type | ERECT
UAEA | Scaffold Tag Activity Type | ERECT
UAEA | Scaffold Tag Activity Type | MODIFY
UAEA | Scaffold Tag Activity Type | Takeover
MOF | Scaffold Tag Activity Type | MODIFY

## Scaffold Tags
Downer Group Imports
Import: Scaffold Tag
Job Site Name | Tag | Order | Priority | Project | Step | Status | Notes | Location | Planned Load Date | Planned Build Date | Planned Dismantle Date | Actual Load Date | Actual Build Date | Actual Dismantle Date
AAAA | 5000 |  |  |  |  | On Rent | [5 empty] | 2016-01-22
AGRU 2 | 5001 |  |  |  |  | On Rent
UAEA | 5002 |  |  |  |  | On Rent | [5 empty] | 2016-02-03
UAEA | 5003 |  |  |  |  | On Rent | [5 empty] | 2016-01-28
Jetty | 5004 |  |  |  |  | On Rent | [5 empty] | 2016-01-30
GAEA | 5005 |  |  |  |  | On Rent | [5 empty] | 2016-01-29
GAEA | 5006 |  |  |  |  | On Rent | [5 empty] | 2016-01-29
UACB | 5007 |  |  |  |  | On Rent | [5 empty] | 2016-02-07
MOF | 5008 |  |  |  |  | On Rent
MOF | 5009 |  |  |  |  | On Rent
MOF | 5010 |  |  |  |  | On Rent
MOF | 5011 |  |  |  |  | On Rent
MOF | 5012 |  |  |  |  | On Rent
MOF | 5013 |  |  |  |  | On Rent
MOF | 5014 |  |  |  |  | On Rent
MOF | 5015 |  |  |  |  | On Rent
MOF | 5016 |  |  |  |  | On Rent
MOF | 5017 |  |  |  |  | On Rent
MOF | 5018 |  |  |  |  | On Rent
MOF | 5019 |  |  |  |  | On Rent
MOF | 5021 |  |  |  |  | On Rent

## Scaffold Tag Activities
Downer Group Imports
Import: Scaffold Tag Activity
Tag | Job Site Name | Summary | Detail | Activity Type | Shift | Request Date | Planned Date | Actual Date | Planned Load Date | Text | List 1
5000 | AAAA | build access scaffold on base of AAAF vessel for l | build access scaffold on base of AAAF vessel for lagging and painting | ERECT |  | 2016-01-22 |  | 2016-01-22 |  | 1996 | Med Duty
5000 | AAAA | Summary 2651 | Dismantle & re-build access scaffold on base of AAAF vessel for lagging and painting | MODIFY |  | 2016-01-22 |  | 2016-01-22 |  | 2651 | Med Duty
5001 | AGRU 2 | Modify Scaffold and remove 1mx1m in floor for inst | Modify Scaffold and remove 1mx1m in floor for installation of cable ladder. No tag attached | TAKEOVER |  | 2016-04-13 |  | 2016-04-17 |  | 3204 | Med Duty
5001 | AGRU 2 | Summary 3731-1 | Modify Scaffold and remove 1mx1m in floor for installation of cable ladder. | MODIFY |  | 2016-04-28 |  | 2016-04-30 |  | 3731-1 | Med Duty
5001 | AGRU 2 | Summary 3731-2 | Remove 1 meter square section of the existing scaffold to allow for th installation of the cable ladder down to the Mercury Sampling Panel. This will also involve removing a section of the floor boards. | MODIFY |  | 2016-04-28 |  | 2016-05-05 |  | 3731-2 | Med Duty
5002 | UAEA | Scaff handrails to be around top of tanks, single | Scaff handrails to be around top of tanks, single access point with board walkdway from tank 1 to tank 2. UACE module west side in construction area | ERECT |  | 2016-01-28 |  | 2016-02-03 |  | 2037 | Med Duty
5002 | UAEA | Summary 2117 | Modify pipe supports | MODIFY |  | 2016-02-06 |  | 2016-02-06 |  | 2117 | Med Duty
5003 | UAEA | Scaff access to remove & install fitting for level | Scaff access to remove & install fitting for level gauges. UACE heater medium module, west side of module in construction area | ERECT |  | 2016-01-28 |  | 2016-01-28 |  | 2038 | Med Duty
5003 | UAEA | Summary 2118 | Modify pipe supports | MODIFY |  | 2016-02-06 |  | 2016-02-06 |  | 2118 | Med Duty
5004 | Jetty | Can a third handrail (Scaffold) be added to the Tu | Can a third handrail (Scaffold) be added to the Tug Pen Gangways where we have an above head Flourescent light fitting ( 4 light fittings per Gangway). Third handrail is for | ERECT |  | 2016-01-29 |  | 2016-01-30 |  | 2048 | Med Duty
5005 | GAEA | Barricade around sensor probes on second level - w | Barricade around sensor probes on second level - western edge | ERECT |  | 2016-01-29 |  | 2016-01-29 |  | 2050 | Med Duty
5005 | GAEA | Summary 4531 | Re-instate Grid mesh & Removal of Scaffold GAEA Level 2 | MODIFY |  | 2016-05-25 |  |  |  | 4531 | Med Duty
5006 | GAEA | Build scaffold to enable the installation of gaske | Build scaffold to enable the installation of gaskets on sensor probe, 2nd level, central/eastern corner | ERECT |  | 2016-01-29 |  | 2016-01-29 |  | 2051 | Med Duty
5007 | UACB | Catalyst loading hopper to be put in place on the | Catalyst loading hopper to be put in place on the top of vessel 4401 fuelgas. Once hopper is in place the access scaffold needs to be built with sulzers input so theres no confusion like last time | ERECT |  | 2016-01-29 |  | 2016-02-07 |  | 2052 | Med Duty
5008 | MOF | Modify existing scaffold to eliminate "LNG Line" C | Modify existing scaffold to eliminate "LNG Line" Clashes | MODIFY |  | 2016-01-31 |  | 2016-01-31 |  | 2053 | Med Duty
5009 | MOF | Modify existing scaffold to eliminate "LNG Line" C | Modify existing scaffold to eliminate "LNG Line" Clashes | MODIFY |  | 2016-01-31 |  | 2016-01-31 |  | 2054 | Med Duty
5010 | MOF | Modify existing scaffold to eliminate "LNG Line" C | Modify existing scaffold to eliminate "LNG Line" Clashes | MODIFY |  | 2016-01-31 |  | 2016-01-31 |  | 2055 | Med Duty
5011 | MOF | Modify existing scaffold to eliminate "LNG Line" C | Modify existing scaffold to eliminate "LNG Line" Clashes | MODIFY |  | 2016-01-31 |  | 2016-01-31 |  | 2056 | Med Duty
5012 | MOF | Modify existing scaffold to eliminate "LNG Line" C | Modify existing scaffold to eliminate "LNG Line" Clashes | MODIFY |  | 2016-01-31 |  | 2016-01-31 |  | 2057 | Med Duty
5013 | MOF | Modify existing scaffold to eliminate "LNG Line" C | Modify existing scaffold to eliminate "LNG Line" Clashes | MODIFY |  | 2016-01-31 |  | 2016-01-31 |  | 2058 | Med Duty
5014 | MOF | Modify existing scaffold to eliminate "LNG Line" C | Modify existing scaffold to eliminate "LNG Line" Clashes | MODIFY |  | 2016-01-31 |  | 2016-01-31 |  | 2059 | Med Duty
5015 | MOF | Modify existing scaffold to eliminate "LNG Line" C | Modify existing scaffold to eliminate "LNG Line" Clashes | MODIFY |  | 2016-01-31 |  | 2016-01-31 |  | 2060 | Med Duty
5016 | MOF | Modify existing scaffold to eliminate "LNG Line" C | Modify existing scaffold to eliminate "LNG Line" Clashes | MODIFY |  | 2016-01-31 |  | 2016-01-31 |  | 2061 | Med Duty
5017 | MOF | Modify existing scaffold to eliminate "LNG Line" C | Modify existing scaffold to eliminate "LNG Line" Clashes | MODIFY |  | 2016-01-31 |  | 2016-01-31 |  | 2062 | Med Duty
5018 | MOF | Modify existing scaffold to eliminate "LNG Line" C | Modify existing scaffold to eliminate "LNG Line" Clashes | MODIFY |  | 2016-01-31 |  | 2016-01-31 |  | 2063 | Med Duty
5019 | MOF | Modify existing scaffold to eliminate "LNG Line" C | Modify existing scaffold to eliminate "LNG Line" Clashes | MODIFY |  | 2016-01-31 |  | 2016-01-31 |  | 2064 | Med Duty
5021 | MOF | Modify existing scaffold to eliminate "LNG Line" C | Modify existing scaffold to eliminate "LNG Line" Clashes | MODIFY |  | 2016-01-31 |  | 2016-01-31 |  | 2066 | Med Duty

## Scaffold Tag Balances
CompanyName
Import: Scaffold Tag Balances
| Rent Start: | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01
| Job Site: | AAAA | AGRU 2 | UAEA | UAEA | Jetty | GAEA | GAEA | UACB | MOF | MOF | MOF | MOF | MOF | MOF | MOF | MOF | MOF | MOF | MOF | MOF | MOF
| Tag: | 5000 | 5001 | 5002 | 5003 | 5004 | 5005 | 5006 | 5007 | 5008 | 5009 | 5010 | 5011 | 5012 | 5013 | 5014 | 5015 | 5016 | 5017 | 5018 | 5019 | 5021
| Activity: | ERECT | TAKEOVER | ERECT | ERECT | ERECT | ERECT | ERECT | ERECT | MODIFY | MODIFY | MODIFY | MODIFY | MODIFY | MODIFY | MODIFY | MODIFY | MODIFY | MODIFY | MODIFY | MODIFY | MODIFY
PartNumber | Description
101 | x | 3 |  | 0 | 6 | 7 | 3 |  | 0 | 6 | 7 | 3 |  | 0 | 6 | 7 | 3 |  | 0 | 6 | 7 | 3
102 | xx | 7 | 15 | 30 | 8 | 9 | 7 | 15 | 30 | 8 | 9 | 7 | 15 | 30 | 8 | 9 | 7 | 15 | 30 | 8 | 9 | 7
103 | xxx | 4 | 7 | 21 | 10 | 14 | 4 | 7 | 21 | 10 | 14 | 4 | 7 | 21 | 10 | 14 | 4 | 7 | 21 | 10 | 14 | 4
104 | xxxx | 2016-09-01: 14; 2016-09-01: 1; 2016-09-01: 0; 2016-09-01: 14; 2016-09-01: 1; 2016-09-01: 0; 2016-09-01: 14; 2016-09-01: 1; 2016-09-01: 0; 2016-09-01: 14; 2016-09-01: 1; 2016-09-01: 0

## Job Site Balances
CompanyName
Import: Job Site Balances
| Rent Start: | 2016-09-07
| Job Site: | A-True
PartNumber | Description
101 | x | 12
102 | xx | 14
103 | xxx | 16
104 | xxxx | 18